## Store SOW
SECTION H Project Specific Scope of Works
PROJECT NO: |  | N1.2642
PROJECT NAME: |  | GORDONVALE
STATE: |  | QLD
FINANCIAL YEAR: |  | FY22
BLUEPRINT REFERENCE PACK: |  | 2021.1A
STANDARD NOTIFICATIONS INCL: | [8 empty] | 4
Ref: | 4 |  |  |  | DO NOT AMEND - This is the reference of master version you used |  |  |  | 4
Owner: | WW
Version Control | Date | Change Description | Who | Approved
1 | 2020-08-10 | For Tender |  |  | Tender
2 | 2020-05-12 | For Contract | SL | SM | Contract - hide for tender pack
Hide row - for version control only
Hide row - for version control only
Hide row - for version control only
| This document shall be read in conjunction with all drawings and with all other requirements of this tender listed in the "Conditions of Tendering & Standard SOW" including but not limited to: Section 3 – General Issues and Requirements; Section 4 – Selected Sub Contractor Work; and Section 5 – WHS. Note: The following is provided as a guide only, and does not in any way, represent the full or final scope of works to be undertaken by the tenderer. The document is to read in conjunction with all associated Woolworths design and services documents, the associated Blueprint Reference Kit drawings and specifications, and any other document forming part of this tender package. The tenderer is to make their own assessment and allowances of the entire works package based upon all of the provided tender documentation. |  |  |  | Scope | Trade Category | Instructions to PM | Scope included in EA approved cost plan | Track changes
1 | Project Details |  |  |  | Yes | 1. Department |  | Yes
1.01 | Location |  |  |  | Yes | 1. Element |  | Yes
1.02 | Woolworths Supermarket 148 LOGAN RD WOOLLOONGABBA QLD 4102 |  |  |  | Yes | Preliminaries | PM to amend | Yes
1.03 | Store Contact Details |  |  |  | Yes | 1. Element |  | Yes
1.04 | As this is a new store there are currently no Store Manager contact details. |  |  |  | Yes | Preliminaries | PM to consider - new store only | Yes
1.05 | Woolworths Project Manager Details |  |  |  | Yes | 1. Element |  | Yes
1.06 | Construction PM: Michael Allsop Mobile: 0407 211 266 Email: mallsop@woolworths.com.au |  |  |  | Yes | Preliminaries | Select PM from Drop box | Yes
1.07 | All questions relating to the Project including access and/or tender information are to be directed to the Construction Project Manager. |  |  |  | Yes | Preliminaries |  | Yes
1.08 | Equipment PM: Asta Hartley Mobile: 0419 132 268 Email: ahartley@woolworths.com.au |  |  |  | Yes | Preliminaries | Select EPM in Drop box - new store only | Yes
1.09 | The successful Contractor to contact Equipment Project Manager a full list of contacts for Woolworths Equipment suppliers and installation Contractors please contact the Equipment Project Manager, upon successful award. |  |  |  | Yes | Preliminaries | PM to consider - new store only | Yes
1.1 | Lessor Details |  |  |  | Yes | 1. Element |  | Yes
1.11 | Base Build Contractor:ADCO JOHN ANDERSON Mobile: 0447 435 255 Email: janderson@adcoconstruct.com.au |  |  |  | Yes | Preliminaries | PM to amend | Yes
1.12 |  |  |  |  | Yes | Preliminaries | PM to amend | Yes
1.13 | Construction Period |  |  |  | Yes | 1. Element |  | Yes
1.14 | Commence no later than 17th MAY 2022 |  |  |  | Yes | Preliminaries | PM to consider | Yes
1.15 | Practical Completion no later than the 24TH JUNE 2022. |  |  |  | Yes | Preliminaries | PM to consider | Yes
1.16 | Supervision and attendance is to be provided for the duration of construction period stated above. |  |  |  | Yes | Preliminaries | PM to consider - new store only | Yes
1.17 | Tendering Contractors are to submit a proposed construction schedule for the works and the submitted schedule will form part of the evaluation criteria of this tender. |  |  |  | Yes | Preliminaries |  | Yes
1.18 | Tender Submission |  |  |  | Yes | 1. Element |  | Yes
1.19 | Tenders are to be submitted no later than 4.00pm (AEST) on 15TH MARCH 2022. |  |  |  | Yes | Preliminaries | PM to consider | Yes
2 | Preliminaries |  |  |  | Yes | 1. Department |  | Yes
2.01 | Generally |  |  |  | Yes | 1. Element |  | Yes
2.02 | The Works generally comprise the installation of Woolworth’s shop-fixtures, storage fixtures, internal signage, production equipment and service equipment including but not limited to the following: |  |  |  | Yes | Preliminaries |  | Yes
2.03 | WH& S and Site Supervision Coordination and Security. |  |  |  | Yes | Preliminaries |  | Yes
2.04 | Installation of Shop Fixtures and Fittings to the Trading Area. |  |  |  | Yes | Preliminaries |  | Yes
2.05 | Installation of signage to the Trading Area (non-illuminated). |  |  |  | Yes | Preliminaries |  | Yes
2.06 | Installation of Production Equipment to Preparation Areas. |  |  |  | Yes | Preliminaries |  | Yes
2.07 | Daily Cleaning OF ALL AREAS INC AMENITIES AND TRADING FLOOR AND STOCKROOM and Waste Removal. |  |  |  | Yes | Preliminaries |  | Yes
2.08 | Attend meeting prior to Site commencement to ascertain equipment ordering status and additional items required. |  |  |  | Yes | Preliminaries |  | Yes
2.09 | Make contact with relevant stakeholders, arrange and chair weekly Site Meetings with those Stakeholders, who may include but not be limited to Woolworths Equipment PM, Woolworths Construction PM, Woolworths Refit Manager, Woolworths Retail Operations Area Manager, Store Manager, and retail specialists, Woolworths IT Project Delivery Coordinator, Refrigeration Field Engineer, Woolworths Group Investigations Officer (Security). |  |  |  | Yes | Preliminaries |  | Yes
2.1 | Make contact with suppliers to confirm dates for Staff equipment training. Liaise with Store management to ensure required staff attend the training sessions. |  |  |  | Yes | Preliminaries |  | Yes
2.11 | Chair and minute final meeting at the completion of Shopfit period, with all relevant stakeholders to identify any outstanding items and defects. Minutes of all meeting are to be circulated to all stakeholders within 24 hours of the meeting conclusion. |  |  |  | Yes | Preliminaries |  | Yes
2.12 | Base Builder Site Induction Requirements |  |  |  | Yes | 1. Element |  | Yes
2.13 | Tenderer to refer to Attachment G for the "Store Specific Base Builder Site Induction Requirements" set by the Base Builder and include for all additional cost in order to comply. The successful tenderer and their subcontractors are required to complete the Pre-Commencement Assessment that needs to be completed prior to commencement onsite. |  |  |  | Yes | Preliminaries | PM to consider - new store only, must amend to suit | Yes
2.14 | The successful tenderer is required to submit the following items to the Base Builder: • Insurances – Workcover and Public Liability • Company and site supervisor information: o Subcontractor Company Name o Subcontractor ABN o Subcontractor Email Address |  |  |  | Yes | Preliminaries | PM to consider - new store only, must amend to suit | Yes
2.15 | Transition Report |  |  |  | Yes | 1. Element |  | Yes
2.16 | Prior to commencement and prior to completion provide a transition report identifying any incomplete Work by Others for the purpose of: |  |  |  | Yes | Preliminaries |  | Yes
2.17 | Determination by the Construction Project Manager as to whether any attendance will be required. |  |  |  | Yes | Preliminaries |  | Yes
2.18 | Identification to the Refit (Operations) Manager of the Scope of any incomplete work by others and the timing of completion. |  |  |  | Yes | Preliminaries |  | Yes
2.19 | Builders Attendance |  |  |  | Yes | 1. Element |  | Yes
2.2 | The Contractor shall be engaged for the duration of the Works comprising the Equipment Installation period commencing from the Handover Date until the Stocking Period. |  |  |  | Yes | Preliminaries |  | Yes
2.21 | During the Stocking Period the Principal Contractor shall only attend as directed by Woolworths at an additional cost or to supervise incomplete or defective work rectification. Tenderer to submit cost for builder's preliminaries for extended project duration per day and per week for attendance during Stocking Period. |  |  |  | Yes | Preliminaries |  | Yes
2.22 | The Contractor shall attend the site at all times during the Works. The site shall operate in accordance with the incumbent managing contractors schedule. |  |  |  | Yes | Preliminaries |  | Yes
2.23 | The Contractor shall also allow for administration, attendance at the project start up meeting usually held a week prior to handover and meeting / inspection with the Lessor’s base build Principal Contractor for but not limited to the purpose of developing the site specific Project Safety Plan. |  |  |  | Yes | Preliminaries |  | Yes
2.24 | Contract |  |  |  | Yes | 1. Element |  | Yes
2.25 | The Contract shall be the Woolworths AS4000-1997 Contract. The Tenderer shall be given possession of the Site within the Supermarket, under the AS4000 contract for the duration of the fitout period. The overall Project shall remain under the Control of the Developer and his Building Contractor. The tenderer shall allow in his pricing to comply with all directions from the Developer and his Building Contractor during the course of the Equipment Installation period. |  |  |  | Yes | Preliminaries |  | Yes | 3
2.26 | COVID-19 Restrictions |  |  |  | Yes | 1. Element |  | Yes | 4
2.27 | Shopfitter are required to follow Government Guidelines for social distancing, border closure and travel restrictions, Tenderer to include for all additional cost in order to comply. |  |  |  | Yes | Preliminaries | PM to consider | Yes | 4
3 | Scope of Works - Equipment Installation and Shopfitting |  |  |  | Yes | 1. Department |  | Yes
3.01 | The complete installation of all shop-fixtures, storage fixtures, internal signage, service and production equipment as shown on the Drawings and listed in the separate Shopfitting Scope of Works in Attachment E. Tenders should include the following allowances: |  |  |  | Yes | Preliminaries |  | Yes
3.02 | Allocation of fitout start/end dates to be reconfirmed by Woolworths appointed Construction Project Manager (CPM) / Equipment Project Manager (EPM) before commencement. |  |  |  | Yes | Preliminaries |  | Yes
3.03 | Subject to equipment availability and transport issues all equipment will be requested to be on-site within the first two (2) weeks, and fitout should aim to be fully completed by the end of the 3rd week with all defects complete and the store cleaned ready for handover, by the end of the forth week. |  |  |  | Yes | Preliminaries |  | Yes
3.04 | Allow for the possibility of minor modification or rectification of faulty equipment. This should be carried out during the EIS fitout stage and only within the Store Stocking Period if requested by the EPM or CPM, or agreed prior. |  |  |  | Yes | Preliminaries |  | Yes
3.05 | Allow to provide fixings, glues, sealant etc as required to install items where none have been supplied. This must be done in accordance with the manufacturers guidelines, where this information is not available to the contractor for it is essential that the EPM is made aware. |  |  |  | Yes | Preliminaries |  | Yes
3.06 | Purpose Built Units (PBU) and/or Slat wall; measure, supply & Install. Detail for proposed PBUs shall be discussed with the Woolworths Equipment Project Manager for approval prior to manufacture. |  |  |  | Yes | Preliminaries |  | Yes
3.07 | Equipment & Signage may be updated during construction and will need to be installed as per any updates. |  |  |  | Yes | Preliminaries |  | Yes
3.08 | All Shopfitting items included in the Scope of Works affected by late / damaged /missing equipment shall still be carried out until completed, so long as it falls within the duration of the fit out and shall not be subject to additional costs. |  |  |  | Yes | Preliminaries |  | Yes
3.09 | The contractor shall provide sufficient skip bins for removal of all waste from shopfitting operations. No variations will be accepted if insufficient skip bins were allowed in your submission for shopfit scope of works. |  |  |  | Yes | Preliminaries | PM to consider | Yes | 2
3.1 | Allow to undertake a detailed cross check of signage with Décor elevation drawings, advise EPM of any anomalies – this must be undertaken 2 weeks in advance of Shopfit commencement. Advise of any signage clashes with lighting or services. |  |  |  | Yes | Preliminaries |  | Yes
3.11 | Contractor is responsible for receiving and signing for all deliveries and consignments from Woolworths suppliers, and is required to unload all trucks and accept all machinery and equipment on behalf of Woolworths. |  |  |  | Yes | Preliminaries |  | Yes
3.12 | The Contractor shall be responsible for checking completeness of all deliveries and following up short deliveries with the Suppliers. The Contractor shall also check deliveries for damaged equipment and shall advise the Woolworths Equipment Project Manager immediately. |  |  |  | Yes | Preliminaries |  | Yes
3.13 | Shopfitters are to check off all equipment deliveries against Woolworths Purchase order reports, provided by the EPM and place in their relevant departments. |  |  |  | Yes | Preliminaries |  | Yes
3.14 | Short deliveries or missing equipment shall not be accepted as reason for late completion and the Contractor shall use best endeavours to ensure these matters are addressed in a timely manner so the works are not delayed. |  |  |  | Yes | Preliminaries |  | Yes
3.15 | Shopfitters to have a designated Foreman to liaise with EPM on any issues and provide timely notice of missing equipment daily. Including emailing of relevant photos and reports to enable the EPM to order missing supplies and equipment. |  |  |  | Yes | Preliminaries |  | Yes
3.16 | The Tenderer shall provide to their Site Supervisor suitable digital technology to enable the Site supervisor to email photos and reports and minutes, to all and any relevant project stakeholder. |  |  |  | Yes | Preliminaries |  | Yes
3.17 | Contacting relevant Woolworths machinery suppliers to ensure that equipment is available for delivery (supplier list will be provided by the EPM). |  |  |  | Yes | Preliminaries |  | Yes
3.18 | Making arrangement with all suppliers and the Lessor’s contractors for the supply and installation of that equipment, where the equipment is connected into the Site infrastructure. |  |  |  | Yes | Preliminaries |  | Yes
3.19 | Compile Shopfitting departmental defect list including missing equipment issues for circulation to relevant stakeholders. All defects are to be completed prior to the end of the Shopfit period – any defects remaining will be undertaken by the Contractor out of Store working hours. |  |  |  | Yes | Preliminaries |  | Yes
3.2 | 3 days before completion of Shopfit period, co-ordinate with Store staff to collate, catalogue and remove surplus equipment to Stockroom. |  |  |  | Yes | Preliminaries |  | Yes
3.21 | Contractor is to allow for the supply of transport and labour to enable the removal of redundant and surplus equipment to a destination point as instructed by the EPM and prior to Store opening. |  |  |  | Yes | Preliminaries |  | Yes
3.22 | Allow for 2 off 2400x1200 tables, 12 chairs, microwave, fridge, coffee and tea making supplies for the duration of the shop fitout period. Amenities area is to be kept tidy and a thorough clean of the amenities undertaken on a weekly basis. |  |  |  | Yes | Preliminaries |  | Yes
3.23 | Installation shall be completed in accordance with store specific drawings and the Blueprint Reference Pack. |  |  |  | Yes | Preliminaries |  | Yes
3.24 | Shopfitter are required to discard all cardboards into recycle bins provided by Woolworths. |  |  |  | Yes | Preliminaries |  | Yes
3.25 | Shopfitter are required to stack and stockpile all pallets at a location approved by the EPM for collection by Woolworths |  |  |  | Yes | Preliminaries |  | Yes
3.26 | Shopfitter are required to follow Government Guidelines for social distancing, border closure and travel restrictions, Tenderer to include for all additional cost in order to comply. |  |  |  | Yes | Preliminaries | PM to consider | Yes | 4
3.27 | Tenderer to include for installation of hand sanitisers (BOH and Frontend), SCOs dividers and Checkout screens. Please note these items are not indicated on the control plan, shopfitter to allow for installation as per the 2018.1B Blueprint Standard Notifications. |  |  |  | Yes | Preliminaries | PM to consider | Yes | 4
4 | Additional Works Requested by Woolworths CPM |  |  |  | Yes | 1. Department | PM to consider - store specific | Yes
4.01 | Contractor to supply and install Foot mounted door openers to doors of Male and Female Locker room and Toilets.
4.02 | Contractor to install TV Brackets for On Line Pick up TV's, Community TV Bracket on front wall of store and floor mounted Cartoliogy bracket as supplied by WW.
4.03 | Contractor to install Tiger tape Tensa barriers to wall of stockroom as supplied by WW.
4.04 | Contractor to supply and install Tassie Oak boxing around Produce fogging unit mounted on top of Produce case
4.05 | Contractor to install AED Cabinet supplied by WW.
4.06 | Contractor to install all G Track signage supplied by WW.
4.07 | Contractor to install no. 5 off Pin and White boards supplied by WW on walls in stockroom.
4.08 | Contractor to install timber backing panels to support TV Brackets painted to match wall colour in Team Dining room and Planning Office.
4.09 | Contractor to supply and install all boxed in corners indicated on Control Plan by Shopfitter .
4.1 | Contractor to supply and install alum keg rail to wall of Bakery 7 meters long beside cooling racks beside bake oven.
4.11 | Contractor to install Flues provided by others to wall above both deli ovens.
4.12 | Contractor to install On Line Pick up no. 2 off TV BRACKETS as supplied by Techmedia to external walls of Direct to Boot area.
4.13 | Contractor to install service hub.
4.14 | Contractor to supply and install all PBU's indicated on Control Plan.
4.15 | Contractor to install SHIM PLATE for cartology screen
4.16 | Contractor to engage site painter to paint touch up refrigeration pipework ,cash tube installation over checkouts and general paint touch up across project just prior to handover to traders.
4.17
4.18 | Contractor to install timber infills beside Pet food case. |  |  |  | Yes | Preliminaries | PM to consider - store specific | Yes
5 | Coordinate Works by Separate Contractors |  |  |  | Yes | 1. Department |  | Yes
5.01 | Tenderer to allow for management, coordination and attendance of the following Direct Contractors engaged by Woolworths. |  |  |  | Yes | Preliminaries |  | Yes
5.02 | External Safety Auditor |  |  |  | Yes | 1. Element |  | Yes
5.03 | Tenderer to note that Woolworths will engage safety auditor directly, Tenderer to allow for co-ordination with external safety auditor. |  |  |  | Yes | Preliminaries |  | Yes
5.04 | Cash Handling System |  |  |  | Yes | 1. Element |  | Yes
5.05 | Cash Handling System (Cash Vac) Sub-Contractor shall be contracted directly by Woolworths. The Contractor shall co-ordinate the works of the sub-contractor and provide attendance to ensure the works are completed within the Equipment Installation timeframe to the specification and the other requirements detailed herein. |  |  |  | Yes | Preliminaries |  | Yes
5.06 | Public Address System |  |  |  | Yes | 1. Element |  | Yes
5.07 | Public Address Sub-Contractor shall be contracted directly by Woolworths. The Contractor shall co-ordinate the works of the sub-contractor and provide attendance to ensure the works are completed within the Equipment Installation timeframe to the specification and the other requirements detailed herein. |  |  |  | Yes | Preliminaries |  | Yes
5.08 | Intruder Alarm System, Electronic Article Surveillance System, CCTV System and other Security Systems |  |  |  | Yes | 1. Element |  | Yes
5.09 | Security System Sub-Contractor(s) shall be contracted directly by Woolworths. The Contractor shall co-ordinate the works of the sub-contractor and provide attendance to ensure the works are completed within the Equipment Installation timeframe to the specification and the other requirements detailed herein. |  |  |  | Yes | Preliminaries |  | Yes
5.1 | The Contractor shall assist in providing additional supports and ceiling access for supporting CCTV cameras and monitors, being installed by the security contractor. |  |  |  | Yes | Preliminaries |  | Yes
5.11 | The Contractor shall utilise the Intruder Alarm System 24 hours a day, 7 days a week to assist with security to the premises. |  |  |  | Yes | Preliminaries |  | Yes
5.12 | Installation of Production Equipment |  |  |  | Yes | 1. Element |  | Yes
5.13 | Production Equipment such as bakery ovens, chicken cookers, donut machines, etc shall be supplied and installed by Vendors contracted directly by Woolworths. The Principal Contractor shall co-ordinate the works of these Vendors and provide attendance to ensure the works are completed within the Equipment Installation timeframe to the specification and the other requirements detailed herein. |  |  |  | Yes | Preliminaries |  | Yes
5.14 | Installation of Service Equipment |  |  |  | Yes | 1. Element |  | Yes
5.15 | Service Equipment such as the deli queuing system, cash office safes, weighing scales (Wedderburn), etc shall be supplied and installed by Vendors contracted directly by Woolworths. The Principal Contractor shall co-ordinate the works of these Vendors and provide attendance to ensure the works are completed within the Equipment Installation timeframe to the specification and the other requirements detailed herein. |  |  |  | Yes | Preliminaries |  | Yes
5.16 | IT Systems |  |  |  | Yes | 1. Element |  | Yes
5.17 | Installation, commissioning and test of point of sales hardware, computerised equipment and telephones shall be undertaken by various sub-contractors contracted directly to Woolworths. The Contractor shall co-ordinate the works of these Vendors and provide attendance to ensure the works are completed within the Equipment Installation timeframe and other requirements detailed herein. The Contractor shall include their activities in the Shopfitting Period Program of Works. |  |  |  | Yes | Preliminaries |  | Yes
5.18 | Other Sub Contractors |  |  |  | Yes | 1. Element |  | Yes
5.19 | Other sub-contractors may include fire extinguishers (Chubb), hygiene equipment and chemicals (Johnson Diversity), media systems (Torch Media), pallet racking, bailer, etc. These sub-contractors are contracted directly to Woolworths. The Principal Contractor shall co-ordinate the works of these sub-contractors and provide attendance to ensure the works are completed within the Equipment Installation timeframe and other requirements detailed herein. |  |  |  | Yes | Preliminaries |  | Yes
5.2 | Refrigeration |  |  |  | Yes | 1. Element |  | Yes
5.21 | Refrigeration works shall be undertaken by sub-contractors contracted directly to Woolworths. Commissioning of the Refrigeration System shall be undertaken during the Equipment Installation Period. The Contractor shall co-ordinate these works and provide attendance to ensure the works are completed within the Equipment Installation timeframe to the specification and other requirements detailed herein. The Contractor shall include their activities in the Shopfitting Period Program of Works. |  |  |  | Yes | Preliminaries |  | Yes
5.22 | Electrical |  |  |  | Yes | 1. Element |  | Yes
5.23 | The Lessor’s Electrical Sub Contractor shall undertake certain works to connect shop equipment and lighting during the Equipment Installation Period. The Contractor shall co-ordinate these works and provide attendance to ensure the works are completed within the Equipment Installation timeframe to the specification and other requirements detailed herein. The Contractor shall include their activities in the Shopfitting Period Program of Works. The Supermarket Electrical Specification and drawings will be made available to successful Tenderers for coordination purposes. |  |  |  | Yes | Preliminaries |  | Yes
5.24 | Plumbing |  |  |  | Yes | 1. Element |  | Yes
5.25 | The Lessor’s Plumbing Sub Contractor shall undertake certain works to connect production equipment during the Equipment Installation Period. The Contractor shall co-ordinate these works and provide attendance to ensure the works are completed within the Equipment Installation timeframe to the specification and other requirements detailed herein. The Contractor shall include their activities in the Shopfitting Period Program of Works. The Supermarket Hydraulic Specification and drawings will be made available to successful Tenderers for coordination purposes. |  |  |  | Yes | Preliminaries |  | Yes
5.26 | Waste Removal and Cleaning |  |  |  | Yes | 1. Element |  | Yes
5.27 | The Contractor shall keep the premises clean at all times. Rubbish shall be removed daily and not allowed to accumulate within the premises. Amenities and dining facilities shall be kept clean at all times. Amenities shall be maintained with adequate suppliers of toilet paper, soap, hand towels, etc. |  |  |  | Yes | Preliminaries |  | Yes
5.28 | The Contractor shall be responsible and make full allowance for removal of all rubbish from the site. The Shop Fitting Sub-Contractor scope of works includes provision of waste bins for rubbish generated by shop fitting operations only. The Contractor shall ensure the proper disposal of all solid, liquid and gaseous contaminants is undertaken in accordance with all statutory and contractual requirements. |  |  |  | Yes | Preliminaries |  | Yes
5.29 | The Contractor shall coordinate and supervisor the Woolworths engaged cleaning contractor. |  |  |  | Yes | Preliminaries |  | Yes
5.3 | Lessor Defects and Outstanding Works |  |  |  | Yes | 1. Element |  | Yes
5.31 | Provide co-ordination and attendance to permit the completion of any outstanding works, rectification of any defective works and inspection and testing by the Lessor, it’s Principal Contractor, Sub Contractors and Consultants in accordance with the requirements detailed herein. The Woolworths Project Manager will provide a list of building defects resulting from the handover inspection, at commencement of the EIS period, these are to be closed out within 10 days. The Tenderer is to contact both the Principal Contractors and Woolworths nominated contractors to actively manage, coordinate and ensure those defects are being closed out. |  |  |  | Yes | Preliminaries |  | Yes
5.32 | Works During the Stocking Period |  |  |  | Yes | 1. Element |  | Yes
5.33 | Certain works including but not limited to the following shall be undertaken during the stocking period: • Refrigeration system commissioning optimisation and checks • Installation of hygiene equipment and chemicals • Changeover of the keying system • Delivery of shopping trolleys The Contractor shall not be required to manage these Works unless directed by Woolworths CPM. |  |  |  | Yes | Preliminaries |  | Yes
6 | Provisional Sums |  |  |  | Yes | 1. Department | PM to consider | Yes
6.01 | Note: The below Provisional Sums are to be included in the tender sum. |  |  |  | Yes | Provisional Sums | PM to consider | Yes
6.02 |  |  |  |  | Yes | Provisional Sums | PM to consider | Yes
6.03 |  |  |  |  | Yes | Optional Costs | PM to consider | Yes
6.04 | Other - PM to consider |  |  |  | Yes | Optional Costs | PM to consider | Yes
6.05 | Other - PM to consider |  |  |  | Yes | Optional Costs | PM to consider | Yes
7 | Optional Costs |  |  |  | Yes | 1. Department | PM to consider | Yes
7.01 | Note: The below items will not be included in the lump sum tender price but may be considered in the tender award process. |  |  |  | Yes | Optional Costs | PM to consider | Yes
7.02 | WEEKLY RATE FOR PRINCIPAL CONTRACTOR TO REMAIN ON SITE |  |  |  | Yes | Optional Costs | PM to consider | Yes
7.03 | DAILY RATE FOR PRINCIPAL CONTRACTOR TO REMAIN ON SITE IE PER DAY IF NOT IN WEEK BLOCK |  |  |  | Yes | Optional Costs | PM to consider | Yes
7.04 | Other - PM to consider |  |  |  | Yes | Optional Costs | PM to consider | Yes
7.05 | Other - PM to consider |  |  |  | Yes | Optional Costs | PM to consider | Yes

## WW PM
ST | Construction PM: Stephen Tarrant Mobile: 0439 164 821 Email: starrant@woolworths.com.au | JB | Equipment PM: John Barclay Mobile: 0438 716 781 Email: jbarclay@woolworths.com.au
LN | Construction PM: Louise Nelson Mobile: 0428 401 810 Email: lnelson@woolworths.com.au | CG | Equipment PM: Craig Gill Mobile: 0409 716 759 Email: cgill@woolworths.com.au
RJ | Construction PM: Ross Johnson Mobile: 0429 463 647 Email: rjohnson6@woolworths.com.au | JN | Equipment PM: Asta Hartley Mobile: 0419 132 268 Email: ahartley@woolworths.com.au
MA | Construction PM: Michael Allsop Mobile: 0407 211 266 Email: mallsop@woolworths.com.au | CS | Equipment PM: Courtney Stokes Mobile: 0418 579 489 Email: cstokes@woolworths.com.au
MC | Construction PM: Mark Caughley Mobile: 0413 117 717 Email: mcaughley@woolworths.com.au
GP | Construction PM: Gavin Palmer Mobile: 0498 532 951 Email: gpalmer3@woolworths.com.au
JB | Construction PM: John Barclay Mobile: 0438 716 781 Email: jbarclay@woolworths.com.au

## Instructions-How to use (hidden)
Instructions on 'How to use this document'
Please note this document provides a framework to capture the scope of work (SOW) and will need to be modified and customised to suite respective project.
1. Update the project no, name and other details specific to your project.
2. Please ensure to update the texts highlighted in red as per your respective project.
3. Under ‘Scope’ column you have four options to select from, ‘Yes’, ‘No’, ‘Under Options’, ‘Under Provisional Sums’.
4. You can insert additional rows under any heading or sub-heading. Ensure to assign a Trade Category to the newly added row.
5. If a particular department is not applicable to your project, detete the text from column 'I' of the same row to re-number the department headings automatically.
6. Ensure the Department headings are numbered in sequential order, especially when a particular department is not in scope like 'Sushi' or 'Façade Works' etc.
7. Once you have completed identfying scope under each department, filter Scope column and untick the box against iten No. This will huide all the items that don't form part of the SOW for your project.
8. Create a PDF of the SOW document selecting from column A to I and share it under 'Attachment C - SOW and Tender Submission Form'.