## Bakery
Store Name: Woolloongabba | RENEWAL & NEW STORE STORE - DAY WORKS AND NIGHT WORKS
Store Number: 2865 | FITOUT PERIOD AS PER PM'S & BUILDERS PROGRAM |  | V8
Plan Number Tendered On: Control Plan K 10/11/21 | START TBA COMPLETION DATE TBA - SUBJECT TO CHANGE |  | Updated
Date SOW Completed: 08/02/2022 | Shift P to enter a Tick |  | 2020-09-08
BAKERY
Equipment | Fixing method | Tick | Work Done By
Coolroom Racking / Freezer Room / Dry Store Racking | Relocate if required from existing coldrooms to new location as per Control Plan Assemble new if required as per the assembly instructions and locate as per Control Plan Adjust feet to ensure racking is level Install 'SWL' stickers into clip onto each bay Dismantle and dispose of existing racking where directed | Y | Shopfitter
Paper Towel Dispenser (Tork) | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 940mm FFL (bottom) Note - store specific level may need to be confirmed by EPM pending any store specific obstructions. | Y | Shopfitter
Cleaning Cloth Dispenser | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height no higher than the paper towel dispenser Do not install under the draining rack / storage rack above sink | Y | Shopfitter
Wall Bracket for Mop Rack and Brush Rack (Cleaning products) (White) | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 1500mm above floor level for both units | Y | Shopfitter
Hose Reel Holder | Installation location as per Control Plan | Y | Shopfitter/Builder
Knife Holder | Installation location as per Control Plan Fixed using plugs and screws Screws are not to be too tight/flush due to the knife holder design of being removable | Y | Shopfitter
Insectocutor (Vectothor Osprey LED) | "Install as per Control Plan Wall mount a min of 1.8m from the base of the unit to floor level Avoid heat oil and sharp edges Use hardware provided in the kit for installation Excess power cord to be coiled neartly to required length. (Do not cut/trim power cord as this will void warranty) Install to the left of the Power supply" | Y | Shopfitter
Hairnet Dispenser | Install as per plan or EPM location | Y | Shopfitter
Low Height, Naked Bread and Full Height Units | Assemble as per the assembly guidelines and locate as per control plan Dismantle and dispose of existing fixtures where directed. (Renewals only) Relocate existing as per control plan | Y | Shopfitter
Bread Tables/Train | Assemble as per the assembly guidelines and locate as per control plan Dismantle and dispose of existing fixtures where directed. (Renewals only) Relocate existing as per control plan | Y | Shopfitter
Naked Perimeter Wall Unit | Assemble as per the assembly guidelines and locate as per control plan | Y | Shopfitter
Bread Tables/Train Signage | Locate and leave signage on tables for store team installation | Y | Shopfitter
Bulkhead Gantry Signage | Install Hanging Signage as per signage plan. | Y | Shopfitter
Full Height Cabinet G Track Pelmet and Signage (Fresh Made Easy) | Remove, stack and wrap on pallets any existing Fresh Made Easy Signage for reuse Install new or reinstall existing G Track Pelmet as per Fresh Made Easy Guidelines, Signage Plan and G Track Installation Guide Install new or reinstall existing Blank Signage backing boards into Pelmet as per Fresh Made Easy Guidelines Install new or reinstall existing Signage Inserts as per Departmental Plan and Fresh Made Easy Guidelines | Y | Shopfitter
Prepare Accessory Equipment for Checking Off in Bakery | Position equipment in department for checking as per control plan | Y | Shopfitter
Can Opener | Locate as per control plan Fixed to bench using screws and siliconed off |  | Shopfitter
Condiment Rack | Fixed to the wall using plugs and screws Location to be advised by EPM after advice from renewal fresh food coach | Y | Shopfitter
Cooling Trolleys/Racks | Locate as control plan | Y | Shopfitter
Depanning Bench Rubber Replacement | Install onto the existing depanning bench Affix by silicone |  | Shopfitter
Kwik - Lok Machine | Installation location as per Control Plan | Y | Shopfitter
Microwave | Install onto microwave shelf as per control plan | Y | Shopfitter
Microwave Shelf | Relocated microwave shelf as per control plan |  | Shopfitter
Mobile Stainless Steel Benches | Locate as per control plan | Y | Shopfitter
Stainless Steel Brackets & Rail for Tickets | Install 3 x stainless steel rail to back of bakery stainless bench for bakery tickets - store specific location may need to be confirmed by EPM pending any store specific obstructions. | Y | Shopfitter
Stand A4 PLU | Assemble and locate on the bench |  | Shopfitter
2 Door Freezer/Fridge | Allow to unpack freezer/fridge upright doors and install as per control plan |  | Shopfitter
Purpose Built Units / Infill panels | Supply and install of purpose built unit / infills as per Control Plan (matches current kit standards) | Y | Shopfitter

## Deli
Store Name: Woolloongabba | RENEWAL & NEW STORE STORE - DAY WORKS AND NIGHT WORKS
Store Number: 2865 | FITOUT PERIOD AS PER PM'S & BUILDERS PROGRAM |  | V8
Plan Number Tendered On: Control Plan K 10/11/21 | START TBA COMPLETION DATE TBA - SUBJECT TO CHANGE |  | Updated
Date SOW Completed: 08/02/2022 | Shift P to enter a Tick |  | 2020-09-08
DELI
Equipment | Fixing method | Tick | Work Done By
Coolroom Racking | Relocate if required from existing coldrooms to new location as per Control Plan Assemble new if required as per the assembly instructions and locate as per Control Plan Adjust feet to ensure racking is level Install 'SWL' stickers into clip onto each bay Dismantle and dispose of existing racking where directed | Y | Shopfitter
Paper Towel Dispenser (Tork) | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 940mm FFL (bottom) Note - store specific level may need to be confirmed by EPM pending any store specific obstructions. | Y | Shopfitter
Cleaning Cloth Dispenser | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height no higher than the paper towel dispenser Do not install under the draining rack / storage rack above sink | Y | Shopfitter
Wall Bracket for Mop Rack and Brush Rack (Cleaning products) | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 1500mm above floor level for both units | Y | Shopfitter
Hose Reel Holder | Installation location as per Control Plan | Y | Shopfitter/Builder
Knife Holder | Installation location as per Control Plan Fixed using plugs and screws Screws are not to be too tight/flush due to the knife holder design of being removable | Y | Shopfitter
Insectocutor (Vectothor Osprey LED) | Install as per Control Plan Wall mount a min of 1.8m from the base of the unit to floor level Avoid heat oil and sharp edges Use hardware provided in the kit for installation Excess power cord to be coiled neartly to required length. (Do not cut/trim power cord as this will void warranty) Install to the left of the Power supply | Y | Shopfitter
Hairnet Dispenser | Installation location as per Control Plan | Y | Shopfitter
Prep Area - Safety Signage | Install under EPM (or renewal) direction | Y | Shopfitter
Deli Fresh Salad Board (Lazy L) | Locate on the Deli counter | Y | Shopfitter
Low Height Cabinet Gantry Rails and Signage Kit (Fresh Made Easy) | Remove, stack and wrap on pallets any existing Fresh Made Easy Signage for reuse Install new or reinstall existing Gantry Rails as per Fresh Made Easy guidelines and Signage Plan Install new or reinstall existing Blank Signage backing boards onto Gantry Rails as per Fresh Made Easy Guidelines Install new or reinstall existing Inserts as per Departmental Plan and Fresh Made Easy Guidelines | Y | Shopfitter
Full Height Cabinet G Track Pelmet and Signage (Fresh Made Easy) | Remove, stack and wrap on pallets any existing Fresh Made Easy Signage for reuse Install new or reinstall existing G Track Pelmet as per Fresh Made Easy Guidelines, Signage Plan and G Track Installation Guide Install new or reinstall existing Blank Signage backing boards into Pelmet as per Fresh Made Easy Guidelines Install new or reinstall existing Signage Inserts as per Departmental Plan and Fresh Made Easy Guidelines | Y | Shopfitter
Bulkhead Gantry Signage | Install Hanging Signage as per signage plan. | Y | Shopfitter
Prepare Accessory Equipment for Checking Off in Deli | Position in department for checking | Y | Shopfitter
Can Opener | Locate as per control plan Fixed to bench using screws and silicone off |  | Shopfitter
Bench Wrapper | Installation location as per Control Plan | Y | Shopfitter
Slicers | Relocate existing if required as per the control plan | Y | Shopfitter
Purpose Built Units / Infills | Supply and install of purpose built unit / infills as per Control Plan (matches current kit standards) | Y | Shopfitter
Chicken Warmer Unit PBU Cladding | Supply and Install PBU Tassy Oak cladding to unit as per control plan |  | Shopfitter

## Sushi (hidden)
Store Name: Woolloongabba | RENEWAL & NEW STORE STORE - DAY WORKS AND NIGHT WORKS
Store Number: 2865 | FITOUT PERIOD AS PER PM'S & BUILDERS PROGRAM |  | V8
Plan Number Tendered On: Control Plan K 10/11/21 | START TBA COMPLETION DATE TBA - SUBJECT TO CHANGE |  | Updated
Date SOW Completed: 08/02/2022 | Shift P to enter a Tick |  | 2020-09-08
SUSHI
Equipment | Fixing method | Tick | Work Done By
Coolroom Racking | Relocate if required from existing coldrooms to new location as per Control Plan Assemble new if required as per the assembly instructions and locate as per Control Plan Adjust feet to ensure racking is level Install 'SWL' stickers into clip onto each bay Dismantle and dispose of existing racking where directed |  | Shopfitter
Paper Towel Dispenser (Tork) | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 940mm FFL (bottom) Note - store specific level may need to be confirmed by EPM pending any store specific obstructions. |  | Shopfitter
Cleaning Cloth Dispenser | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height no higher than the paper towel dispenser Do not install under the draining rack / storage rack above sink |  | Shopfitter
Wall Bracket for Mop Rack and Brush Rack (Cleaning products) | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 1500mm above floor level for both units |  | Shopfitter
Knife Holder | Installation location as per Control Plan Fixed using plugs and screws Screws are not to be too tight/flush due to the knife holder design of being removable |  | Shopfitter
Insectocutor | Install as per Control Plan Wall mount a min of 1.8m from the base of the unit to floor level Avoid heat oil and sharp edges Use hardware provided in the kit for installation Excess power cord to be coiled neartly to required length. (Do not cut/trim power cord as this will void warranty) Install to the left of the Power supply |  | Shopfitter
Hairnet Dispenser | Installation location as per Control Plan |  | Shopfitter
Prepare Accessory Equipment for Checking Off in Sushi | Position equipment in department for checking off by AFC or Sushi franchisee operator |  | Shopfitter
Demo Desk | Install as per installation guidelines and locate in department |  | Shopfitter
Merchandiser Unit | Install as per installation guidelines and locate as per control plan |  | Shopfitter
Purpose Built Units | Supply and install of purpose built unit / infills as per Control Plan (matches current kit standards) |  | Shopfitter

## Seafood
Store Name: Woolloongabba | RENEWAL & NEW STORE STORE - DAY WORKS AND NIGHT WORKS
Store Number: 2865 | FITOUT PERIOD AS PER PM'S & BUILDERS PROGRAM |  | V8
Plan Number Tendered On: Control Plan K 10/11/21 | START TBA COMPLETION DATE TBA - SUBJECT TO CHANGE |  | Updated
Date SOW Completed: 08/02/2022 | Shift P to enter a Tick |  | 2020-09-08
SEAFOOD
Equipment | Fixing method | Tick | Work Done By
Coolroom Racking/Freezer Room | Relocate if required from existing coldrooms to new location as per Control Plan Assemble new if required as per the assembly instructions and locate as per Control Plan Adjust feet to ensure racking is level Install 'SWL' stickers into clip onto each bay Dismantle and dispose of existing racking where directed | Y | Shopfitter
Paper Towel Dispenser (Tork) | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 940mm FFL (bottom) Note - store specific level may need to be confirmed by EPM pending any store specific obstructions. | Y | Shopfitter
Cleaning Cloth Dispenser | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height no higher than the paper towel dispenser Do not install under the draining rack / storage rack above sink | Y | Shopfitter
Wall Bracket for Mop Rack and Brush Rack (Cleaning products) | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 1500mm above floor level for both units | Y | Shopfitter
Hose Reel Holder | Installation location as per Control Plan | Y | Shopfitter/Builder
Knife Holder | Installation location as per Control Plan Fixed using plugs and screws Screws are not to be too tight/flush due to the knife holder design of being removable | Y | Shopfitter
Insectocutor (Vectothor Osprey LED) | Install as per Control Plan Install to the left of the Power supply Wall mount a min of 1.8m from the base of the unit to floor level Avoid heat oil and sharp edges Use hardware provided in the kit for installation Excess power cord to be coiled neartly to required length. (Do not cut/trim power cord as this will void warranty) | Y | Shopfitter
Hairnet Dispenser | Installation location as per Control Plan | Y | Shopfitter
Low Height Cabinet Gantry Rails and Signage Kit (Fresh Made Easy) | Remove, stack and wrap on pallets any existing Fresh Made Easy Signage for reuse Install new or reinstall existing Gantry Rails as per Fresh Made Easy guidelines and Signage Plan Install new or reinstall existing Blank Signage backing boards onto Gantry Rails as per Fresh Made Easy Guidelines Install new or reinstall existing Inserts as per Departmental Plan and Fresh Made Easy Guidelines | Y | Shopfitter
Full Height Cabinet G Track Pelmet and Signage (Fresh Made Easy) | Remove, stack and wrap on pallets any existing Fresh Made Easy Signage for reuse Install new or reinstall existing G Track Pelmet as per Fresh Made Easy Guidelines, Signage Plan and G Track Installation Guide Install new or reinstall existing Blank Signage backing boards into Pelmet as per Fresh Made Easy Guidelines Install new or reinstall existing Signage Inserts as per Departmental Plan and Fresh Made Easy Guidelines | Y | Shopfitter
Prepare Accessory Equipment for Checking Off in Seafood | Position equipment in department for checking | Y | Shopfitter
Bench Wrapper | Locate as per control plan | Y | Shopfitter
Purpose Built Units | Supply and install of purpose built unit / infills as per Control Plan (matches current kit standards) | Y | Shopfitter

## Meat
Store Name: Woolloongabba | RENEWAL & NEW STORE STORE - DAY WORKS AND NIGHT WORKS
Store Number: 2865 | FITOUT PERIOD AS PER PM'S & BUILDERS PROGRAM |  | V8
Plan Number Tendered On: Control Plan K 10/11/21 | START TBA COMPLETION DATE TBA - SUBJECT TO CHANGE |  | Updated
Date SOW Completed: 08/02/2022 | Shift P to enter a Tick |  | 2020-09-08
MEAT
Equipment | Fixing method | Tick | Work Done By
Coolroom Racking/Dry Store Racking | Relocate if required from existing coldrooms to new location as per Control Plan Assemble new if required as per the assembly instructions and locate as per Control Plan Adjust feet to ensure racking is level Install 'SWL' stickers into clip onto each bay Dismantle and dispose of existing racking where directed | Y | Shopfitter
Paper Towel Dispenser (Tork) | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 940mm FFL (bottom) Note - store specific level may need to be confirmed by EPM pending any store specific obstructions. | Y | Shopfitter
Cleaning Cloth Dispenser | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height no higher than the paper towel dispenser Do not install under the draining rack / storage rack above sink | Y | Shopfitter
Wall Bracket for Mop Rack and Brush Rack (Cleaning products) | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 1500mm above floor level for both units | Y | Shopfitter
Hose Reel Holder | Installation location as per Control Plan | Y | Shopfitter/Builder
Knife Holder | Installation location as per Control Plan Fixed using plugs and screws Screws are not to be too tight/flush due to the knife holder design of being removable | Y | Shopfitter
Insectocutor (Vectothor Osprey LED) | Install as per Control Plan Install to the left of the Power supply Wall mount a min of 1.8m from the base of the unit to floor level Avoid heat oil and sharp edges Use hardware provided in the kit for installation Excess power cord to be coiled neartly to required length. (Do not cut/trim power cord as this will void warranty) | Y | Shopfitter
Hairnet Dispenser | Installation location as per Control Plan | Y | Shopfitter
Low Height Cabinet Gantry Rails and Signage Kit (Fresh Made Easy) | Remove, stack and wrap on pallets any existing Fresh Made Easy Signage for reuse Install new or reinstall existing Gantry Rails as per Fresh Made Easy guidelines and Signage Plan Install new or reinstall existing Blank Signage backing boards onto Gantry Rails as per Fresh Made Easy Guidelines Install new or reinstall existing Inserts as per Departmental Plan and Fresh Made Easy Guidelines | Y | Shopfitter
Full Height Cabinet G Track Pelmet and Signage (Fresh Made Easy) | Remove, stack and wrap on pallets any existing Fresh Made Easy Signage for reuse Install new or reinstall existing G Track Pelmet as per Fresh Made Easy Guidelines, Signage Plan and G Track Installation Guide Install new or reinstall existing Blank Signage backing boards into Pelmet as per Fresh Made Easy Guidelines Install new or reinstall existing Signage Inserts as per Departmental Plan and Fresh Made Easy Guidelines | Y | Shopfitter
Prepare Accessory Equipment for Checking Off in Meat | Position in department for checking | Y | Shopfitter
Stainless Steel and Cutting Benches | Locate as per control plan Adjust feet to ensure benches are level |  | Shopfitter
Holder Info Card 2 Pocket | Install and clip over the wire front of the meat cabinet and shelves |  | Shopfitter
Wall Hook for Ring Spanner | Fixed to the wall near the mincer. Fixed to the wall using plugs and screws and sealed to the wall using silicon. Fixed to the wall at a height of 1800mm above floor level |  | Shopfitter
Purpose Built Units | Supply and install of purpose built unit / infills as per Control Plan (matches current kit standards) | Y | Shopfitter

## Fruit & Veg
Store Name: Woolloongabba | RENEWAL & NEW STORE STORE - DAY WORKS AND NIGHT WORKS
Store Number: 2865 | FITOUT PERIOD AS PER PM'S & BUILDERS PROGRAM |  | V8
Plan Number Tendered On: Control Plan K 10/11/21 | START TBA COMPLETION DATE TBA - SUBJECT TO CHANGE |  | Updated
Date SOW Completed: 08/02/2022 | Shift P to enter a Tick |  | 2020-09-08
PRODUCE MERCHANDISING
Equipment | Fixing method | Tick | Work Done By
Paper Towel Dispenser (Tork) | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 940mm FFL (bottom) Note - store specific level may need to be confirmed by EPM pending any store specific obstructions. | Y | Shopfitter
Cleaning Cloth Dispenser | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height no higher than the paper towel dispenser Do not install under the draining rack / storage rack above sink | Y | Shopfitter
Wall Bracket for Mop Rack and Brush Rack (Cleaning products) | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 1500mm above floor level for both units | Y | Shopfitter
Hose Reel Holder | Installation location as per Control Plan | Y | Shopfitter/Builder
Knife Holder | Installation location as per Control Plan Fixed using plugs and screws Screws are not to be too tight/flush due to the knife holder design of being removable | Y | Shopfitter
Insectocutor | Suspended from the ceiling using stainless steel crimp wire Suspended from the ceiling at a height of minimum of 2400mm above floor level as shown on control plan Installation location as per Control Plan | Y | Shopfitter
Hairnet Dispenser | Installation location as per Control Plan | Y | Shopfitter
Ambient Produce Tables (inc Banana End, Promo Bins and Avocado Table) | Assemble as per the assembly guidelines and locate as per control plan Dismantle and dispose of existing fixtures where directed. (Renewals only) Relocate existing fixtures, if applicable, as per control plan (Renewals only) Ensure end units with bins have doors facing towards rear of store as per control plan | Y | Shopfitter
Berry Case Cladding | Assemble as per the assembly guidelines and install around Berry Case | Y | Shopfitter
Nut Unit Display | Assemble as per the assembly guidelines and locate as per the control plan | Y | Shopfitter
Gantry Rails for Ambient Produce Tables (inc Banana End, Promo Bins, Avocado Table and Berry Case) | Install as per Produce Guidelines | Y | Shopfitter
Timber Price Signage for Ambient Tables | 800mm Boards - Install one per Table and End Table 1100mm Boards - Install one per Promo Table, Avocado Table and Berry Case | Y | Shopfitter
Inspirational Signage for Ambient Tables | Locate on Produce Tables for Store Installation | Y | Shopfitter
Promo Bin Flip Price Signage | Install on front of Promo Bins, Avocado Bin and Berry Cladding | Y | Shopfitter
Low Height Cabinet Gantry Rails and Signage Kit (Fresh Made Easy) | Remove, stack and wrap on pallets any existing Fresh Made Easy Signage for reuse Install new or reinstall existing Gantry Rails as per Fresh Made Easy guidelines and Signage Plan Install new or reinstall existing Blank Signage backing boards onto Gantry Rails as per Fresh Made Easy Guidelines Install new or reinstall existing Inserts as per Departmental Plan and Fresh Made Easy Guidelines | Y | Shopfitter
Full Height Cabinet G Track Pelmet and Signage (Fresh Made Easy) | Remove, stack and wrap on pallets any existing Fresh Made Easy Signage for reuse Install new or reinstall existing G Track Pelmet as per Fresh Made Easy Guidelines, Signage Plan and G Track Installation Guide Install new or reinstall existing Blank Signage backing boards into Pelmet as per Fresh Made Easy Guidelines Install new or reinstall existing Signage Inserts as per Departmental Plan and Fresh Made Easy Guidelines | Y | Shopfitter
Local Source Tables | Assemble as per the assembly guidelines and locate as per the control plan | Y | Shopfitter
Floral units / bag stand | Locate as per Control Plan | Y | Shopfitter
Free Fruit for Kids Stand | Locate as per Control Plan | Y | Shopfitter
Hanging Scale Stand and Extension Pole for Produce Tables | Install as per install guidelines and locate as per Control Plan Relocate existing as per control plan (Renewals Only) | Y | Shopfitter
Bag Holders | Install as per Control Plan onto Ambient Tables Install cabinet bag holders | Y | Shopfitter
Mushroom Bag Holder for Cabinets | Install into mushroom bay | Y | Shopfitter
Console Wrapper on Stand | Locate as per control plan | Y | Shopfitter
Prepare Accessory Equipment for Checking Off in F&V | Position equipment in department for checking | Y | Shopfitter
Old Produce Trading Floor | Dismantle and dump at the tip OR Pack and strap to be relocated to another nominated store by Operations team | Y | Shopfitter
Produce Case Shelving | Install or relocate as per EPM/Refit supplied Planogram | Y | Shopfitter
Fogging/Misting Unit Shroud | Install Fogging Shroud around the Fogging/Misting Unit on top of the case | Y | Shopfitter
Speciality Produce Case Equipment Kits | Assembled as per the assembly guidelines Layout as per EPM/Refit supplied Planogram | Y | Shopfitter
Stainless Steel Brackets & Rail for Tickets | Install 3 x 1mt stainless steel rail to produce wall. Affix to the wall with silicone | Y | Shopfitter
Purpose Built Units / Infill panels | Supply and install of purpose built unit / infills as per Control Plan (matches current kit standards) | Y | Shopfitter

## Frozen Food and Dairy
Store Name: Woolloongabba | RENEWAL & NEW STORE STORE - DAY WORKS AND NIGHT WORKS
Store Number: 2865 | FITOUT PERIOD AS PER PM'S & BUILDERS PROGRAM |  | V8
Plan Number Tendered On: Control Plan K 10/11/21 | START TBA COMPLETION DATE TBA - SUBJECT TO CHANGE |  | Updated
Date SOW Completed: 08/02/2022 | Shift P to enter a Tick |  | 2020-09-08
FROZEN FOOD/DAIRY
Equipment | Fixing method | Tick | Work Done By
Coolroom Racking for Freezer | Relocate if required from existing coldrooms to new location as per Control Plan Assemble new if required as per the assembly instructions and locate as per Control Plan Adjust feet to ensure racking is level Install 'SWL' stickers into clip onto each bay Dismantle and dispose of existing racking where directed | Y | Shopfitter
Coolroom Racking for Dairy | Relocate if required from existing coldrooms to new location as per Control Plan Assemble new if required as per the assembly instructions and locate as per Control Plan Adjust feet to ensure racking is level Install 'SWL' stickers into clip onto each bay Dismantle and dispose of existing racking where directed | Y | Shopfitter
Wall Bracket for Mop Rack (Cleaning products) | Installation location as per Control Plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 1500mm above floor level for both units | Y | Shopfitter
Prepare Accessory Equipment for Checking Off in Perishables | Position equipment in Dairy coldroom for checking |  | Shopfitter
Freezer Jacket Hanging Hooks | Allow to supply a 800mm x 40mm gal rail with 4 hooks to hang freezer jackets. Install at 1700mm FFL. Screw and silicone this to the wall | Y | Shopfitter
Full Height Cabinet G Track Pelmet and Signage | Remove, stack and wrap on pallets any existing Fresh Made Easy Signage for reuse Install G Track Pelmet as per Signage Plan and G Track Installation Guidelines Install blank and price point signage backing boards into Pelmet as per Departmental Plan | Y | Shopfitter
Freezer Coffin G Track Pelmet | Remove, stack and wrap on pallets any existing Fresh Made Easy Signage for reuse Install G Track Pelmet as per Signage Plan and G Track Installation Guidelines Install blank and price point signage backing boards into Pelmet as per Departmental Plan |  | Shopfitter
Purpose Built Units / Infill panels | Supply and install of purpose built unit / infills as per Control Plan (matches current kit standards) | Y | Shopfitter

## Liquor (hidden)
Store Name: Woolloongabba | RENEWAL & NEW STORE STORE - DAY WORKS AND NIGHT WORKS
Store Number: 2865 | FITOUT PERIOD AS PER PM'S & BUILDERS PROGRAM |  | V8
Plan Number Tendered On: Control Plan K 10/11/21 | START TBA COMPLETION DATE TBA - SUBJECT TO CHANGE |  | Updated
Date SOW Completed: 08/02/2022 | Shift P to enter a Tick |  | 2020-09-08
LIQUOR
Equipment | Fixing method | Tick | Work Done By
Coolroom Shelving | Installed OR Relocated as per the control plan Installed level Dismantle and dispose of existing racking where directed. |  | Shopfitter
Paper Towel Dispenser (Tork) | Locate near each hand wash basin Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 940mm FFL (bottom) - store specific level may need to be to be confirmed by EPM pending any store specific obstructions. |  | Shopfitter
Counter Cash Wrap | Installed as per the control plan Installed level All accessories to be installed as per specification Dismantle and dispose of existing Refurbs Only |  | Shopfitter
Cigarette / Miniature Units | Installed as per the control plan Installed level All accessories to be installed as per specification Dismantle and dispose of existing Refurbs Only |  | Shopfitter
Cash Vacuum Pole | Fixed to the wall behind the cash wrap Fixed to the wall using brackets, plugs and screws |  | Shopfitter
Trading Floor Fixtures (High and Low Profile) | Assembled as per the assembly instructions Adjust feet to ensure shelving is level Locate as per control plan |  | Shopfitter
Existing Trading Floor Fixtures Wall Only | Allow to temporary remove/relocate for wall painting Reinstate as per control plan when painting is completed Adjust feet to ensure shelving is level Locate as per control plan |  | Shopfitter
Security Mirrors | Installed in consultation with store manager Locate to assist staff in obtaining a clear view of all areas of the trading floor |  | Shopfitter
Mobile First Aid Kit | Locate in the cash wrap |  | Shopfitter
Liquor Signage | Installed as per departmental signage plan Hanging signage to be suspended using stainless steel crimp wire Suspended at a height of 2100mm above floor level (to underside of the sign) |  | Shopfitter
-External Anti Theft A0 Frames | Fixed to the glass shopfront using double sided tape as provided with the snap frames Fixed to the glass shopfront at a height of 1200mm above ground level (to the underside of the sign) |  | Shopfitter
-Legal Notice Panel | Fixed to the wall using plugs and screws Fixed to the wall at a height of 1200mm above floor level (to the underside of the sign) on a wall adjacent to the cash wrap |  | Shopfitter
Price Points & Frames | Locate as per departmental signage plan |  | Shopfitter
-Low Profile Gondola | Fixed to the centre of Low Profile Fixtures |  | Shopfitter
"Trading Hours" Sign (Single Sided) | Locate as per departmental signage plan Fixed to the wall using plugs and screws Fixed to the wall at a height of 1300mm above floor level (to the underside of the sign) |  | Shopfitter
"Trading Hours" Sign (Doubled Sided) | Suspended from the ceiling as per the departmental signage plan Suspended from the ceiling using stainless steel crimp wire Suspended from the ceiling at a height of 1300mm above floor level (to the underside of the sign) when store has glass front OR Suspended from ceiling at a height of 2700mm above floor level (to the underside of the sign) if in a walkway |  | Shopfitter
Circle Display Units | Locate as per Store Managers instructions Install sign |  | Shopfitter
Security Bottle Holder Kit | Unit is to be pop riveted to the back panel in 4 locations per row. Installed as per installation instructions |  | Shopfitter
Purpose Built Units / Infill panels | Supply and install of purpose built unit / infills in Produce dept as per control plan |  | Shopfitter

## Trading Floor
Store Name: Woolloongabba | RENEWAL & NEW STORE STORE - DAY WORKS AND NIGHT WORKS
Store Number: 2865 | FITOUT PERIOD AS PER PM'S & BUILDERS PROGRAM |  | V8
Plan Number Tendered On: Control Plan K 10/11/21 | START TBA COMPLETION DATE TBA - SUBJECT TO CHANGE |  | Updated
Date SOW Completed: 08/02/2022 | Shift P to enter a Tick |  | 2020-09-08
SUPERMARKET MAIN TRADING FLOOR
Equipment | Fixing method | Tick | Work Done By
Trading Floor Shelving (New Store) | Installation of primary and secondary fixtures throughout the trading floor as per Control Plan, Departmental Plan and Refit Supplied POG's Each bay of punch panel to be Tec screwed (x2) to each T-post. Tec screw locations are notch 34 (1st notch of top panel) Capping shelves to be installed as per standard. Install 510 base supports (drink aisle) Install 750 shelving for Papergoods Install Data Stripping onto all Shelves | Y | Shopfitter
Trading Floor Shelving (Renewal Strip and Build) | Removal of all existing Trading Floor equipment offsite and to be recycle/or dumped unless instructed otherwise Installation of primary fixtures throughout the trading floor as per Control Plan and Departmental Plan. Each bay of punch panel to be Tec screwed (x2) to each T-post. Tec screw locations are notch 34 (1st notch of top panel) Capping shelves to be installed as per standard. Install 510 base supports (drink aisle) |  | Shopfitter
Trading Floor Shelving (510 Secondary Swap) | Installation of Primary Equipment as per Control Plan and Departmental Plan Capping shelves to be installed as per standard. Replace missing post plugs Check gondolas to be removed / relocated / disposed - compare control plan against existing plan Removal of existing equipment offsite and to be recycle/or dumped unless instructed otherwise |  | Shopfitter
Heavy Duty Shelving to Drinks Aisle | Install new Heavy Duty shelving to drinks aisle as indicated on Control Plan as per installation guidelines |  | Shopfitter
Outrigger Removal | Remove and dump old outriggers from all fixtures. | Y | Shopfitter
Pinning T-post | Every second T-post foot to be pinned down and on one side only of gondola for HBB Aisle All single sided fixtures to be pinned down throughout trading floor | Y | Shopfitter
Workstation Gondola/Freestanding | Install workstation as per installation guidelines and located as per control plan | Y | Shopfitter
D pallet kit | Install D pallet kit as per departmental plan |  | Shopfitter
Capping Shelves | Install capping shelves and brackets as per Capping Shelf Standard | Y | Shopfitter
Rolling Existing Gondolas | Please allow to roll gondolas as per builders program - Check with each builder for program when quoting. Relocate Promo and BEM Ends when moving gondolas. Temporary relocate aisle signs as required when rolling gondolas |  | Shopfitter
Existing Wall Gondolas | Allow to remove or temporarily relocate for wall painting Reinstate as per control plan once painted |  | Shopfitter
Cut Shelves | Allow to cut shelves or baskets around all columns where they appear in the gondolas. Allow to brace the cut shelves to the column with angle aluminium. | Y
Remove Light Boxes | Remove existing light boxes (in conjunction with an electrician) |  | Shopfitter
Promo Ends | Remove existing, recycle/or dumped unless instructed otherwise Assemble new as per assembly instructions and locate as per the control plan Allow for retro fitting of all Pelmet Types and Capping Shelf Brackets for support beam | Y | Shopfitter
V Ticket Frames | Fitted to all ends as per control plan (ensure that the frames are installed level) | Y | Shopfitter
Aisle Signs | Install as per the signage plan Suspended from the purlins using stainless steel crimp wire, making sure that it doesn't interfere with overhead lighting at a height of 2400mm above floor level (to the underside of the sign) Category name and number panels to be fitted Wipe down and remove fingerprints Note - When removing existing Aisle Signs check ceiling grid for existing timber supports sitting on top of grid and remove if found Note - when rolling gondolas to temp locations until relays are complete please plan to relocate existing aisle signs as required centred to temp aisles prior to store opening next trading day. | Y | Shopfitter
Street Signs | Install to the top of the T-post as per departmental plan (min 5 bays between street signs and start in the 2nd bay. If the Planogram is more than 15 bays add a 2nd street sign with same name) Slide down arm into T-post and utilise square infill provided or back to back street sign arm | Y | Shopfitter
Display Units | DVD unit - assemble & install as per departmental plan Magazine display units - assemble & install as per departmental plan Scrum units and accessories - assemble & install as per departmental plan. Install graphic inserts for base/mid shelves | Y | Shopfitter
HBB Pelmet | Install HBB Pelmet as per installation guidelines and locate as per Departmental Plan | Y | Shopfitter
HBB G Track Pelmet and Signage Inserts | Install G Track Pelmet and Signage Inserts as per Signage Plan, Departmental Plan and HBB G Track Installation Guidelines | Y | Shopfitter
Cosmetics DLP Signage | Install DLP Cosmetics Signage inserts into G Track Pelmet Connect daisy chain power connections to builder supplied GPO's as per installation guidelines |  | Shopfitter
HBB Illuminated Pelmet | Remove and dump redundant HBB metal pelmet and covers. Install new illuminated Pelmet as per installation guidelines Connect daisy chain power connections to builder supplied GPO's as per installation guidelines | Y | Shopfitter
3.0 Cosmetics Unit | Remove and dump redundant cosmetic equipment Install new 3.0 Cosmetics Unit as per installation guidelines Connect daisy chain power connections to builder supplied GPO's as per installation guidelines | Y | Shopfitter
HBB Halo Light | Install new HBB Halo Light as per installation guidelines | Y
HBB Fins | Install HBB Sigange Fins | Y | Shopfitter
Health Food Pelmet | Install Health Food Pelmet as per installation guidelines and locate as per Departmental Plan and guidence from Refit for descriptions | Y | Shopfitter
Events Pelmet | Install Events Pelmet as per installation guidelines and locate as per Departmental Plan | Y
Gift Card End and Signage | Install or relocate as per control plan Assembled as per install guidelines | Y | Shopfitter
End Panels & Corner Box | Supply & install melamine end panels to the ends of all single sided gondola's where they do not abut a wall and allow for boxing out corners | Y | Shopfitter
Purpose Built Units / Infill panels | Supply and install of purpose built unit / infill's control plan | Y | Shopfitter
Paper Towel Dispenser (Tork) | Install paper towel dispensers as per control plan | Y | Shopfitter

## Checkout Area
Store Name: Woolloongabba | RENEWAL & NEW STORE STORE - DAY WORKS AND NIGHT WORKS
Store Number: 2865 | FITOUT PERIOD AS PER PM'S & BUILDERS PROGRAM |  | V8
Plan Number Tendered On: Control Plan K 10/11/21 | START TBA COMPLETION DATE TBA - SUBJECT TO CHANGE |  | Updated
Date SOW Completed: 08/02/2022 | Shift P to enter a Tick |  | 2020-09-08
CHECKOUT AREA
Equipment | Fixing method | Tick | Work Done By
Checkouts | As per installation instructions Locate as per store control plan Bolted together to make a neat visual finish Installed level All accessory items to be installed as per the installation instructions Fixed to the floor using construction adhesive Check that conveyor is operational prior to leaving site from installation Install There's no need to lift heavy items signage on every conveyor Shopfitters to remove all rubbish Install new Customer Centric Checkout Ends | Y | Shopfitter
Dismantle and remove existing Front End equipment | Dismantle and dispose as required - all redundant equipment to be removed from site |  | Shopfitter
Service Desk Area | As per installation instructions Locate as per store control plan Installed level All accessory items to be installed as per the installation instructions, locate smoke acrylic dividers and isolate for store team Connect power source to Telco unit (by electrical contractor) | Y | Shopfitter
Hand Operated Claxon Siren | Locate in the cupboards of the Service Desk | Y | Shopfitter
Frame For Smoking Kills Sign (State Specific) | Install frame for the sign on bench top over cig units | Y | Shopfitter
Express Checkouts | As per installation instructions Bolted together to make a neat visual finish All accessory items to be installed as per the specification | Y | Shopfitter
Purpose Built Unit | Supply and install of purpose built unit / infill's as per Control Plan (matches current kit standards) | Y | Shopfitter
Tensabarriers | Installed as per installation instructions | Y | Shopfitter
Checkout Service Poles | Installed into recessed section of the checkout and aligned with the ceiling tiles as per installation instructions. Top hat installed to secure poles and cover installation marks (ensure it is inverted into ceiling tiles) Cut and install / or modify to suit the store | Y | Shopfitter
Checkout ID Lights | Fixed to the service poles as per installation instructions Fixed to the service poles using screws and brackets into the pre-drilled holes on the checkout service pole Connected to power source from service pole (by electrical contractor) | Y | Shopfitter
Checkout Merchandisers (Std, Exp & ACO and Mini Merch ACO units) | Install as per control plan. Ensure that all lights are operational | Y | Shopfitter
Checkout and ACO Screen's | Install new or relocate existing Register and ACO's Screens | Y | Shopfitter
Stainless Steel Railing | Fixed to the floor using stainless steel counter sunk dyna-bolts (supplied by shopfitter). Installed as per the store control drawing | Y | Shopfitter
FOS Hand Sanitiser | Locate as per control plan. | Y | Shopfitter
Front-End Fridges | Locate as per control plan. | Y | Shopfitter
Anti Fatigue Mats | Locate at each checkout | Y | Shopfitter
Customer Courtesy Seats | Locate as per control plan | Y | Shopfitter
Mobile First Aid Kit | Locate at service desk | Y | Shopfitter
"Opening Hours" Sign (Single & Double Sided) | Located as per signage plan Add numerals to sign for trading hours. | Y | Shopfitter
"Confectionery Free" Sign | Install as per installation guidelines, leave on kiosk for operation team | Y | Shopfitter
Security Camera Sign | Fixed to the bottom of the security monitor stand | Y | Shopfitter
Recycling Bin | Locate as per control plan | Y | Shopfitter
Wi-Fi, Pick Up, We're Here to Help, Express and Self Service checkouts signage | Suspended from the purlins as per signage plan | Y | Shopfitter
Trolley Bay Legal signage | Installed as per Signage plan | Y | Shopfitter
Managers On Duty Board | Installed as per Signage plan | Y | Shopfitter
Community Notice Board | Installed as per Signage plan | Y | Shopfitter
Plaque Indigenous Acknowledgement | Installed as per Signage plan | Y
Cafe | Locate items as per control plan |  | Shopfitter
Hanging Rails across full store Front end, Fresh Foods and Trading floor | Suspended from the purlins as per Signage Plan (approximately 20-30 per Store) | Y | Shopfitter
AED Unit | Installed as per Control Plan | Y | Shopfitter

## Team Room and Amenities
Store Name: Woolloongabba | RENEWAL & NEW STORE STORE - DAY WORKS AND NIGHT WORKS
Store Number: 2865 | FITOUT PERIOD AS PER PM'S & BUILDERS PROGRAM |  | V8
Plan Number Tendered On: Control Plan K 10/11/21 | START TBA COMPLETION DATE TBA - SUBJECT TO CHANGE |  | Updated
Date SOW Completed: 08/02/2022 | Shift P to enter a Tick |  | 2020-09-08
TEAM DINING ROOM
Equipment | Fixing method | Tick | Work Done By
First Aid Kit | Locate as per control plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 1270mm above floor level | Y | Shopfitter
Lunchroom Tables and Chairs | Assembled as per installation instructions and locate as per Control Plan. Relocate or remove existing | Y | Shopfitter
Lounge Chairs & Coffee Table | Locate as per control plan | Y | Shopfitter
Fridge | Locate as per control plan Relocate or remove existing | Y | Shopfitter
Microwave | Locate on the kitchen bench or In purpose built joinery void space in Kitchenette | Y | Shopfitter
55 inch TV on Wall Bracket (VOC) | Fixed to wall as per control plan Bracket installed as per instructions located in box |  | Shopfitter
55 inch TV on Wall Bracket (Free to Air) | Fixed to wall as per control plan Bracket installed as per instructions located in box | Y | Shopfitter
Island Waste Bins | Locate in lunchroom under Island Kitchen Bench | Y | Shopfitter
Paper Towel Dispenser (Tork) | Locate near each hand wash basin Fixed to the wall using plugs and screws and sealed to the wall using silicon Locate in wash area - 1 in each toilet and 1 in kitchen near the sink | Y | Shopfitter
Door Sign Kit as supplied | Installed as per signage application guide Fixed to the door at 1250mm from finished floor level (to underside of the sign as per AN standard) | Y | Shopfitter
Cubby House | Assembled as per installation instructions and locate as per Control Plan.
AMENITIES & CLEANERS ROOM
Equipment | Fixing method | Tick | Work Done By
Lockers | Assembled as per installation instructions and locate as per Control Plan. Relocate or remove existing | Y | Shopfitter
Shelf with Hanging Coat Rail | Fixed to the lockers as per control plan | Y | Shopfitter
Team bench | Assembled as per installation instructions and locate as per Control Plan. | Y | Shopfitter
Cleaning Room Shelving | Relocate if required from existing location to new location as per Control Plan Assemble new if required as per the assembly instructions and locate as per Control Plan Adjust feet to ensure racking is level Install 'SWL' stickers into clip onto each bay Dismantle and dispose of existing racking where directed | Y | Shopfitter
Mop & Broom Rack | Locate as per control plan Fixed to the wall using plugs and screws. Fixed to the wall at a height of 1500mm above floor level | Y | Shopfitter
Paper Towel Dispenser (Tork) | Locate near each hand wash basin Fixed to the wall using plugs and screws and sealed to the wall using silicon Locate in wash area - 1 in each toilet and 1 in kitchen near the sink | Y | Shopfitter
Wall Bracket for Mop Rack and Brush Rack (Cleaning products) | Locate as per control plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 1500mm above floor level for both units | Y | Shopfitter
Door Sign Kit as supplied | Installed as per signage application guide Fixed to the door at 1250mm from finished floor level (to underside of the sign as per AS standard) | Y | Shopfitter
OFFICES
Equipment | Fixing method | Tick | Work Done By
G12 Cupboard | Locate as per control plan Shelving to be installed | Y | Shopfitter
Fax Machine | Locate in systems office Locate as per control plan | Y | Shopfitter
Hand Operated Claxon Siren | Locate one in general office in G12 | Y | Shopfitter
Filing Cabinets | Locate as per control plan | Y | Shopfitter
Chairs | Locate as per control plan | Y | Shopfitter
Black unit for Cash Vac Capsules | Install on wall near safe at the direction of the EPM | Y | Shopfitter
Prepare Accessory Equipment for Checking Off in Offices | Position equipment in Cashiers Office for checking | Y | Shopfitter
Door Sign Kit as supplied | Installed as per signage application guide Fixed to the door at 1250mm from finished floor level (to underside of the sign as per AS standard) | Y | Shopfitter
TEAM PLANNING ROOM
Equipment | Fixing method | Tick | Work Done By
Planning Table | Locate as per control plan | Y | Shopfitter
Filing Cabinets | Locate as per control plan | Y | Shopfitter
55 inch TV on Wall Bracket | Locate as per control plan TV installed on brackets supplied with unit | Y | Shopfitter
Chairs | Locate as per control plan Relocate or remove existing | Y | Shopfitter
Whiteboards | Locate as per control plan | Y | Shopfitter
Pinboards | Locate as per control plan | Y | Shopfitter
Door Sign Kit as supplied | Installed as per signage application guide Fixed to the door at 1250mm from finished floor level (to underside of the sign as per AS standard) | Y | Shopfitter

## Stockroom and Online
Store Name: Woolloongabba | RENEWAL & NEW STORE STORE - DAY WORKS AND NIGHT WORKS
Store Number: 2865 | FITOUT PERIOD AS PER PM'S & BUILDERS PROGRAM |  | V8
Plan Number Tendered On: Control Plan K 10/11/21 | START TBA COMPLETION DATE TBA - SUBJECT TO CHANGE |  | Updated
Date SOW Completed: 08/02/2022 | Shift P to enter a Tick |  | 2020-09-08
STOCKROOM
Equipment | Fixing method | Tick | Work Done By
Mailbox (Except QLD) | Fixed to the wall in the outside dock area as per control plan. Fixed to the wall using plugs and screws. Fixed to the wall at a height of 1500mm above floor level. |  | Shopfitter
Workstation and Stool | Locate as per control plan. Remove existing. | Y | Shopfitter
Wall Bracket for Mop Rack and Brush Rack (Cleaning products) | Locate as per control plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 1500mm above floor level for both units | Y | Shopfitter
Security Box for Temperature Gun | Installed in the stockroom area near the storeman's workstation as EPM instruction Fixed to the wall using plugs and screws. Fixed to the wall at a height of 1600mm above floor level | Y | Shopfitter
Equipment Reserve Fixture | Install as per installation instructions and locate as per Control Plan SWL plaques to be installed every second upright | Y | Shopfitter
Damaged Stock Fixture | Install as per installation instructions Locate as per control plan SWL plaques to be installed every second upright | Y | Shopfitter
First Aid Kit | Fixed to the wall near the hand basin Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 1270mm above floor level - installation locations not to be visible to customers | Y | Shopfitter
"No Smoking" Sign | Suspended throughout the Stockroom area as per Equipment Project Manager or affixed to a wall 2000mm from floor level | Y | Shopfitter
Stockroom Checkpoints Signs | Suspended or affixed to the wall in the stockroom area as per instruction from Equipment Project Manager at a height of 2000mm FFL (bottom of sign) | Y | Shopfitter
Back Dock External Safety Signage (900x600). Back Dock Dangerous Goods Sign (600x300) | Positioned 3 metres from finished ground level and as per external Signage plan. Fixed to external Wall using plugs and screws 3 metres from floor | Y | Shopfitter
Insectocutor | Suspended from the ceiling using stainless steel crimp wire Suspended from the ceiling at a height of minimum of 2400mm above floor level as shown on control plan | Y | Shopfitter
Hazchem Sign (NSW/QLD only) | Fixed in a prominent position at front and rear entries of the store (for Emergency Services benefit) on discussion and approval with Equipment Project Manager | Y | Shopfitter
Staff Entry Signs | Installed as per kit instructions Fixed to the door at 1500mm above floor level (to underside of the sign) | Y | Shopfitter
Hooks for Freezer Jackets and Kneeling Pads | Provide and install up to 12 hooks for freezer jackets and kneeling pads | Y | Shopfitter
Pallet Racking | New pallet racking locate as per control plan by supplier. Horizontal beams located at 2100mm above floor level. Fixed 300mm from the wall. 2 dyna-bolts in base plate. Column guards installed. 4 dyna-bolts in column protectors. Safety locks on all horizontal beam joins. SWL plaques provided on every second upright | Y | Builder / Shopfitter to Relocate.
Security Cages | Locate as per control plan. | Y | Shopfitter
No Entry or Exit Signs | Install as stores discretion | Y | Shopfitter
CLEANERS ROOM
Equipment | Fixing method | Tick | Work Done By
Cleaning Room Shelving | Assembled as per the assembly instructions and located as per control plan. Adjust feet to ensure racking is level. SWL Plaque = 1 per room | Y | Shopfitter
Mop & Broom Rack | Fixed to the wall in the Cleaners Room in an accessible location as near to wash-up sink as possible. Fixed to the wall using plugs and screws. Fixed to the wall at a height of 1500mm above floor level | Y | Shopfitter
Paper Towel Dispenser (Tork) | Locate near the wash up sink Fixed to the wall using plugs and screws and sealed to the wall using silicon Locate in wash area - 1 in each toilet and 1 in kitchen near the sink | Y | Shopfitter
ONLINE AREA
Equipment | Fixing method | Tick | Work Done By
Racking | Assembled as per the assembly instructions and located as per control plan. Adjust feet to ensure racking is level. SWL Plaque = 1 per room | Y | Shopfitter
Bins | Locate as per Control plan | Y | Shopfitter
Benches and Trolleys | Locate as per Control plan | Y | Shopfitter
Fridges and Freezers | Locate as per Control plan | Y | Shopfitter
Mop & Broom Rack | Fixed to the wall using plugs and screws. Fixed to the wall at a height of 1500mm above floor level | Y | Shopfitter
First Aid Kit | Locate as per control plan Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 1270mm above floor level. Note - installation locations not to be visible to customers | Y | Shopfitter
Insectocutors | Wall mount a min of 1.7 to 2m from the base of the unit to floor level Avoid heat oil and sharp edges Use hardware provided in the kit for installation | Y | Shopfitter
Paper Towel Dispenser (Tork) | Locate near each hand wash basin Fixed to the wall using plugs and screws and sealed to the wall using silicon Fixed to the wall at a height of 940mm FFL (bottom) - store specific level may need to be to be confirmed by EPM pending any store specific obstructions. | Y | Shopfitter

## Extra Tasks
Store Name: Woolloongabba | RENEWAL & NEW STORE STORE - DAY WORKS AND NIGHT WORKS
Store Number: 2865 | FITOUT PERIOD AS PER PM'S & BUILDERS PROGRAM |  | V8
Plan Number Tendered On: Control Plan K 10/11/21 | START TBA COMPLETION DATE TBA - SUBJECT TO CHANGE |  | Updated
Date SOW Completed: 08/02/2022 | Shift P to enter a Tick |  | 2020-09-08
EXTRA SHOPFITTING TASKS
Equipment | Instructions | Tick | Work Done By
Existing FME G-TRACK | Allow to remove all existing, store and reinstall at the end of the program |  | Shopfitter
Workplace Health and Safety | Comply with all WH&S Regulations, Woolworths Destination Zero requirements and directions of the Principal Contractor Maintain work area in a clean and tidy state by removing all rubbish into bins as it is generated | Y | Shopfitter
Forklift/Scissor Lift | Allow for forklift/scissor lift and licensed operator for unloading of delivery trucks and install for signage (Site Specific) | Y | Shopfitter
Purchase Order Report | Allow to check off the purchase order as per department delivery into the store. Supply EPM with updated copy as each department is finished off | Y | Shopfitter
Provision for Skip Bins | The shopfitter/principal contractor shall provide sufficient skip bins for removal of all waste from shopfitting operations & all equipment is to be cleared, kept tidy at all times. Cardboard packaging should be recycled - utilise Woolworths baler. | Y | Shopfitter or Principal Contractor
Additional | The shopfitter shall have the same Site Supervisor / Foreman on site at all times from start to end of fit out. The Site Supervisor will liaise with the Principal Contractor and EPM on any issues and provide timely notices as required. A Site Supervisor shall be supplied with appropriate digital technology to send and receive emails, photographs, minutes, etc. A Site Supervisor shall be available to attend all site meetings as required including pre-commencement meetings. | Y | Shopfitter or Principal Contractor
Signage | Signage scope TBC - allow for hanging aisle signs 2x per aisle and g-track with quick release saddle installation across all cases in the store | Y | Shopfitter
Ceiling Hooks | Allow to remove all redundant ceiling hooks/wires and fixings |  | Shopfitter
Daily Project Reporting | Shopfitter to provide a daily report whilst onsite back to principal contractor, CC'ing EPM via a Site Audit Pro report identifying works completed, defects and damaged equipment. Each daily delivery a store receives, the Shopfitter must report back to the EPM with any missing or damaged equipment including PO/PL no., EQ no. and QTY | Y | Shopfitter
Defects & Outstanding Works | All defects must be completed prior to the end of the Equipment Install period. Any defects outstanding beyond this period shall be completed at a time as directed by the EPM | Y | Shopfitter
Excess Equipment | All excess equipment not required to be installed, must be, packed, strapped, wrapped, palletised and labelled with EQ number, QTY in full order multiple and description of the equipment. This information must be then sent onto the EPM so a pick-up and return to 3PL can be arranged. All unwanted equipment must be removed from site for a clean handover to the operations team. Any equipment that is not packed to the Woolworths standards as mentioned above, will be rejected by the truck driver and the shopfitter will be charged with costs for futile trip. Under no circumstances should anything not on the equipment transfer form be returned without EPM permission. | Y | Shopfitter/EPM
Empty Pallet Returns | All WOW pallets must be collected and returned to 3PL unless otherwise advised. All pallets must be counted and stacked neatly with no more than 15 to be collected at a time organised through EPM. | Y | Shopfitter/EPM
Extra Hardware | Allowance must be made for additional hardware such as nuts, bolts, crimps, etc, for signage and equipment | Y | Shopfitter
Forklift/Scissor Lift | Allow for forklift/scissor lift and licensed operator for unloading of delivery trucks and install for signage (Site Specific) | Y | Shopfitter
General Including Work Flows & Completion Timeframes | Allow a cost for five (5) full separate or consecutive days of labour by two (2) shopfitters to install various shopfittings and perform miscellaneous shopfitting tasks over and above the items listed on the Scope of Works. Actual date / dates will be advised by Project Manager - Note, shopfitting completion timeframes and attendance may not be concurrent - resources need to be provided when requested by WW to attend site to meet unplanned equipment delays, late orders, late deliveries. If project is a refurb this is to be costed at after hour rates | Y | Shopfitter
Installation | Allow for the possibility of minor modifications or rectification of any faulty equipment | Y | Shopfitter
Provision for Skip Bins | The shopfitter/principal contractor shall provide sufficient skip bins for removal of all waste from shopfitting operations & all equipment is to be cleared, kept tidy at all times. Cardboard packaging should be recycled - utilise Woolworths baler. | Y | Shopfitter or Principal Contractor
Purchase Order Report | Allow to check off the purchase order as per department delivery into the store. Supply EPM with updated copy as each department is finished off | Y | Shopfitter
Rubbish Removal | Removal of all packaging and redundant equipment not required as nominated by the EPM. Rubbish shall be removed from the work area as it is generated. | Y | Shopfitter
Supervision | The shopfitter shall have the same Site Supervisor / Foreman on site at all times from start to end of fit out. The Site Supervisor will liaise with the Principal Contractor and EPM on any issues and provide timely notices as required. A Site Supervisor shall be supplied with appropriate digital technology to send and receive emails, photographs, minutes, etc. A Site Supervisor shall be available to attend all site meetings as required including pre-commencement meetings. | Y | Shopfitter
Travel Allowance and Accommodation | Allowance for travel and accommodation if project is outside any metro area - non local travel time is not to be included in standard working hours onsite |  | Shopfitter
Unloading of Truck | Allow for unloading of all equipment off trucks throughout duration of project and checking of equipment against PO Listing supplied prior to delivery. All discrepancies against the delivery schedule provided must be addressed with the EPM within 24 hours of receipt. | Y | Shopfitter
Waterproof Protection to Cover External Renewal Equipment | Shopfitter to provide sufficient protection to be utilised to cover renewal equipment removed daily and to ensure renewal equipment is protected from all external elements. | Y | Shopfitter
Workplace Health and Safety | Comply with all WH&S Regulations, Woolworths Destination Zero requirements and directions of the Principal Contractor Maintain work area in a clean and tidy state by removing all rubbish into bins as it is generated | Y | Shopfitter