## Estimation
Construction Data Extraction - Project Estimation
Project Task / Activity Description | Effort in Hours | Cost per Hour | Total Cost | Remarks | Phase Summary | Cost
Analysis and Planning |  |  |  |  | Analysis and Planning | 0
Analyze the documents and categorize by complexity (Easy/Medium/Hard) . Examples from Samples Easy- : DA Decision Notice, Project Brief → Direct text extraction Medium - Architectural drawings, Approved Plans → OCR + Table detection required Hard - Survey Plan → Image enhancement + dimension calculation | 24 |  |  |  | Core Extraction Pipeline | 0
Document type classification: DA Approval, Architectural, Brief/Report, Other Categorizes documents by type: - DA Approval (Development Approval) - Brief/Report - Architectural - Construction - Other - Priority-based data aggregation: - **GFA**: DA Approval > Brief/Report > Architectural - **Site Area**: DA Approval > Architectural > Brief/Report - **Levels**: Architectural > DA Approval > Brief/Report | 16 |  |  | Automated classification | Advanced Features | 0
Identify document coverage gaps and flag incomplete projects | 16 |  |  | Quality check before processing | Production Features | 0
Create extraction priority matrix (which doc types for which metrics) | 16 |  |  | DA→GFA, Arch→Levels | Integration and QA | 0
Design confidence for each of the 4 Deliverables - Levels (Above Ground) Levels (Below Ground) Gross Floor Area External Area | 24 |  |  | Flag low-confidence for review | Project Management | 1800
[5 empty] | Infrastructure | 0
Development - Core Extraction Pipeline
Multi-Document Processing ( Python/Docling/PDF Readers) |  |  |  |  | TOTAL | 1800
Implement multi-PDF reader for projects | 40
Document type classifier using filename patterns and content | 32
Cross-document validation and conflict resolution | 32 |  |  | When values differ
Levels Extraction (Above & Below Ground)
Pattern matching for architectural drawings (LEVEL X, BASEMENT, B1) | 24
Fallback extraction from DA Approval documents | 16 |  |  | Secondary source
Handle edge cases: Split levels, mezzanines, sub-basements | 24 |  |  | Complex projects
GFA (Gross Floor Area) Extraction
Direct text extraction from DA Approval documents | 32 |  |  | Better source
Table detection and area schedule parsing | 64
Multi-page table continuation handling | 24 |  |  | Tables split across pages
Unit normalization (sqm, sqft, hectares) | 16 |  |  | Convert all to sqm
GFA term variations (Total Floor Area, NLA, Lettable Area) | 24 |  |  | Different terminology
Site Area Extraction
Extract from DA Approval (primary source) | 24 |  |  | Highest reliability
Fallback to architectural site plans | 24 |  |  | Secondary source
Parse dimensions from survey plans for calculation | 32 |  |  | When not stated explicitly
External Area Calculation
Implement formula: External Area = Site Area - GFA | 16 |  |  | Derived metric
Validation logic for negative or impossible values | 16 |  |  | Sanity checks
Development - Advanced Features
Enhanced OCR and Image Processing
Implement Docling AI for document understanding | 40
RapidOCR integration for text extraction | 32 |  |  | Handle scanned docs
Image enhancement: denoising, contrast, deskewing | 40 |  |  | Improve OCR quality
Handle low-quality scans and rotated documents | 32 |  |  | Pre-processing
LLM Validation (High Impact)
Integrate OpenAI GPT-4 or Claude API for GFA extraction | 48 |  |  | Priority 1 - +10% accuracy
Design prompts for metric extraction | 32 |  |  | Fallback strategy
GPT-4 Vision API for architectural drawing interpretation | 48 |  |  | Parse visual layouts
Cross-validation: LLM checks extracted values for sanity | 32 |  |  | Quality assurance
Dimension-Based GFA Calculation
Parse dimensions from architectural floor plans | 64 |  |  | Fallback when not stated
Scale detection and conversion (1:100, 1:50 scales) | 40 |  |  | Read drawing scales
Calculate floor area from parsed dimensions | 40 |  |  | Geometric calculation
Handle complex geometries (L-shapes, curved buildings) | 32 |  |  | Advanced cases
Document Quality Classification
ML model for Easy/Medium/Hard complexity classification | 56
Feature extraction: scanned vs digital, image quality, text density | 40 |  |  | Classification inputs
Auto-route to appropriate extraction strategy per document | 32 |  |  | Easy→Text, Hard→OCR+LLM
Smart Document Filtering
Pre-filter equipment specs and irrelevant documents | 32 |  |  | Skip 37% of "Other" docs
Flag projects with insufficient documentation before processing | 24 |  |  | Avoid wasted effort
Generate document request list for incomplete projects | 16 |  |  | Client communication
Integration and QA
Human-in-the-Loop Interface
Design Streamlit web interface for project upload and review
Implement review workflow for flagged values
Add manual correction and feedback collection
Project Management
Project manger | 0
Business Analyst | 0
Infrastructure and DevOps
| Virtual Machine |  | 1000
| OpenAI Cost |  | 800
1800
TOTAL ESTIMATED COST