## Line_items_estimate (hidden)
Stage | Task | Description
Planning | Analysis of Input Sources and Schema Alignment | Review input types (emails, PDFs, DOCX, HTML pages) and align to the unified Real Deals schema for structured extraction.
Planning | Evaluation of Parsing Options | Assess extraction options using unstructured.io, PDF parsers, and web scrapers for consistent text and metadata capture.
Planning | RAG Pipeline Planning and Architecture | Design retrieval-augmented extraction flow – embeddings, retrievers, schema-driven prompts, and output validation layer.
Planning | Analysis of Editorial Summary Requirements | Study article structure and Real Deals writing tone for integration into two-stage summary generation.
Planning | Confidence Framework & Validation Rules | Define confidence scoring logic and schema validation rules (Pydantic + Guardrails AI).
Development | Setup of Document Pre-processing Pipeline | Build pipeline for text extraction, HTML/PDF parsing, cleaning, and markdown conversion.
Development | Embedding and Indexing for RAG | Create vector embeddings of extracted content and store in FAISS/Chroma with metadata.
Development | Schema-Guided RAG Extraction Setup | Implement retrieval + prompt-based extraction for all key data fields (Target, Sponsor, Sector, Value, etc.).
Development | Prompt Engineering and Schema Validation | Develop structured prompts for each field and validate model outputs via Pydantic schema enforcement.
Development | Post-processing and Field Normalization | Add normalization (currency, region, value range) and enrichment logic.
Development | Auto-Summary Template Creation (Stage 1) | Implement auto-generated summary layer based on structured data placeholders.
Development | Editorial Refinement Model (Stage 2) | Develop AI-based editorial polish module to rewrite Stage 1 outputs in Real Deals tone.
Development | Integration Setup with CMS & Database | Map structured outputs and summaries to Azure SQL + ExpressionEngine CMS via API connector.
Development | Evaluation and Fine-tuning of Extraction Accuracy | Run iterative validation and prompt tuning to improve per-field extraction confidence.
Development | End-to-End Testing & Handover | Validate the full flow from input file → structured extraction → polished summary → CMS draft.

## Consolidated Cost for Proposal
Description | Cost | Comments
Discovery, Analysis and Planning | FOC | Covered in POC |  | Discovery, Analysis and Planning |  |  | Solution Architect Split | Margin Split AI | Margin Split Scraping
Solution Design and System Set up | 3474.9 |  |  | Solution Design and System Set up | 2200 | 880 | 150.2 | 184.54 | 60.16
ScrapeX configuration – cXX sources | 2376 |  |  | ScrapeX configuration – cXX sources | - | 2376
AI/ML solution using KIAA framework - classifier, semantic de-duping, data mining | 9414.5 |  |  | AI/ML solution using KIAA framework - classifier, semantic de-duping, data mining | 7440 |  | 751 | 922.7 | 300.8
Solution Testing /QA (Tech) | 3878.6 |  |  | Solution Testing /QA (Tech) | 2500 | 739 | 150.2 | 369.08 | 120.32
Data Transformation, Logging, Alerts, Reports and Delivery | 704 |  |  | Data Transformation, Logging, Alerts, Reports and Delivery |  | 704
Solution Integration and Deployment | 4021.8 |  |  | Solution Integration and Deployment | 2880 | 352 | 300.4 | 369.08 | 120.32
Documentation | FOC |  |  | Documentation | FOC | FOC
Project Management | FOC |  |  | Project Management | FOC | FOC
Total Solution Set Up / Configuration Costs | 23869.8 |  |  | Buffer For Contingencies | 1502 | 505
|  |  |  | Infrastructure | 430 | 460
Buffer For Contingencies | 2007 |  |  |  | 16952 | 6016
|  |  |  | Solution Architecture | 1502
Total Infra Costs | 890 | Covered in Appendix IV |  | Total | 18454 | 6016
|  |  |  | Margin | 20299.4 | 6617.6
Total Cost of Solution Customisation / Configuration | 26766.8 |  |  | Using our propieratory product ScrapeX we have saved XX% and by
|  |  |  | Savings using Merits accelerators | 1845.4 | 601.6
Infrastructure + token costs ( * Approximate one time Set up cost for development but will be charged on actuals)
Total Infra cost for initial phase |  |  |  | 430
Virtual Machine(Ubuntu) - On-prem --Per Month cost - 1 A6 (4 Cores, 28 GB RAM) x 720 Hours (Pay as you go), Linux, (Pay as you go); 0 managed disks – S4; Inter Region transfer type, 5 GB outbound data transfer from UK South to East Asia | 8 Cores, 16 GB RAM, 150 GB Temporary Storage 256 SSD |  |  | 320
Open AI - token cost
Average Token cost per document (based on current pricing of openAI and the samples provided) - mainly GPT5 |  |  |  | 0.11
- 40 *25 days = 1000 |  |  | 0 | 1000
Overall token cost for PoC |  |  |  | 110
BAU - Ongoing Recurring Cost - monthly
Average Token cost per document (based on current pricing of openAI and the samples provided) - Alternate between usage of 4o, o3 and o4-mini based on type of response |  |  |  | 0.11
Projected # of documents per month |  |  |  | 1000
Overall token costs per month |  |  |  | 110
Support and Maintenance (Tech Resources) - 0.25 FTE ML engineer per month | 30 | 30 |  | 875
Virtual Machine(Ubuntu) - On-prem | 8 Cores, 16 GB RAM, 150 GB Temporary Storage 256 SSD |  |  | 0
Solution running cost
BAU - Ongoing Recurring Cost - monthly |  |  |  | 985

## AIML_cost
A. Customisation and Deployment of Solution - One off Cost
AIML Solution - Document Classification & Information Retrieval | [6 empty] | Type | Stage |  |  | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8
Description | hrs_simple | hrs_medium | hrs | Cost per hour | total_cost |  | Scraping | End to End Scraping |  |  | Week1: Week 1; Week2: Week 2; Week3: Week 3
Planning - Customising AIML Framework for current requirement |  |  | 88 |  | 2200 |  | AI/ML | Planning - Customising AIML Framework for current requirement | 12.5714 | 1.2571 | Week1: Week 1; Week2: Week 2
Analysis of Input Sources and Schema Alignment |  | 16 | 8 | 25 | 200 |  |  | Development - AIML Framework | 35.4286 | 3.5429 | Week3: Week 3; Week4: Week 4; Week5: Week 5; Week6: Week 6
Assess extraction options using unstructured.io, PDF parsers, and web scrapers for consistent text and metadata capture. |  | 24 | 16 | 25 | 400 |  |  | Integration Effort | 13.7143 | 1.3714 | Week7: Week 7; Week8: Week 8
Design retrieval-augmented extraction flow – embeddings, retrievers, schema-driven prompts, and output validation layer. |  | 16 | 32 | 25 | 800
Analysis of Editorial Summary Requirements - Study article structure and Real Deals writing tone for integration into two-stage summary generation. |  | 24 | 24 | 25 | 600
Define confidence scoring logic and schema validation rules (Pydantic + Guardrails AI). |  | 24 | 8 | 25 | 200
Project Mgmt cost - Planning |  |  | 0 |  | 0
Solution Architect Effort |  |  | 0 | 40 | 0
PM Effort |  |  | 0 | 25 | 0
BA Effort |  |  | 0 | 25 | 0
Development - AIML Framework |  |  | 248 |  | 7440
Setup of Document Pre-processing Pipeline - Build pipeline for text extraction, HTML/PDF parsing, cleaning, and markdown conversion. |  |  | 16 | 30 | 480
Embedding and Indexing for RAG |  |  | 24 | 30 | 720
Schema-Guided RAG Extraction Setup - Implement retrieval + prompt-based extraction for all key data fields (Target, Sponsor, Sector, Value, etc.). |  |  | 56 | 30 | 1680
Prompt Engineering and Schema Validation - Develop structured prompts for each field and validate model outputs via Pydantic schema enforcement. |  |  | 32 | 30 | 960
Post-processing and Field Normalization - Add normalization (currency, region, value range) and enrichment logic. |  |  | 24 | 30 | 720
Auto-Summary Template Creation (Stage 1) - based on structured data placeholders. |  |  | 24 | 30 | 720
Editorial Refinement Model (Stage 2) - Develop AI-based editorial polish module to rewrite Stage 1 outputs in Real Deals tone. |  |  | 24 | 30 | 720 |  |  | Discovery, Analysis and Planning
Map structured outputs and summaries to Azure SQL + ExpressionEngine CMS via API connector. |  |  | 24 | 30 | 720 |  |  | Solution Design and System Set up | 2200 | 880
Evaluation and Fine-tuning of Extraction Accuracy |  |  | 24 | 30 | 720 |  |  | ScrapeX configuration – cXX sources | - | 2464
Integration Effort |  |  | 96 |  | 2880 |  |  | AI/ML solution using KIAA framework - classifier, semantic de-duping, data mining | 7440 | -
Azure SQL Database (structured storage for extracted fields) ExpressionEngine CMS (publishing layer for editorial summaries) |  |  | 64 | 30 | 1920 |  |  | Solution Testing /QA (Tech) | 2500 | 756
Integration testing |  |  | 32 | 30 | 960 |  |  | Data Transformation, Logging, Alerts, Reports and Delivery |  | 440
Documentation - AIML Framework |  |  | 0 |  | 0 |  |  | Automated Validation Checks
Code Standardization |  |  | 0 | 25 | 0 |  |  | Solution Integration and Deployment | 2880 | 352
Code Documentation |  |  | 0 | 25 | 0 |  |  | Documentation | 600 | 0
Documentation - user manual |  |  | 0 | 25 | 0 |  |  | Project Management | 3124 | 0
Testing - AIML Framework |  |  | 100 |  | 2500 |  |  | Buffer For Contingencies | 1562 | 490
Unit testing | 14 | 24 | 50 | 25 | 1250 |  |  | Infrastructure | 430 | 460
Data quality | 14 | 24 | 50 | 25 | 1250 |  |  |  | 20736 | 5842
Total Production Man Hours |  |  | 532
Total Cost |  |  |  |  | 15020
Solution Architect Effort @ 0.1 |  |  | 0 | 0 | 1502
PM Effort @ 0 |  |  | 0 | 0 | 0 |  |  | 532 |  | 4 sources
BA Effort @ 0 |  |  | 0 | 0 | 0 | 5 |  | 8
Contingency @ 0.1 |  |  | 107 | 22 | 1502 |  |  | 66.5
Grand Total - One time setup Cost |  |  |  |  | 18024 |  |  | 3.1667
1.5833
Infrastructure + token costs ( * Approximate one time Set up cost for development but will be charged on actuals)
Total Infra cost for initial phase |  |  |  |  | 280
Virtual Machine(Ubuntu) - AMD EPYC 9554 - CPU-8x-32GB | 8 Cores, 16 GB RAM, 150 GB Temporary Storage 256 SSD |  |  |  | 170
Open AI - token cost
Average Token cost per document (based on current pricing of openAI and the samples provided) - mainly GPT5 |  |  |  |  | 0.11
- 40 *25 days = 1000 |  |  |  |  | 1000
Overall token cost for PoC |  |  |  |  | 110
BAU - Ongoing Recurring Cost - monthly
Average Token cost per document (based on current pricing of openAI and the samples provided) - Alternate between usage of 4o, o3 and o4-mini based on type of response |  |  |  |  | 0.11
Projected # of documents per month |  |  |  |  | 1000
Overall token costs per month |  |  |  |  | 110
Support and Maintenance (Tech Resources) - 0.25 FTE ML engineer per month | 30 | 30 |  |  | 750
Virtual Machine(Ubuntu) - AMD EPYC 9554 - CPU-8x-32GB | 8 Cores, 16 GB RAM, 150 GB Temporary Storage 256 SSD |  |  |  | 170
Solution running cost
BAU - Ongoing Recurring Cost - monthly |  |  |  |  | 1030

## DataHarvesting_cost
Robust Solution Development for Deals Extraction
I. Design, Development and Deployment of Solution - One off Cost
S.No | Project Task / Activity Description | Cost per hour | Effort in Hours | Total Cost
1 | Planning, Design and System Set up | 22 | 40 | 880
1.2 | Solution Approach (System Architecture and Database Design) |  | 24
1.3 | Infrastructure Setup |  | 16
2 | Scraper Development/Configuration | 22 | 108 | 2376
2.1 | 40 Sources Scraper development |  | 72
2.2 | Data collection from email subscriptions |  | 28
2.3 | Open Search(Google OpenSearch limited to first 10 pages to identify relevant base articles or leads) |  | 8
2.4 | Organisation Details Extraction(Trade or Registered company name, Turnover, Revenue (Profit), Sectors, Region (deal level).) |  | 16
3 | Data Transformation, Logging, Alerts, Reports and Delivery | 22 | 32 | 704
3.1 | Download and Upload processed files(Raw responses will be stored in Blob storage) |  | 12
3.2 | Content DeDuping |  | 8
3.4 | Logging |  | 12
4 | Data Quality & Validation | 22 | 12 | 264
4.1 | Automated Checks - Data Validation
5 | UAT Issue Fixes | 22 | 21.6 | 475.2
6 | Integration and Deployment | 22 | 16 | 352
7 | Documentation | 22 | 0 | 0
8 | Project Management | 22 | 0 | 0
8.1 | Project Management Charges(PM and BAs)
| Total Estimated Hours | 22 | 229.6 | 5051.2
| Buffer for Contingencies(10%) | 22 | 22.96 | 505.12
| Infrastructure Charges During Set Up |  |  | 460
| Total Set Up Costs |  | 252.56 | 6016.32
* Note :Costs will be impacted if scraper schedule changes to daily/ monthly or any other custom schedule
BAU - Deals Extraction(*Daily)
Infrastructure Details | [7 empty] | Proxy Services
S.No | Infrastructire Charges During POC | FTE Count | Cost(Azure and third party services) |  | 0.1 | 350 | 535 | Virtual Machine(Ubuntu)
1 | Tech Support | 0.15 | 450 |  | 0.25 | 875 | 110 | DataBase
S.No | Infrastructire Charges During POC |  | Cost(Azure and third party services) |  |  |  |  | Storage
1 | Proxy Services | Region specific proxies | 60 | Will be billed on actuals |  |  |  | Backup
2 | Virtual Machine(Ubuntu) | AMD EPYC 9554 - CPU-4x-16GB | 100 | Will be billed on actuals |  |  |  | Serper(Open Search)
3 | DataBase | D Series, 4 vCore, £0.2955/hour | 275 | Will be billed on actuals |  |  |  | Virtual Machine(Ubuntu) - AMD EPYC 9554 - CPU-8x-32GB
4 | Storage |  | 20 | Will be billed on actuals |  |  |  | Open AI - token cost
5 | Backup |  | 20 | Will be billed on actuals
6 | Serper(Open Search) |  | 60 | Subscription cost
Total Monthly Cost |  |  | 985

## Infrastructure_Details
Robust Solution Development for Finding Land Purchase deals(Datacenters)
Infrastructure Details
S.No | Infrastructire Charges During POC |  | Cost(Azure and third party services)
1 | Proxy Services | Region specific proxies | 60 | Will be billed on actuals
2 | Virtual Machine(Ubuntu) | AMD EPYC 9554 - CPU-4x-16GB | 100 | Will be billed on actuals
3 | DataBase | D Series, 4 vCore, £0.2955/hour | 200 | Will be billed on actuals
4 | Storage |  | 20 | Will be billed on actuals
5 | Backup |  | 20 | Will be billed on actuals
6 | Serper(Open Search) |  | 60 | Subscription cost
AI/ML Infra
1 | GPU Machine
2 | Open AI Key
Total Monthly Cost |  |  | 460

## Resource Loading Sheet
Type | Stage | Days | Weeks | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8
Scraping | End to End Scraping |  |  | Week 1 | Week 2 | Week 3
AI/ML | Planning - Customising AIML Framework for current requirement | 12.5714 | 1.2571 | Week 1 | Week 2
| Development - AIML Framework | 35.4286 | 3.5429 |  |  | Week 3 | Week 4 | Week 5 | Week 6
| Integration Effort | 13.7143 | 1.3714 | [6 empty] | Week 7 | Week 8

## AIML_workflow
Web & Document Collection
Automatically capture deal announcements, press releases, and updates from company websites, investor pages, and emails.
Support multiple formats such as .eml, .pdf, .docx, and .html.
Record key source metadata (URL, publication date, document type) for tracking and auditability.
Content Parsing & Structuring
Extract readable text from varied file types using automated parsing tools.
Clean and organize content to remove non-informative sections like disclaimers, footers, and hyperlinks.
Segment text into logical sections (e.g., company background, deal rationale, financials) to improve AI accuracy.
AI-Powered Data Extraction
Apply a Retrieval-Augmented Generation (RAG) pipeline aligned to a pre-defined schema.
Automatically identify and extract key entities (e.g., Target, Sponsor, Fund, Seller) and financial data (Deal Value, Turnover, Profit).
Generate structured JSON output with confidence scores for each extracted field.
Validation & Taxonomy Alignment
Match extracted entities against Real Deals’ controlled vocabularies/picklist values for Sector, Sub-Sector, Region, and Deal Type.
Standardize numeric values, currency formats, and naming conventions.
Flag low-confidence data for editorial review and prevent duplicates through automated checks.
Summarization & Content Generation
Stage 1 – Auto Summary: Create a first-level summary by filling a predefined deal template using extracted fields.
Stage 2 – Editorial Summary: Refine the draft into a polished article that matches Real Deals’ editorial tone using advanced LLM models (GPT-4o / GPT-5).
Integration & Publishing
Push validated structured data into Azure SQL for long-term storage, analytics, and dashboards.
Automatically upload deal summaries into ExpressionEngine CMS as draft articles for editorial review and publication.
Maintain an audit log of processed documents, extracted data, and system confidence levels.

## Sources Details
Total Sources(Assumption) | 40
Category | Approx. % of Sources | Approx. Count (out of 2000) | Scraping Approach | Hours Required(for each website) | Total Hours Required
Common Framework (Press releases, News Rooms, Third party news sources and org press and news releases) | 60% | 24 | Generic crawler framework (Scrapy + Playwright + article/PDF/text extractor + NLP for facts) | 1 | 24
Custom Scrapers | 40% | 16 | Site-specific scrapers, form-handling, OCR for PDFs, multilingual pipelines OCR (Donut/Tesseract) + translation dictionaries/models | 3 | 48
Total |  |  |  |  | 72 | 1.8
Gmail Email Reading & Attachment Download(for Free Official API)
Task Description | Analysis (In hours) | Development (In hours) | Testing (In hours) | Total Efforts (In Hours)
Requirement understanding & API feasibility for Gmail | 2 | 0 | 0 | 2
Implement Gmail API integration to read emails & download attachments | 2 | 14 | 4 | 20
Logging, reporting, and storage setup for downloaded attachments | 1 | 6 | 2 | 9
End-to-end testing & documentation | 1 | 3 | 2 | 6
Total | 6 | 23 | 8 | 37
Outlook (Microsoft Graph) Email Reading & Attachment Download(for Free Official API)
Task Description | Analysis (In hours) | Development (In hours) | Testing (In hours) | Total Efforts (In Hours)
Requirement understanding & API feasibility for Outlook | 2 | 0 | 0 | 2
Implement Outlook (Microsoft Graph API) integration to read emails & download attachments | 2 | 12 | 2 | 16
Logging, reporting, and storage setup for downloaded attachments | 1 | 4 | 1 | 6
End-to-end testing & documentation | 1 | 2 | 1 | 4
Total | 6 | 18 | 4 | 28
Data ingested into CMS via API(endpoints, authentication, payload, error handling)
Task Description | Analysis (In hours) | Development (In hours) | Testing (In hours) | Total Efforts (In Hours)
Requirement understanding & API documentation review | 2 | 0 | 0 | 2
Data mapping & validation logic | 3 | 12 | 3 | 18
CMS API integration & batch processing | 2 | 4 | 2 | 8
Error handling & retry mechanism | 1 | 2 | 1 | 4
Deployment setup (Docker & CI/CD) | 2 | 8 | 2 | 12
End-to-end testing & documentation | 2 | 4 | 2 | 8
TOTAL | 12 | 30 | 10 | 52

## Call - Queries and Answers
Section / Topic | Discussion Summary | Clarifications / Actions | Next Steps / Notes
Missing Seller Fields | Some Seller fields in sample data are blank. | Seller Name (Free Text) captured only if Seller is a financial sponsor (from Organization table). Not captured for private companies. If Seller + Parent Company exist, Seller Type and Organization always covered. | Document in data validation logic how missing Seller information should be handled.
External Validation (Company / Deal Data) | Discussion on validating data with external corporate data sources. | Additional fields to include: Organization information, Turnover, Revenue (Profit), Sectors, Region (deal level).
Data Enrichment via Open Web | Question on using open web (Google Search) to fill missing structured fields. | Permitted practice – team uses Google Search to fill in missing fields where applicable. | Define a confidence scoring or tagging mechanism for data enriched via open web.
Deal Coverage Scope | Clarified if deals are region or domain-specific. | All deals covered – no filters by region or sector. Region-specific sources available for France and Spain etc | Ensure schema and pipeline support multilingual and region-specific formats.
Financial Data Sources | Financial / filing data sources by country. | For UK: Companies House used as the main source. | Identify equivalent regulatory data sources for other regions (EU, US, APAC).
Regional and Sectoral Prioritization | Discussion on granularity level for geography. | Region → Country → Sub-region (State / County). Team will share this mapping. | Await region & sub-region mapping document for integration into metadata standards.
CMS Ingestion Process | Understanding current ingestion workflow. | Data ingested into CMS via API (no CSV/manual upload). Requires structured payload as per schema. | Obtain API documentation (endpoints, authentication, payload, error handling).

## consolidated_sheet (hidden)
Scraping Solution Development
I. Design, Development and Deployment of Solution - One off Cost
I.1 | Project Task / Activity Description | Cost per hour | Effort in Hours | Total Cost
I.1.a | Source Configuration | 22 | 174 | 3828
I.1.b | Data Transformation(Cleansing and Formatting) | 22 | 8 | 176
I.1.c | Downloader Script | 22 | 24 | 528
I.1.d | System and DB Design | 22 | 8 | 176
I.1.e | UAT Support | 22 | 24 | 528
I.1.f | Integration and Deployment | 22 | 32 | 704
I.2 | Project Management
I.2.a | Project Management Charges(PM and BAs) | 30 | 67.5 | 2025
I.2.b | Documentation | 12 | 8 | 96
I.3 | Infrastructire Charges During Set Up
1.3.a | To be paid on actuals |  | Approximately | 640
| Total Estimated Hours |  | 345.5 | 8701
| Buffer for Contingencies | 22 | 34.55 | 760.1
| Total Set Up Costs |  |  | 9461.1
II. BAU - Ongoing Recurring Cost (Scrpaers Run Weekly *) - Monthly Charges
II.1 | Support and Maintenance Resources |  | FTE(Quantity) | Cost
II.1.a | Support and Maintenance (Tech Resources) |  | 0.25 | 875
I.2 | Infrastructire Charges During BAU
II.2.a | Proxies for Scraping(15 Ips) |  | Approximately | 95
II.2.b | Virtual Machine(Ubuntu) |  | Approximately | 200
II.2.c | MySQL |  | Approximately | 275
II.2.d | Document Storage |  | Approximately | 60
II.2.e | Back-up |  | Approximately | 10
| Total Monthly Cost |  |  | 1515
* Note :Costs will be impacted if scraper schedule changes to daily/ monthly or any other custom schedule
ML Solution Development
I. Design, Development and Deployment of Solution - One off Cost
I.1 | Project Task / Activity Description | Cost per hour | Effort in Hours | Total Cost
I.1.a | Planning - AIML Framework |  | #N/A | #N/A
I.1.b | Development - AIML Framework |  | 248 | 7440
I.1.c | Integration Effort |  | 96 | 2880
I.1.d | Documentation - AIML Framework |  | 0 | 0
I.1.e | Testing - AIML Framework |  | 100 | 2500
I.2 | Project Management
I.2.a | Solution Architect Effort |  | 0 | 1502
I.2.b | PM Effort |  | 0 | 0
| Contingency @ 10% |  | #N/A | #N/A
I.2 | Infrastructire Charges During Set Up |  |  | #N/A
1.2.a | ML Infrastructure
| Virtual Machine(Ubuntu) - On-prem --Per Month cost |  |  | #N/A
1.2.b | Open AI - GPT 4o mini model consumption
| Average Token cost per document (based on current pricing of GPT 4o mini and the samples provided) |  |  | 0.11
| # of URLs |  |  | 1000
| Overall token cost for initial phase |  |  | 110
| Total Set Up Costs |  |  | #N/A
II. BAU - Ongoing Recurring Cost - Monthly Charges
II.1 | Support and Maintenance Resources |  | FTE(Quantity) | Cost
II.1.a. | Support and Maintenance (Tech Resources) - 30 hrs of ML engineer per month |  | 0.25 | 750
I.2 | Infrastructire Charges During BAU
II.2.a | Average Token cost per document(based on current pricing of GPT 4o mini) |  |  | 0.11
| Projected # of documents per year |  |  | 1000
| Overall token costs per year |  |  | 110
| Virtual Machine(Ubuntu) - On-prem | 8 Cores, 16 GB RAM, 150 GB Temporary Storage 256 SSD |  | 200
II.2.b
| Total Monthly Cost |  |  | 2060.11

## lookup
| plan | dev | testing |  | Role | Effort%
Labor cost | 25 | 30 | 25 |  | Solution Architect | 10%
UI labor cost |  | 22 |  |  | PM | 0%
[5 empty] | BA | 0%
[5 empty] | Contingency | 10%
| plan | dev
Solution Architect Effort | 0 | 0
PM Effort | 0 | 0
Dev Unit Testing | 0.2 | 0.2
QA Testing | 0.25 | 0.25
Integration Testing | 0.2 | 0.2
BA Effort | 0 | 0
Scraping Labor cost
| plan | dev | testing | w
Labor cost | 22 | 22 | 22 | 30

## unit_cost
One time cost | 18024
infra | 280
BAU per month | 1030
BAU per year | 12360
Total cost | 30664
# of entries per year | 12000
cost per document | 1.5253

## Resource Loading
[6 empty] | Sprint-1 | [9 empty] | Sprint-2 |  |  | Sprint-3 |  | Hardening | Sprint-4 |  | Sprint-5 |  | Sprint-6 |  | UAT & Deployment | Warranty & Support
Streams | Roles | Count | Planned Capacity (hrs) | No of Productive days | No. of weeks | Week-1 |  |  |  |  | Week-2 |  |  |  |  | Week-3 |  | Week-4 | Week-5 | Week-6 | Week-7 | Week-8 | Week-9 | Week-10 | Week-11 | Week-12 | Week-13 | Week-14 | Week-15 | Week-16
Scraper | Python resources - Pipeline & Transformation | 1
| Lead Python resources (Source config) | 1
| Sr.Python resources (Source config) | 1
| Python resources (Source config) | 1
AI/ML | DA | 1
| AI/ML Consultant | 1
| Sr. AI/ML Dev | 1 | 216 | 30.8571 | 6.1714
| AI/ML Dev | 1 | 216 | 30.8571 | 6.1714
Proj Mgmt | PM | 1
| Scraping Lead | 0.5
| AI/ML Lead | 0.5
| BA | 1
Total
Buffer
Total |  | 11
[6 empty] | Type | Stage |  |  | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8
SL No | Modules | Effort (hrs) | Cost | Remarks |  | Scraping | End to End Scraping |  |  | Week1: Week 1; Week2: Week 2; Week3: Week 3
| Scrapping Soution | 1578 | 53500 |  |  | AI/ML | Planning - Customising AIML Framework for current requirement | 12.5714 | 1.2571 | Week1: Week 1; Week2: Week 2
| AI/ML Solution | 807.1 | 23509.5 |  |  |  | Development - AIML Framework | 35.4286 | 3.5429 | Week3: Week 3; Week4: Week 4; Week5: Week 5; Week6: Week 6
| Web App Solution | 807.48 | 21214.12 |  |  |  | Integration Effort | 13.7143 | 1.3714 | Week7: Week 7; Week8: Week 8
| Total Build Effort | 3192.58 | 98223.62
| PM | 798.145 | 23944.35 | 25% of Build effort
| BA | 638.516 | 12770.32 | 20 % of Build effort ? - To be discussed
| Documentation ? | 0 | 0 | Free of Cost
| Client training ? | 40 | 800
| Overall Buffer | 319.258 | 7342.934 | 10% of Build effort - To be discussed
| Scrapping infra cost |  | 1190 | Is this PCM cost? or for the entire build / set up duration?
| Overall Set Up Costs |  | 144271.224
| Application Support and Maintaince |  | 196560 | Cost calculated for 2 year : Monthly cost - £8,184
Misc ??
| Total Solution Effort | 4988.499 | 583326.068
| Productive days | 712.6427
| No of days per resource on average | 62
| No of weeks | 12.4
| No of sprint | 6.2
Assumptions
| Productive hours | 7
| Days/week | 5