## Scraper_Estimation_FullProject
Robust Solution Development for Finding Land Purchase deals(Datacenters)
I. Design, Development and Deployment of Solution - One off Cost | [5 empty] | US Only for POC
S.No | Project Task / Activity Description | Cost per hour | Effort in Hours | Total Cost
[6 empty] | Total Sources(Assumption) | 2000
1 | Planning, Design and System Set up | 20 | 40 | 800 |  | Category | Approx. % of Sources | Approx. Count (out of 2000) | Scraping Approach | Hours Required(for each website) | Total Hours Required
1.2 | Solution Approach (System Architecture and Database Design) |  | 24 |  |  | Common Framework (Press releases, aggregators, financial/industry media, marketplaces, open data, commercial providers) | 90% | 1800 | Generic crawler framework (Scrapy + Playwright + article/PDF/text extractor + NLP for facts) | 1 | 1800
1.3 | Infrastructure Setup |  | 16 |  |  | Custom Scrapers (Government registries, court/legal, zoning/permits, auction/tender portals, OCR-heavy sources)(OCR + Multilingual Layer (subset of custom)) | 10% | 200 | Site-specific scrapers, form-handling, OCR for PDFs, multilingual pipelines OCR (Donut/Tesseract) + translation dictionaries/models | 3 | 600
[6 empty] | Total |  |  |  |  | 2400
2 | Scraper Development/Configuration | 20 | 2456 | 49120
2.1 | 2000 Sources(Media sites, land registries, company websites, compatitor website) 1. Key media sources – state level business publications / magazines and country level newspapers / magazines (US only) and not exceeding 15 URLs 2. Key competitor websites (not more than 3) to be screened for identifying relevant posts 3. Land registry extraction covering 5 US states (to be suggested by DCB) – Merit recommendation for 5 states : Virginia, Texas, Arizona, Georgia, Ohio |  | 2400 | [8 empty] | 300 | 13.6364 | 3.4091
2.2 | Company-level press releases and annual reports details will be extracted during the PoC stage itself to identify further land transactions |  | 8
2.3 | Data scraped and collected from 15 Twitter handles |  | 24 |  |  |  | Larger Project
2.4 | Open Search(Google OpenSearch limited to first 10 pages to identify relevant base articles or leads (English only) – United States) |  | 8 |  |  |  | 2000
2.5 | Linkedin Posts Scraping 1. Key word search on LinkedIn to extract relevant posts (United States) 2. SME links (20 key contacts) 3. Key company links (20 orgs) |  | 16
3 | Data Transformation, Logging, Alerts, Reports and Delivery | 20 | 28 | 560 |  |  | Slides
3.1 | Download and Upload processed files(Raw responses will be stored in Blob storage) |  | 8 |  |  |  | Workflow diagram
3.2 | Content DeDuping |  | 8 |  |  |  | Technical architecture
3.3 | Multilingual sources(Translation Required) |  | 8
3.4 | Logging |  | 4 |  |  |  | Cost
4 | Data Quality & Validation | 20 | 12 | 240
4.1 | Automated Checks - Data Validation
5 | UAT Issue Fixes | 20 | 246 | 4920
6 | Integration and Deployment | 20 | 16 | 320
7 | Documentation | 20 | 0 | 0
8 | Project Management | 20 | 0 | 0 | FOC
8.1 | Project Management Charges(PM and BAs)
9 | Infrastructure Charges During Set Up |  |  | 810
9.1 | To be paid on actuals
| Total Estimated Hours | 20 | 2798 | 55960
| Buffer for Contingencies(10%) | 20 | 279.8 | 5596
| Total Set Up Costs |  | 3077.8 | 62366
* Note :Costs will be impacted if scraper schedule changes to daily/ monthly or any other custom schedule

## Infrastructure_Details_FullProj
Robust Solution Development for Finding Land Purchase deals(Datacenters)
Infrastructure Details
S.No | Infrastructire Charges During POC |  | Cost(Azure and third party services) | Cost (Project Duration - 8 weeks) |  |  |  |  | Task | Analysis (Hours) | Development (Hours) | Testing (Hours) | Total Hours | Details
1 | Proxy Services | Region specific proxies | 120 | 240 | Will be billed on actuals |  |  |  | 1. Scale Tweet Collection Script | 1 | 4 | 1 | 6 | Optimize pagination, rate handling for 50K volume; integrate Apify for efficiency
2 | Virtual Machine(Ubuntu) | B4as v2: 4 vCPUs, 16 GB RAM, 0 GB Temporary storage, £0.127/hour | 100 | 200 | Will be billed on actuals |  |  |  | 2. Enhance Database for Larger Scale | 1 | 3 | 1 | 5 | Add partitioning/indexes for 25x data growth; handle storage for 50K inserts
3 | DataBase | D Series, 4 vCore, £0.2955/hour | 300 | 600 | Will be billed on actuals |  |  |  | 3. Data Processing Pipeline Enhancements | 4 | 16 | 4 | 24 | Improve URL/link extraction, deduplication for higher throughput
4 | Storage |  | 20 | 40 | Will be billed on actuals |  |  |  | 4. Implement Airflow Workflow | 2 | 6 | 2 | 10 | Set up DAGs for scheduling, error retries, and full E2E pipeline
5 | Backup |  | 20 | 40 | Will be billed on actuals |  |  |  | 5. Proxy & Infra Configuration | 1 | 3 | 1 | 5 | Integrate/add proxies; configure VM for production
6 | Twitter Subscription and Apify |  | 80 | 200 | Subscription cost |  |  |  | 6. Advanced Monitoring & Logging | 1 | 3 | 1 | 5 | Enhance alerts, integrate with Airflow for large runs
7 | Serper(Open Search) |  | 60 | 120 | Subscription cost | 900 | 9000 |  | 7. End-to-End Integration & Optimization | 1 | 2 | 1 | 4 | Tune for BAU; performance testing at 50K scale
8 | Linkedin Post Scraping - Subscription |  | 110 | 110 | Subscription cost | 900 | 270000 | 90000 | TOTAL | 11 | 37 | 11 | 59
AI/ML Infra
1 | GPU Machine |  |  | 1000
2 | Open AI Key |  |  | 400
Total Monthly Cost |  |  | 810 | 2950 |  |  |  |  | Cost(Azure and third party services) Per Month | Change in Infra
[9 empty] | 240 | Proxy Services
[9 empty] | 200 | Virtual Machine(Ubuntu)
[9 empty] | 160 | Twitter Subscription and Apify
[6 empty] | 2000 | 20000

## Scraper_Estimation_POC
Robust Solution Development for Finding Land Purchase deals(Datacenters)
I. Design, Development and Deployment of Solution - One off Cost | [5 empty] | US Only for POC
S.No | Project Task / Activity Description | Cost per hour | Effort in Hours | Total Cost
[6 empty] | Total Sources(Assumption) | 110
1 | Planning, Design and System Set up | 20 | 40 | 800 |  | Category | Approx. % of Sources | Approx. Count (out of 2000) | Scraping Approach | Hours Required(for each website) | Total Hours Required
1.2 | Solution Approach (System Architecture and Database Design) |  | 24 |  |  | Common Framework (Press releases, aggregators, financial/industry media, marketplaces, open data, commercial providers) | 90% | 99 | Generic crawler framework (Scrapy + Playwright + article/PDF/text extractor + NLP for facts) | 1 | 99
1.3 | Infrastructure Setup |  | 16 |  |  | Custom Scrapers (Government registries, court/legal, zoning/permits, auction/tender portals, OCR-heavy sources)(OCR + Multilingual Layer (subset of custom)) | 10% | 11 | Site-specific scrapers, form-handling, OCR for PDFs, multilingual pipelines OCR (Donut/Tesseract) + translation dictionaries/models | 3 | 33
[6 empty] | Total |  |  |  |  | 132
2 | Scraper Development/Configuration | 20 | 188 | 3760
2.1 | 150 Sources(Media sites, land registries, company websites, compatitor website) 1. Key media sources – state level business publications / magazines and country level newspapers / magazines (US only) and not exceeding 15 URLs 2. Key competitor websites (not more than 3) to be screened for identifying relevant posts 3. Land registry extraction covering 5 US states (to be suggested by DCB) – Merit recommendation for 5 states : Virginia, Texas, Arizona, Georgia, Ohio |  | 132
2.2 | Company-level press releases and annual reports details will be extracted during the PoC stage itself to identify further land transactions |  | 8
2.3 | Data scraped and collected from 15 Twitter handles |  | 24 |  |  |  | Larger Project
2.4 | Open Search(Google OpenSearch limited to first 10 pages to identify relevant base articles or leads (English only) – United States) |  | 8 |  |  |  | 2000
2.5 | Linkedin Posts Scraping 1. Key word search on LinkedIn to extract relevant posts (United States) 2. SME links (20 key contacts) 3. Key company links (20 orgs) |  | 16
3 | Data Transformation, Logging, Alerts, Reports and Delivery | 20 | 20 | 400 |  |  | Slides
3.1 | Download and Upload processed files(Raw responses will be stored in Blob storage) |  | 8 |  |  |  | Workflow diagram
3.2 | Content DeDuping |  | 8 |  |  |  | Technical architecture
3.3 | Logging |  | 4 |  |  |  | Cost
4 | Data Quality & Validation | 20 | 12 | 240
4.1 | Automated Checks - Data Validation
5 | UAT Issue Fixes | 20 | 19 | 380
6 | Integration and Deployment | 20 | 16 | 320
7 | Documentation | 20 | 0 | 0
8 | Project Management | 20 | 0 | 0 | FOC
8.1 | Project Management Charges(PM and BAs)
9 | Infrastructure Charges During Set Up |  |  | 810
9.1 | To be paid on actuals
| Total Estimated Hours | 20 | 295 | 5900
| Buffer for Contingencies(10%) | 20 | 29.5 | 590
| Total Set Up Costs |  | 324.5 | 7300
* Note :Costs will be impacted if scraper schedule changes to daily/ monthly or any other custom schedule

## DC Byte Poc
A. Design, Development and Deployment of Solution
Project Task / Activity Description : | Effort in Hours | Cost per Hour | Total Cost | Remarks
Analysis and planning
Source articles analysis and Domain knowledge gathering | 16 | 0 | 0 | FOC
Walkthrough and workshop sessions | 8 | 0 | 0 | FOC
Internal DB schema design | 8 | 0 | 0 | FOC
Scraper - Planning, Design and System Set-up
Solution Approach (System Architecture and Database Design) | 24 | 20 | 480
Infrastructure Setup | 16 | 20 | 320
Scraper - Generic Framework
100 Sources(Media sites, land registries, company websites, compatitor website) 1. Key media sources – state level business publications / magazines and country level newspapers / magazines (US only) and not exceeding 15 URLs 2. Key competitor websites (not more than 3) to be screened for identifying relevant posts 3. Land registry extraction covering 5 US states (to be suggested by DCB) – Merit recommendation for 5 states : Virginia, Texas, Arizona, Georgia, Ohio | 100 | 20 | 2000
Company-level press releases and annual reports details will be extracted during the PoC stage itself to identify further land transactions | 8 | 20 | 160
Data scraped and collected from 15 Twitter handles | 24 | 20 | 480
Open Search(Google OpenSearch limited to first 10 pages to identify relevant base articles or leads (English only) – United States) | 8 | 20 | 160
Linkedin Posts Scraping 1. Key word search on LinkedIn to extract relevant posts (United States) 2. SME links (20 key contacts) 3. Key company links (20 orgs) | 16 | 20 | 320
Classifier
Bifurcation of land sales real estate transactions from other press releases | 24 | 20 | 480
Classification of land sales made for building datacentres | 24 | 20 | 480
Testing and Analysis - Classifier | 16 | 20 | 320
Semantic Grouping or Deduplication
Deduplicate the same land sales | 64 | 20 | 1280
Testing and Analysis - Semantic Deduplication | 16 | 20 | 320
Data Mining
Refer to the source to extract mentioned datapoints | 80 | 20 | 1600
Extract remaining datapoints from LinkedIn | 16 | 20 | 320
Testing and Analysis - Data Extracted | 16 | 20 | 320
Scraper - Data Transformation, Logging, Alerts, Reports and Delivery
Download and Upload processed files(Raw responses will be stored in Blob storage) | 8 | 20 | 160
Content DeDuping | 8 | 20 | 160
Logging | 4 | 20 | 80
Scraper - UAT Issue Fixes | 24 | 20 | 480
Scraper - Integration and Deployment | 16 | 20 | 320
Export the data into Excel
Export the required datapoints in a proper Excel format | 8 | 20 | 160
Testing
Scraper testing | 12 | 20 | 240
Data quality | 64 | 10 | 640
Documentation | 16 | FOC | 0
Project Management hours | 76.1 | 20 | 1522
Total | 720.1 |  | 12802
Project Management hours
Project manger | 0
Business Analyst | 0
Total | 0
Infra Cost
Infrastructure | Virtual Machine |  | 1000
| OpenAI Cost |  | 400
| Scraper |  | 1500
Total |  |  | 2900 | Cost for 8 weeks
Total Cost (AI/ML + Scraping) |  |  | 15702
B. In-scope and Out-of-scope covered during the PoC Phase
In-Scope for the PoC
Coverage limited to four U.S. states
Articles with English language
Data extraction from the first 10 pages of Google search results (10 links per page)
Additional data extraction from LinkedIn, besides the source article and Google search
Out of Scope for the PoC
Markets operating in non-English languages
Transactions involving currencies other than USD
Data extraction from PDF documents
Unit/Currency conversions or normalization
Matching transactions with existing facilities
Points to be noted
For a one-time PoC delivery, incremental updates will be applicable based on manual comprison of results derived against each run (only for the agreed duration of the POC). During which we will flag updated articles by comparing transaction dates against existing database entries.
Given the limited scope of the PoC, the timeline for a full-scale implementation is expected to be approximately 5-8 times longer than the PoC delivery duration with 2 - 3 times the team size.

## Sheet1
Description | Cost | Comments
Discovery, Analysis and Planning | FOC
Solution Design and System Set up | 800
ScrapeX configuration, Custom Scraper Development - c180 sources | 3520 | Refer Appendix I - V for the full list of sources
AI/ML solution using KIAA framework - classifier, semantic de-duping, data mining | 5120
Solution Testing /QA (Tech) | 1600
Solution Integration and Deployment | 800
Documentation | FOC
Project Management | FOC
Total Solution Customisation and Set Up Costs | 11840
Manual Resource Cost - 2 FTEs | FOC
Total Infra Costs | 2900 | Costs for 8 weeks - Refer Appendix VI for Infra Details
Total Cost of POC | 14740
Description | Cost | Comments
Discovery, Analysis and Planning | 5000
Solution Design and System Set up | 2400
ScrapeX configuration, Custom Scraper Development - c2000 sources | 38000
AI/ML solution using KIAA framework - classifier, semantic de-duping, data mining | 15360
Solution Testing /QA (Tech) | 8000
Automated Validation Checks | 9000
Solution Integration and Deployment | 4000
Documentation | FOC
Project Management | 3850
Total Solution Set Up / Configuration Costs | 85610
Manual Resource Cost - 3 FTEs | 4500
Total Infra Costs | 17400 | Costs for X months - Refer Appendix VI for Infra Details
Total Cost of POC | 107510
Recurring Monthly BAU Cost
Licensing Cost | 16500
Estimated Infra Cost (charged on actuals) | XXX

## Infrastructure_Details
Robust Solution Development for Finding Land Purchase deals(Datacenters)
Infrastructure Details
S.No | Infrastructire Charges During POC |  | Cost(Azure and third party services) | Cost (Project Duration - 8 weeks)
1 | Proxy Services | Region specific proxies | 120 | 240 | Will be billed on actuals
2 | Virtual Machine(Ubuntu) | B4as v2: 4 vCPUs, 16 GB RAM, 0 GB Temporary storage, £0.127/hour | 100 | 200 | Will be billed on actuals
3 | DataBase | D Series, 4 vCore, £0.2955/hour | 300 | 600 | Will be billed on actuals
4 | Storage |  | 20 | 40 | Will be billed on actuals
5 | Backup |  | 20 | 40 | Will be billed on actuals
6 | Twitter Subscription and Apify |  | 80 | 80 | Subscription cost
7 | Serper(Open Search) |  | 60 | 60 | Subscription cost | 900 | 9000
8 | Linkedin Post Scraping - Subscription |  | 110 | 220 | Subscription cost | 900 | 270000 | 90000
AI/ML Infra
1 | GPU Machine |  |  | 1000
2 | Open AI Key |  |  | 400
Total Monthly Cost |  |  | 810 | 2880

## Tasks List (hidden)
Task | Description | Tools/Code
Validation Layer of Article Based on Region
Initiate Scraping | Start the pipeline with keyword(s) or a batch of queries. | Python
Open Search | Keyword Search on Google | SearXNG/SerpAPI
Buyer-Based Search
Source-Based Monitoring
Registry-Based Search
Classifier Component – Classify Articles into Data Center vs Non-Data Center | Pre-train a classifier on labeled dataset | scikit-learn, transformers (HuggingFace)/ zero shot or few shot learning
Use transformers (all-MiniLM-L6-v2) or rule-based + keyword hybrid.
Open and Download Article | After filtering, download HTML
Convert to raw text.
Handle duplicates and store source metadata.
Validation Layer of Article Based on Region | Use regex/NER/LLM to identify region mentions | LLM/Regex/Spaacy
If US region → keep; else discard.
Extract Required Data Points Using LLM | Define structured fields | langchain/llama
| Pass cleaned article text into LLM prompt template | Model: gpt-4o-mini, gpt-4, or local LLM (Llama 3, Mistral)
| Ensure structured JSON-like output. | Use RAG (e.g., ChromaDB) for better accuracy if documents are long.
Parse Output | Validate JSON schema with pydantic | pydantic, jsonschema
| Normalize addresses, dates, funding amounts | dateparser
Store in Excel