## Estimation
A. Design, Development and Deployment of Solution
Project Task / Activity Description : | Effort in Hours | Cost per Hour | Total Cost | Remarks
Analysis and Planning
Analyze the PDF documents and categorize them into three types: Easy, Medium, and Hard. | 16 | 25 | 400 |  | Analysis and Planning | 2800
Research and analyze available open-source libraries or models for OCR to identify the most suitable one. | 16 | 25 | 400 |  | De-duplication | 1200
Explore image enhancement techniques to improve OCR accuracy and quality. | 24 | 25 | 600 |  | Human-in-the-loop: | 1200
Implement post-processing of OCR outputs using rules or LLMs to enhance result quality. | 32 | 25 | 800 |  | Easy - Spare Parts Mapping | 2160
Explore methods to identify whether a document has already been processed. | 24 | 25 | 600 |  | Medium- Spare Parts Mapping | 1560
[5 empty] | Hard - Activity Mapping | 5810
Development |  |  |  |  | Integration and QA | 1920
De-duplication |  |  |  |  | Testing - Pipeline | 400
Develop a Python module to identify the duplicate or similar manufaure data is already in the master. | 40 | 30 | 1200 |  | Project Management | FOC
[5 empty] | Infra Cost | 1400
Human-in-the-loop: | [5 empty] | 18450
Human-in-the-loop: Develop the python module to implement the human in the loop. | 40 | 30 | 1200
Easy - Spare Parts Mapping
Perform OCR on the documents using open-source libraries. | 16 | 30 | 480 | can go in parallel
Use an LLM to validate and restructure the extracted table data for better quality. | 32 | 30 | 960 | can go in parallel
Transformation: Apply data transformation based on client instructions using rules and LLMs. | 24 | 30 | 720 | can go in parallel
Medium- Spare Parts Mapping
Table Detection and Extraction: Perform OCR on the documents using LLM-based models. | 12 | 30 | 360 | can go in parallel
Use an LLM to validate and restructure the extracted table data for improved quality. | 16 | 30 | 480 | can go in parallel
Transformation: Apply data transformation based on client instructions using rules and LLMs. | 24 | 30 | 720 | can go in parallel
Hard - Activity Mapping
Table Detection and Extraction: Detect tables in PDF documents using open-source libraries and perform OCR using an LLM model. | 32 | 35 | 1120 | can go in parallel
Use an LLM to validate and restructure the extracted table data for better accuracy. | 16 | 35 | 560 | can go in parallel
Content Extraction: Perform OCR on the documents using open-source libraries. | 8 | 35 | 280 | can go in parallel
Detect and extract spare parts image from PDFs and store them in their respective folders. | 40 | 35 | 1400 | can go in parallel
Transformation: Apply data transformation based on client instructions using rules and LLMs. | 70 | 35 | 2450 | can go in parallel
Integration and QA
Combine all developed modules into a unified workflow. | 24 | 30 | 720
Data Quality Check (Human-in-the-loop): Manually review and validate outputs to ensure accuracy and consistency. | 48 | 25 | 1200
Note : We should implement the Human-in-the-Loop process after the table extraction step. For the POC, we did not use a UI for validation; instead, we validated the data directly from the Excel file.
Testing - Pipeline | 16 | 25 | 400
Total | 570 |  | 17050
Project Management hours
Project manger | 0
Business Analyst | 0
Infra Cost
| Virtual Machine |  | 1000
| OpenAI Cost |  | 400
|  |  | 1400 | Cost for 8 weeks
| Cost for the POC |  | 18450