## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | POC
Scenario: | baseline
Generated: | 2025-11-25 12:26:10
COST SUMMARY
Total Project Cost: | 26747.6
Total Hours: | 892
Number of Teams: | 5
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Backend Engineering Team | 8756 | 272 | 32.1912 | 50%
Frontend/UI Engineering Team | 4109.6 | 160 | 25.685 | 50%
QA/Testing Team | 3630 | 132 | 27.5 | 30%
DevOps/Infrastructure Team | 4972 | 136 | 36.5588 | 30%
Project Management Team | 5280 | 192 | 27.5 | 50%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 8 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 2 weeks
Deliverables:
• Project Plan
• Initial BRD Draft
• Cost Estimation Template Draft
• Infrastructure Setup Plan
Phase 2: Development - Core Features
Duration: | 3 weeks
Deliverables:
• API Endpoints
• Executive Summary UI
• Gantt Chart Component
• Cost Estimation Template Integration
Dependencies: | Phase(s) Planning & Setup
Phase 3: Testing & QA
Duration: | 2 weeks
Deliverables:
• Backend Testing Report
• UI Testing Report
• QA Testing Report
• Monitoring Setup
Dependencies: | Phase(s) Development - Core Features
Phase 4: Deployment & Handoff
Duration: | 1 weeks
Deliverables:
• CI/CD Pipeline Setup
• Final BRD Document
• Cost Estimation Template
• Deployment Documentation
• End-User Documentation
Dependencies: | Phase(s) Testing & QA
KEY MILESTONES
Milestone | Week
Kickoff | 0
BRD & Cost Estimation Draft Complete | 2
Core Development Complete | 5
Testing Complete | 7
Go-Live | 8

## Backend Engineering Team
BACKEND ENGINEERING TEAM - COST BREAKDOWN
Total Cost: | 8756
Total Hours: | 272
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design Database Schema for BRD and Cost Estimation Tools | N/A | 40 | 0 | 0
Develop API Endpoints for Data Retrieval and Manipulation | N/A | 80 | 0 | 0
Integrate Authentication Mechanism for API Services | N/A | 32 | 0 | 0
Implement Data Validation and Error Handling | N/A | 24 | 0 | 0
Setup Continuous Integration/Continuous Deployment (CI/CD) Pipeline | N/A | 40 | 0 | 0
Conduct API Endpoint Testing | N/A | 40 | 0 | 0
Prepare Backend Deployment Documentation | N/A | 16 | 0 | 0

## Frontend-UI Engineering Team
FRONTEND-UI ENGINEERING TEAM - COST BREAKDOWN
Total Cost: | 4109.6
Total Hours: | 160
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design Executive Summary UI Section | N/A | 32 | 0 | 0
Develop Interactive Gantt Chart Component | N/A | 40 | 0 | 0
Integrate Cost Estimation Template Functionality | N/A | 48 | 0 | 0
UI Testing for BRD Tool Sections | N/A | 24 | 0 | 0
Documentation for End-Users | N/A | 16 | 0 | 0

## QA-Testing Team
QA-TESTING TEAM - COST BREAKDOWN
Total Cost: | 3630
Total Hours: | 132
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Validate Executive Summary Section Functionality | N/A | 16 | 0 | 0
Test Detailed Project Overview Features | N/A | 20 | 0 | 0
Assess Functionality of Requirements Listing | N/A | 24 | 0 | 0
Timeline and Milestones Section Usability Testing | N/A | 32 | 0 | 0
Validate Cost Estimation Template Logic | N/A | 40 | 0 | 0

## DevOps-Infrastructure Team
DEVOPS-INFRASTRUCTURE TEAM - COST BREAKDOWN
Total Cost: | 4972
Total Hours: | 136
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Set up CI/CD pipeline for BRD and Cost Estimation Template development | N/A | 32 | 0 | 0
Implement monitoring for project infrastructure | N/A | 40 | 0 | 0
Configure secure access to databases | N/A | 24 | 0 | 0
Develop automated backup solutions | N/A | 16 | 0 | 0
Prepare environment for BRD and Cost Estimation Template development | N/A | 24 | 0 | 0

## Project Management Team
PROJECT MANAGEMENT TEAM - COST BREAKDOWN
Total Cost: | 5280
Total Hours: | 192
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Draft Executive Summary for BRD | N/A | 16 | 0 | 0
Develop Detailed Project Overview | N/A | 24 | 0 | 0
List and Define Functional and Non-Functional Requirements | N/A | 40 | 0 | 0
Create Timeline and Milestones Section | N/A | 32 | 0 | 0
Outline Structured Deliverables List | N/A | 24 | 0 | 0
Draft Cost Estimation Template | N/A | 40 | 0 | 0
Finalize and Review BRD and Cost Estimation | N/A | 16 | 0 | 0

## Sample Guidance
GUIDANCE FROM UPLOADED SAMPLE DOCUMENTS
This estimation was guided by the patterns extracted from your uploaded sample cost estimate documents:
Given the constraints of not having direct access to the specific uploaded cost estimate documents, I'll provide a general analysis framework based on common practices observed in cost estimation across various industries. This framework will help in understanding how tasks are typically categorized and numbered, effort estimation patterns, team composition, infrastructure and overhead considerations, and the level of task granularity. This should serve as a guide for generating tasks based on the patterns observed in cost estimate examples.
1. **Task Categorization and Numbering**: Tasks in cost estimates are often categorized based on project phases, functional areas, or specific deliverables. A common approach is to use a hierarchical numbering system where the main categories (e.g., Design, Development, Testing) are numbered sequentially (e.g., 1.0, 2.0, 3.0), and subtasks under each category follow a decimal notation (e.g., 1.1, 1.2 for tasks under Design). This structure helps in organizing the estimate logically and facilitates easy reference.
2. **Effort Estimation Patterns**: Effort estimates are typically given in hours or days, with the granularity depending on the project's complexity and duration. Short-term projects might have effort estimated in hours, while long-term projects could use days or even weeks for larger tasks. Effort estimation often follows a pattern where initial estimates are refined as more information becomes available, using techniques like expert judgment, historical data, or parametric estimating.
3. **Team Composition Patterns**: The team composition in cost estimates usually reflects the project's requirements, with roles and responsibilities outlined for each task or phase. Common patterns include core team members (e.g., project manager, developers, designers) and support roles (e.g., QA testers, business analysts). The estimates might also account for the involvement of external consultants or vendors for specialized tasks.
4. **Infrastructure and Overhead Patterns**: Infrastructure needs (e.g., servers, software licenses) and overhead costs (e.g., administrative support, office space) are often listed separately from direct project tasks. These are usually estimated based on the project duration and the resources required, with a clear distinction between one-time costs (e.g., purchasing equipment) and recurring expenses (e.g., monthly subscriptions, utility bills).
5. **Task Granularity**: The level of detail in task breakdown can vary widely. High-level estimates might group several activities under broad categories, suitable for early-stage planning or projects with a high degree of uncertainty. Detailed estimates break down tasks into finer elements, providing a more accurate view