## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | POC
Scenario: | baseline
Generated: | 2025-11-25 13:01:49
COST SUMMARY
Total Project Cost: | 26544
Total Hours: | 840
Number of Teams: | 4
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Development Team | 3564 | 108 | 33 | 30%
Infrastructure Team | 5148 | 156 | 33 | 50%
Backend Engineering Team | 11760 | 392 | 30 | 10%
DevOps/Infrastructure Team | 6072 | 184 | 33 | 10%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 16 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 4 weeks
Deliverables:
• Architecture document
• Database schema
• Infrastructure setup
Phase 2: Development - Core Features
Duration: | 4 weeks
Deliverables:
• Comprehensive BRD and Cost Estimate Template for Project Scope document
Dependencies: | Phase(s) Phase 1 Complete
Phase 3: Testing & QA
Duration: | 4 weeks
Dependencies: | Phase(s) Phase 2 Complete
Phase 4: Deployment & Handoff
Duration: | 4 weeks
Deliverables:
• Project Scope Document for production use
Dependencies: | Phase(s) Phase 3 Complete
KEY MILESTONES
Milestone | Week
Kickoff | 0
Go-Live | 16

## Development Team
DEVELOPMENT TEAM - COST BREAKDOWN
Total Cost: | 3564
Total Hours: | 108
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Set up Playwright for Amazon product scraping environment | N/A | 24 | 0 | 0
Create a simple Business Requirements Document (BRD) | N/A | 30 | 0 | 0
Perform initial code review for the BRD | N/A | 8 | 0 | 0
Identify and prioritize key features for the project scope document | N/A | 6 | 0 | 0
Develop a Cost Estimate Template for the Project Scope document | N/A | 40 | 0 | 0

## Infrastructure Team
INFRASTRUCTURE TEAM - COST BREAKDOWN
Total Cost: | 5148
Total Hours: | 156
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Configure Playwright for Amazon product scraping | N/A | 40 | 0 | 0
Implement database management for project data storage | N/A | 30 | 0 | 0
Prepare network configuration for server setup | N/A | 16 | 0 | 0
Develop server administration script for automated backups | N/A | 30 | 0 | 0
Design documentation for project setup instructions | N/A | 40 | 0 | 0

## Backend Engineering Team
BACKEND ENGINEERING TEAM - COST BREAKDOWN
Total Cost: | 11760
Total Hours: | 392
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Create a comprehensive Business Requirements Document (BRD) and Cost Estimate Template for the Project Scope document. | N/A | 40 | 0 | 0
Define key features for the BRD and Cost Estimate Template. | N/A | 8 | 0 | 0
Gather historical data for the project scope. | N/A | 16 | 0 | 0
Develop a sample database management system for the BRD template. | N/A | 40 | 0 | 0
Create a basic database schema using SQL. | N/A | 24 | 0 | 0
Create sample data for the database management system. | N/A | 16 | 0 | 0
Analyze data quality and consistency issues in the sample database. | N/A | 16 | 0 | 0
Prepare a detailed BRD and Cost Estimate Template for the Project Scope document. | N/A | 80 | 0 | 0
Review and finalize the BRD and Cost Estimate Template with stakeholders. | N/A | 16 | 0 | 0
Prepare a sample cost estimate using the BRD template. | N/A | 40 | 0 | 0
Document project constraints related to timeline and budget expectations. | N/A | 16 | 0 | 0
Prepare a sample BRD and Cost Estimate Template for review by senior management. | N/A | 40 | 0 | 0
Prepare project scope document based on the BRD template and Cost Estimate Template. | N/A | 40 | 0 | 0

## DevOps-Infrastructure Team
DEVOPS-INFRASTRUCTURE TEAM - COST BREAKDOWN
Total Cost: | 6072
Total Hours: | 184
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design and Implement a CI/CD Pipeline for the Project Scope Document | N/A | 24 | 0 | 0
Create a Business Requirements Document (BRD) Template | N/A | 20 | 0 | 0
Prepare Cost Estimate Template for Project Scope Document | N/A | 30 | 0 | 0
Develop a Comprehensive Business Requirements Document (BRD) | N/A | 20 | 0 | 0
Prepare a Cost Estimate Template for Project Scope Document | N/A | 20 | 0 | 0
Create a Sample Data File for BRD Template | N/A | 20 | 0 | 0
Perform a Data Complexity Assessment on Sample Files | N/A | 30 | 0 | 0
Develop a Comprehensive Business Requirements Document (BRD) and Cost Estimate Template for the Project Scope Document | N/A | 20 | 0 | 0

## Sample Guidance
GUIDANCE FROM UPLOADED SAMPLE DOCUMENTS
This estimation was guided by the patterns extracted from your uploaded sample cost estimate documents:
### 1. How Tasks are Categorized and Numbered
In the analyzed cost estimate document, tasks were primarily categorized into three main areas: Development, Infrastructure, and Overheads. Each category was further broken down into subcategories to provide a more detailed breakdown of work.
- **Development**: This area included tasks related to software development, including coding, testing, debugging, and integration.
- Subcategories:
- Coding
- Testing
- Debugging
- Integration
- **Infrastructure**: Tasks here pertained to the setup and maintenance of the project's infrastructure, such as database management, network configuration, and server administration.
- Subcategories:
- Database Management
- Network Configuration
- Server Administration
- **Overheads**: This category encompassed all non-project-specific costs associated with running a business or organization. It included expenses like salaries, utilities, insurance, marketing, and administrative tasks.
- Subcategories:
- Salaries
- Utilities
- Insurance
- Marketing
- Administrative Tasks
### 2. Typical Effort Estimation Patterns (Hours/Days)
The typical effort estimation patterns varied significantly across different projects but generally followed a structured approach.
- **Development**: The development tasks were estimated in hours, with an average of around 10 to 30 hours per task depending on the complexity and size of the project.
- Example: A coding task might be estimated at 25 hours.
- **Infrastructure**: Infrastructure tasks were usually estimated in days or weeks. For example, setting up a database could take anywhere from 7 to 14 days, while network configuration might require about 30 days.
- Example: Database setup could be estimated as 8 days, and network configuration as 2 weeks.
- **Overheads**: Overhead tasks were often estimated in terms of hours or days. For instance, salaries for a team member would typically range from 15 to 40 hours per week, depending on the project's size.
- Example: A marketing task might be estimated at 30 hours.
### 3. Team Composition Patterns
The team composition patterns varied significantly across projects but generally followed a typical structure:
- **Core Development Team**: This typically included developers and testers who would handle most of the coding, testing, debugging, and integration tasks.
- Example: A core development team might consist of 5 to 10 members.
- **Infrastructure Team**: This group was responsible for setting