## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | POC
Scenario: | baseline
Generated: | 2025-11-25 13:49:31
COST SUMMARY
Total Project Cost: | 30970.5
Total Hours: | 964
Number of Teams: | 5
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Scraping/Data Collection Team | 6072 | 192 | 31.625 | 10%
Data Engineering Team | 3828 | 116 | 33 | 20%
Backend Engineering Team | 6622 | 204 | 32.4608 | 30%
Frontend/UI Engineering Team | 8112.5 | 260 | 31.2019 | 25%
DevOps/Infrastructure Team | 6336 | 192 | 33 | 15%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 15 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 4 weeks
Deliverables:
• Architecture document
• Database schema
• Infrastructure setup
Phase 2: Development - Core Features
Duration: | 8 weeks
Deliverables:
• Backend system design
• Performance optimization code
• Responsive design implementation
Dependencies: | Phase(s) {'phase_name': 'Planning & Setup', 'week': 0}
Phase 3: Testing & QA
Duration: | 4 weeks
Deliverables:
• Performance optimization tests
• Integration with backend systems test
• Responsive design testing
Dependencies: | Phase(s) {'phase_name': 'Development - Core Features', 'week': 0}
Phase 4: Deployment & Handoff
Duration: | 2 weeks
Deliverables:
• Documentation and training materials for production deployment
Dependencies: | Phase(s) {'phase_name': 'Development - Core Features', 'week': 0}
Phase 5: Go-Live
Duration: | 1 weeks
Deliverables:
• User interface design for responsive layout and performance optimization
Dependencies: | Phase(s) {'phase_name': 'Planning & Setup', 'week': 0}, {'phase_name': 'Deployment & Handoff', 'week': 2}
KEY MILESTONES
Milestone | Week
Kickoff | 0
Go-Live | 15

## Scraping-Data Collection Team
SCRAPING-DATA COLLECTION TEAM - COST BREAKDOWN
Total Cost: | 6072
Total Hours: | 192
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Configure Playwright for Amazon product scraping | N/A | 24 | 0 | 0
Create initial data collection script in Python | N/A | 24 | 0 | 0
Integrate collected data into a database | N/A | 24 | 0 | 0
Perform initial integration testing of the Scraping/Collection System | N/A | 24 | 0 | 0
Create a prototype user interface for the new software feature | N/A | 24 | 0 | 0
Perform performance testing under high traffic conditions | N/A | 24 | 0 | 0
Document the project scope and goals | N/A | 24 | 0 | 0
Train team members on Scraping/Data Collection best practices | N/A | 24 | 0 | 0

## Data Engineering Team
DATA ENGINEERING TEAM - COST BREAKDOWN
Total Cost: | 3828
Total Hours: | 116
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Set up environment for POC project | N/A | 24 | 0 | 0
Design user interface for POC project | N/A | 16 | 0 | 0
Develop performance optimization for high traffic scenarios | N/A | 40 | 0 | 0
Integrate with existing backend systems | N/A | 16 | 0 | 0
Develop responsive design for multiple devices | N/A | 20 | 0 | 0

## Backend Engineering Team
BACKEND ENGINEERING TEAM - COST BREAKDOWN
Total Cost: | 6622
Total Hours: | 204
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Configure Playwright for Amazon product scraping | N/A | 24 | 0 | 0
Develop backend system for prototype | N/A | 40 | 0 | 0
Optimize performance for high traffic scenarios | N/A | 24 | 0 | 0
Integrate with existing backend systems | N/A | 20 | 0 | 0
Responsive design for multiple devices | N/A | 24 | 0 | 0
Perform performance optimization for high traffic scenarios | N/A | 24 | 0 | 0
Write unit tests for backend integration | N/A | 20 | 0 | 0
Document project and integration process | N/A | 20 | 0 | 0
Training session for team members on backend prototype integration | N/A | 8 | 0 | 0

## Frontend-UI Engineering Team
FRONTEND-UI ENGINEERING TEAM - COST BREAKDOWN
Total Cost: | 8112.5
Total Hours: | 260
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design user interface for responsive design across multiple devices | N/A | 20 | 0 | 0
Optimize performance for high traffic scenarios | N/A | 30 | 0 | 0
Integrate with existing backend systems | N/A | 25 | 0 | 0
Create a prototype system for evaluating user interaction with new software features | N/A | 35 | 0 | 0
Perform performance optimization for high traffic scenarios | N/A | 28 | 0 | 0
Design user interface for responsive design across multiple devices | N/A | 22 | 0 | 0
Optimize performance for high traffic scenarios | N/A | 32 | 0 | 0
Design user interface for responsive design across multiple devices | N/A | 20 | 0 | 0
Optimize performance for high traffic scenarios | N/A | 25 | 0 | 0
Design user interface for responsive design across multiple devices | N/A | 23 | 0 | 0

## DevOps-Infrastructure Team
DEVOPS-INFRASTRUCTURE TEAM - COST BREAKDOWN
Total Cost: | 6336
Total Hours: | 192
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Set up Playwright environment for Amazon product scraping | N/A | 24 | 0 | 0
Implement feature: Product Scraping Integration | N/A | 24 | 0 | 0
Create API Endpoint for Scraped Data | N/A | 24 | 0 | 0
Integrate Scraped Data with Backend System | N/A | 24 | 0 | 0
Test Scraping Integration | N/A | 24 | 0 | 0
Deploy Scraped Data Endpoint | N/A | 24 | 0 | 0
Document Scraping Process and Endpoint | N/A | 24 | 0 | 0
Train Support Team on Scraping Integration | N/A | 24 | 0 | 0

## Sample Guidance
GUIDANCE FROM UPLOADED SAMPLE DOCUMENTS
This estimation was guided by the patterns extracted from your uploaded sample cost estimate documents:
### Summary of Cost Estimate Patterns
#### 1. Task Categorization and Numbering:
The cost estimate document is organized into distinct sections, each containing multiple tasks numbered sequentially from 1 to N. This categorizes the tasks based on their nature or scope, such as development, testing, deployment, and support.
#### 2. Typical Effort Estimation Patterns:
- **Hours**: The most common unit of measurement for effort estimation is hours. For example, a task might be estimated at "50 hours" to indicate that it requires five workdays.
- **Days**: Tasks are also often estimated in days, especially when the project timeline is tight or when detailed breakdowns are not required.
#### 3. Team Composition Patterns:
The document includes information about the team members involved in each task. This can be broken down into roles such as developers, testers, and support personnel. The number of team members assigned to a task indicates the complexity and scope of work required for that particular task.
#### 4. Infrastructure and Overhead Patterns:
Infrastructure costs are estimated separately from other tasks. These include expenses related to hardware, software licenses, network resources, and maintenance fees. Overheads such as salaries, benefits, and administrative costs are also included in these estimates but are typically listed separately or at the end of the document.
#### 5. Task Granularity:
Tasks can be categorized into high-level categories like "Development," "Testing," "Deployment," and "Support" to provide a broad overview of project scope. Alternatively, tasks can be detailed down to specific activities within each category (e.g., "Write code for feature X," "Run unit tests on module Y"). This granularity allows for more precise cost estimation but may increase the time required for analysis.
### Summary:
The provided cost estimate document is structured with clear categorization of tasks and effort estimates in hours or days. Team composition details are included, and infrastructure costs are separated from other expenses. The project scope is divided into high-level categories like development, testing, deployment, and support, which can be further broken down for detailed tasks. This structure ensures that the cost estimation process is both organized and comprehensive, making it easier to allocate resources effectively within the budget constraints.