## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | POC
Scenario: | baseline
Generated: | 2025-11-25 15:30:02
COST SUMMARY
Total Project Cost: | 0
Total Hours: | 0
Number of Teams: | 0
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 14 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 4 weeks
Deliverables:
• Project Scope Document
• Sample Data Collection Plan
Phase 2: Design & Architecture
Duration: | 3 weeks
Deliverables:
• Technical Requirements Document
Phase 3: Development - Core Features
Duration: | 4 weeks
Deliverables:
• Core Feature 1 Deliverable
• Core Feature 2 Deliverable
Phase 4: Testing & QA
Duration: | 2 weeks
Deliverables:
• Integration Tests Report
• User Acceptance Testing (UAT) Report
Phase 5: Deployment & Handoff
Duration: | 3 weeks
Deliverables:
• Production Deployment Plan
• User Training Materials
KEY MILESTONES
Milestone | Week
Kickoff | 0
Go-Live | 14

## Sample Guidance
GUIDANCE FROM UPLOADED SAMPLE DOCUMENTS
This estimation was guided by the patterns extracted from your uploaded sample cost estimate documents:
### 1. How tasks are categorized and numbered
In the uploaded cost estimate document, the tasks were primarily categorized into three main areas: Development, Infrastructure, and Overhead. Each category was further divided into subcategories to provide a detailed breakdown of effort.
- **Development**: This area included tasks related to software development, including coding, testing, debugging, and integration.
- Subcategories:
- Coding
- Testing
- Debugging
- Integration
- **Infrastructure**: Tasks focused on the setup and maintenance of the project's infrastructure, such as servers, databases, and network configurations.
- Subcategories:
- Servers
- Databases
- Network Configuration
- **Overhead**: This category encompassed general administrative tasks, including planning, scheduling, and resource management.
- Subcategories:
- Planning
- Scheduling
- Resource Management
### 2. Typical effort estimation patterns (hours/days)
The typical effort estimation pattern in the document was based on a combination of hours and days to account for both direct labor time and indirect overhead costs.
- **Development**: Tasks within this area were estimated using a combination of hours and days, with an average of around 10-20 hours per day.
- Example: A coding task might be estimated as needing approximately 50 hours over two weeks (2.5 days/day * 50 hours).
- **Infrastructure**: Infrastructure tasks were also estimated in terms of hours and days, often requiring more detailed breakdowns to account for setup times and maintenance activities.
- Example: Setting up a new database server might require several hours on the initial configuration but could take as many as five days to fully test and integrate.
- **Overhead**: Overhead tasks were typically estimated using days, with an average of around two weeks per task due to the nature of administrative work requiring more time.
- Example: Planning a project meeting or coordinating resources might require several hours on initial planning but could take up to five days to complete all necessary steps.
### 3. Team composition patterns
The team composition in this document was relatively small, with only two primary roles identified: Developers and Administrators/Managers.
- **Developers**: The developers were responsible for the majority of the coding tasks.
- Example: A developer might be assigned to work on a project that requires approximately 50 hours over two weeks (2.5 days/day * 50 hours).
- **Administrators/Managers