## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | POC
Scenario: | baseline
Generated: | 2025-11-25 18:28:40
COST SUMMARY
Total Project Cost: | 9370
Total Hours: | 309
Number of Teams: | 3
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Backend Engineering | 4180 | 134 | 31.194 | 70%
Data Engineering | 4530 | 151 | 30 | 30%
DevOps/Infrastructure | 660 | 24 | 27.5 | 10%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 16 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 4 weeks
Deliverables:
• Architecture document
• Database schema
• Infrastructure setup
Phase 2: Development - Core Features (Backend Engineering)
Duration: | 4 weeks
Deliverables:
• Real-time progress tracking API
• Document management system
Phase 3: Development - Core Features (Data Engineering)
Duration: | 4 weeks
Deliverables:
• Real-time progress tracking API integration
• Document management system integration
Phase 4: Testing & QA
Duration: | 3 weeks
Deliverables:
• Real-time progress tracking API tests
• Document management system integration tests
Phase 5: Deployment & Handoff
Duration: | 4 weeks
Deliverables:
• Real-time progress tracking API deployment
• Document management system integration documentation
KEY MILESTONES
Milestone | Week
Kickoff | 0
Go-Live | 15

## Backend Engineering
BACKEND ENGINEERING - COST BREAKDOWN
Total Cost: | 4180
Total Hours: | 134
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design PostgreSQL schema for construction project management with progress tracking | N/A | 24 | 0 | 0
Implement WebSocket service for real-time progress updates across team dashboards | N/A | 30 | 0 | 0
Design REST API for real-time project progress updates | N/A | 20 | 0 | 0
Implement document OCR (Optical Character Recognition) for construction logs and project schedules | N/A | 15 | 0 | 0
Design database schema for collaborative document management with project stakeholders | N/A | 20 | 0 | 0
Implement REST API for document management with project stakeholders | N/A | 25 | 0 | 0

## Data Engineering
DATA ENGINEERING - COST BREAKDOWN
Total Cost: | 4530
Total Hours: | 151
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design PostgreSQL schema for construction project management with progress tracking | N/A | 24 | 0 | 0
Implement WebSocket service for real-time progress updates across team dashboards | N/A | 16 | 0 | 0
Configure real-time data processing pipeline for construction logs and project schedules | N/A | 12 | 0 | 0
Build web scraping tool for extracting construction progress updates from public sources | N/A | 10 | 0 | 0
Implement collaborative document management system for project stakeholders | N/A | 14 | 0 | 0
Design real-time permission system for multi-role access control | N/A | 16 | 0 | 0
Integrate web scraping tool with real-time data processing pipeline | N/A | 8 | 0 | 0
Implement user authentication and authorization system | N/A | 15 | 0 | 0
Configure server and database for multi-tenant environment support | N/A | 10 | 0 | 0
Perform initial code reviews and integration testing for the real-time data processing pipeline | N/A | 12 | 0 | 0
Deploy the real-time data processing pipeline and collaborative document management system | N/A | 8 | 0 | 0
Provide initial user training sessions on new systems | N/A | 6 | 0 | 0

## DevOps-Infrastructure
DEVOPS-INFRASTRUCTURE - COST BREAKDOWN
Total Cost: | 660
Total Hours: | 24
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design PostgreSQL schema for construction project management with progress tracking | N/A | 24 | 0 | 0

## Sample Guidance
GUIDANCE FROM UPLOADED SAMPLE DOCUMENTS
This estimation was guided by the patterns extracted from your uploaded sample cost estimate documents:
### 1. How Tasks are Categorized and Numbered
The cost estimate document provided includes tasks categorized into several distinct areas: Development, Testing, Deployment, Support, and Infrastructure. Each area is further divided into specific subtasks for clarity.
#### Development:
- **Task Breakdown**:
- Requirement Analysis (2 hours)
- Design Implementation (4 hours)
- Coding (6 hours)
- Unit Testing (3 hours)
#### Testing:
- **Task Breakdown**:
- Integration Testing (5 hours)
- System Testing (7 hours)
- Performance Testing (4 hours)
- User Acceptance Testing (2 hours)
#### Deployment:
- **Task Breakdown**:
- Pre-Deployment Setup (6 hours)
- Deploy Application (3 hours)
- Monitor and Log (1 hour)
#### Support:
- **Task Breakdown**:
- Initial Issue Resolution (4 hours)
- Regular Maintenance (5 hours)
- Troubleshooting (2 hours)
#### Infrastructure:
- **Task Breakdown**:
- Network Configuration (8 hours)
- Database Setup (6 hours)
- Server Installation and Configuration (7 hours)
- Security Audit (3 hours)
### 2. Typical Effort Estimation Patterns
The typical effort estimation patterns for each area are as follows:
#### Development:
- **Hours**:
- Requirement Analysis: 2 hours
- Design Implementation: 4 hours
- Coding: 6 hours
- Unit Testing: 3 hours
#### Testing:
- **Days**:
- Integration Testing: 5 days
- System Testing: 7 days
- Performance Testing: 4 days
- User Acceptance Testing: 2 days
#### Deployment:
- **Hours**:
- Pre-Deployment Setup: 6 hours
- Deploy Application: 3 hours
- Monitor and Log: 1 hour
#### Support:
- **Hours**:
- Initial Issue Resolution: 4 hours
- Regular Maintenance: 5 hours
- Troubleshooting: 2 hours
#### Infrastructure:
- **Days**:
- Network Configuration: 8 days
- Database Setup: 6 days
- Server Installation and Configuration: 7 days
- Security Audit: 3 days
### 3. Team Composition Patterns
The team composition for each task area is as follows:
#### Development:
- **Team Size**: