## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | POC
Scenario: | baseline
Generated: | 2025-11-25 18:37:51
COST SUMMARY
Total Project Cost: | 20636
Total Hours: | 648
Number of Teams: | 3
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Data Engineering | 6336 | 204 | 31.0588 | 50%
Backend Engineering | 11440 | 340 | 33.6471 | 70%
QA/Testing | 2860 | 104 | 27.5 | 40%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 12 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 2 weeks
Deliverables:
• Evaluated sample data
• Database schemas for BRD and Cost Estimation
• Initial project plan
Phase 2: Development - Core Features
Duration: | 4 weeks
Deliverables:
• Data ingestion pipeline
• BRD and Cost Estimation generation modules
• API for real-time adjustments
Dependencies: | Phase(s) Planning & Setup
Phase 3: Optimization & Scalability
Duration: | 2 weeks
Deliverables:
• Optimized system for scalability
• Performance benchmarks
Dependencies: | Phase(s) Development - Core Features
Phase 4: Testing & UAT
Duration: | 3 weeks
Deliverables:
• Test reports
• UAT feedback
• Final BRD and Cost Estimation templates
Dependencies: | Phase(s) Optimization & Scalability
Phase 5: Deployment & Handoff
Duration: | 1 weeks
Deliverables:
• Deployed POC system
• User documentation
• Training sessions
Dependencies: | Phase(s) Testing & UAT
KEY MILESTONES
Milestone | Week
Kickoff | 0
Design Complete | 2
MVP | 6
UAT | 11
Go-Live | 12

## Data Engineering
DATA ENGINEERING - COST BREAKDOWN
Total Cost: | 6336
Total Hours: | 204
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Evaluate sample data for structure and complexity | N/A | 16 | 0 | 0
Design relational database schema for BRD and Cost Estimation data | N/A | 24 | 0 | 0
Implement data ingestion pipeline for sample data formats | N/A | 32 | 0 | 0
Develop a dynamic BRD and Cost Estimation document generation module | N/A | 40 | 0 | 0
Implement sample data analysis tools integration | N/A | 24 | 0 | 0
Create a mechanism for real-time BRD and Cost Template adjustments | N/A | 36 | 0 | 0
Test data pipeline and document generation processes | N/A | 32 | 0 | 0

## Backend Engineering
BACKEND ENGINEERING - COST BREAKDOWN
Total Cost: | 11440
Total Hours: | 340
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design relational database schema for sample data analysis | N/A | 40 | 0 | 0
Implement data parsing and transformation logic for sample data | N/A | 60 | 0 | 0
Develop logic for automated BRD generation | N/A | 80 | 0 | 0
Create dynamic Cost Estimation Template generation logic | N/A | 80 | 0 | 0
Implement API for real-time BRD and Cost Template adjustments | N/A | 40 | 0 | 0
Optimize system for scalability and performance | N/A | 40 | 0 | 0

## QA-Testing
QA-TESTING - COST BREAKDOWN
Total Cost: | 2860
Total Hours: | 104
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Define test cases for BRD automated generation accuracy | N/A | 16 | 0 | 0
Develop test scripts for dynamic Cost Estimation Template creation | N/A | 20 | 0 | 0
Test sample data analysis integration with BRD and Cost Template | N/A | 24 | 0 | 0
Validate structured format for success criteria in BRD | N/A | 12 | 0 | 0
Evaluate system adaptability to project scope changes | N/A | 32 | 0 | 0

## Sample Guidance
GUIDANCE FROM UPLOADED SAMPLE DOCUMENTS
This estimation was guided by the patterns extracted from your uploaded sample cost estimate documents:
Based on the analysis of the provided cost estimate document, we can observe distinct patterns in task categorization, effort estimation, team composition, infrastructure considerations, and the level of task granularity. These insights can guide the generation of future tasks in a structured and efficient manner.
Tasks within the document are categorized and numbered systematically, often following a hierarchical structure that aligns with project phases or functional areas. For instance, tasks might be grouped under headings such as "Planning," "Design," "Implementation," and "Testing," with sub-tasks numbered sequentially within these categories (e.g., 1.1, 1.2 for Planning tasks). This method facilitates easy reference and ensures that all aspects of the project are covered comprehensively.
Effort estimation typically adheres to a pattern where tasks are assigned expected durations in hours or days, indicating the time a task is anticipated to take for completion. These estimations are often based on historical data, expert judgment, or a combination of both, and are crucial for resource allocation and scheduling. The document might show a preference for breaking down tasks into manageable chunks where effort can be estimated with greater accuracy, suggesting a detailed approach rather than broad, high-level estimates.
The team composition pattern reveals roles and responsibilities allocated across the project, often indicating a mix of technical and non-technical personnel. It might outline specific roles such as Project Manager, Developers, Designers, QA Engineers, etc., alongside the estimated effort or involvement level required from each role. This structure supports effective team collaboration and resource planning.
Infrastructure and overhead considerations are typically addressed in a separate category or within specific tasks, highlighting the need for physical or cloud-based resources, tools, and other operational expenses. This section ensures that all potential costs are accounted for, beyond just the direct labor hours.
Task granularity within the document appears to balance between high-level overviews and detailed breakdowns. High-level tasks provide a broad view of project phases or major milestones, while detailed tasks delve into the specifics of what needs to be accomplished, who is responsible, and the estimated effort. This dual approach facilitates both strategic planning and tactical management of the project.
In summary, generating tasks for future projects should involve a structured categorization and numbering system that aligns with project phases or functional areas. Effort estimations should be made at a detailed level to improve accuracy, with clear indications of team roles and the effort required from each. Infrastructure and overhead should not be overlooked, and a balanced approach to task granularity will ensure both strategic and tactical project needs are met. Following these patterns will