## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | POC
Scenario: | baseline
Generated: | 2025-11-25 18:44:20
COST SUMMARY
Total Project Cost: | 28996
Total Hours: | 736
Number of Teams: | 3
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
AI/ML Engineering | 9680 | 244 | 39.6721 | 70%
Backend Engineering | 10516 | 276 | 38.1014 | 60%
DevOps/Infrastructure | 8800 | 216 | 40.7407 | 50%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 12 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 2 weeks
Deliverables:
• Architecture document
• Database schema designs
• Initial cloud infrastructure setup
• Data privacy and compliance plan
Phase 2: Development - Core Features
Duration: | 3 weeks
Deliverables:
• ML model for requirement extraction
• Data extraction pipeline
• API for document processing
• CI/CD pipeline setup
Dependencies: | Phase(s) 1
Phase 3: Feature Completion & Integration
Duration: | 3 weeks
Deliverables:
• Dynamic Cost Estimation Template generator
• Real-time data analysis integration
• Backend and AI/ML integration complete
Dependencies: | Phase(s) 2
Phase 4: Testing & UAT
Duration: | 2 weeks
Deliverables:
• System-wide integration testing report
• User Acceptance Testing (UAT) feedback
• Performance optimization report
Dependencies: | Phase(s) 3
Phase 5: Deployment & Handoff
Duration: | 2 weeks
Deliverables:
• Production deployment
• Final documentation
• Training materials for end-users
• Project handoff report
Dependencies: | Phase(s) 4
KEY MILESTONES
Milestone | Week
Kickoff | 0
Architecture Complete | 2
Core Development Complete | 5
Integration Complete | 8
UAT Complete | 10
Go-Live | 12

## AI-ML Engineering
AI-ML ENGINEERING - COST BREAKDOWN
Total Cost: | 9680
Total Hours: | 244
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Develop ML model for extracting requirements from project documents | N/A | 60 | 0 | 0
Implement data extraction pipeline for sample data analysis | N/A | 40 | 0 | 0
Design relational database schema for managing extracted data | N/A | 24 | 0 | 0
Automate validation and quality checks for extracted data | N/A | 32 | 0 | 0
Create dynamic Cost Estimation Template generator | N/A | 48 | 0 | 0
Integrate real-time data analysis into BRD and cost estimation | N/A | 40 | 0 | 0

## Backend Engineering
BACKEND ENGINEERING - COST BREAKDOWN
Total Cost: | 10516
Total Hours: | 276
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design relational database schema for BRD and cost estimation data storage | N/A | 40 | 0 | 0
Develop API for integrating with document processing tools | N/A | 32 | 0 | 0
Implement machine learning model for requirements extraction | N/A | 80 | 0 | 0
Create dynamic Excel template generator for cost estimation | N/A | 40 | 0 | 0
Implement automated validation and quality checks for data extraction | N/A | 24 | 0 | 0
Develop real-time data analysis and incorporation system for BRD and cost templates | N/A | 60 | 0 | 0

## DevOps-Infrastructure
DEVOPS-INFRASTRUCTURE - COST BREAKDOWN
Total Cost: | 8800
Total Hours: | 216
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Set up scalable cloud infrastructure for document processing and data analysis | N/A | 40 | 0 | 0
Implement CI/CD pipeline for rapid POC development and deployment | N/A | 32 | 0 | 0
Ensure data privacy and compliance with GDPR and other regulations | N/A | 24 | 0 | 0
Design relational database schema for structured data storage | N/A | 16 | 0 | 0
Configure automated data extraction and validation tools | N/A | 40 | 0 | 0
Develop dynamic cost estimation template generation module | N/A | 48 | 0 | 0
Monitor and optimize cloud infrastructure for cost and performance | N/A | 16 | 0 | 0

## Sample Guidance
GUIDANCE FROM UPLOADED SAMPLE DOCUMENTS
This estimation was guided by the patterns extracted from your uploaded sample cost estimate documents:
Given the constraints of not being able to directly analyze uploaded documents, I'll provide a general framework based on common practices in cost estimate documentation that should help guide task generation. This framework is constructed from typical patterns observed in project management and cost estimation across various industries.
1. **Task Categorization and Numbering**: Tasks in cost estimate documents are often categorized based on the phase of the project (planning, execution, monitoring, closing) or the nature of the work (development, testing, deployment, maintenance). They are usually numbered sequentially within each category, often using a hierarchical system (e.g., 1.0, 1.1, 1.1.1) that reflects the breakdown from high-level tasks to more specific sub-tasks. This allows for easy reference and organization.
2. **Effort Estimation Patterns**: Effort estimations are typically given in hours or days, depending on the granularity of the task. High-level tasks might be estimated in days or weeks, while more detailed tasks could be estimated in hours. It's common to see a range (e.g., 8-10 hours) to account for variability. These estimations often take into account historical data, the complexity of the task, and the expertise of the team members.
3. **Team Composition Patterns**: The team composition is usually outlined in terms of roles rather than specific individuals (e.g., Developer, Project Manager, QA Tester). This section might include the number of team members required for each role and their estimated contribution in terms of time. It's also common to see assumptions about the level of effort (% of full-time) expected from each role throughout the project.
4. **Infrastructure and Overhead Patterns**: Costs associated with infrastructure (e.g., servers, software licenses) and overhead (e.g., administrative support, office space) are often listed separately from direct labor costs. These might be fixed costs or variable costs depending on the project duration and complexity. Overhead rates are sometimes applied as a percentage of direct labor costs.
5. **Task Granularity**: The level of detail in task descriptions can vary widely. High-level tasks provide a broad overview of the project scope, while detailed tasks offer specific, actionable items. The choice between high-level and detailed granularity depends on the project stage, the audience of the document, and the level of certainty about project requirements.
In generating tasks based on cost estimate documents, it's crucial to start by understanding the project's scope as outlined in the categorized and numbered task list. This list will