## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | POC
Scenario: | baseline
Generated: | 2025-11-26 04:33:51
COST SUMMARY
Total Project Cost: | 9999
Total Hours: | 310
Number of Teams: | 3
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Data Engineering | 4070 | 120 | 33.9167 | 50%
DevOps/Infrastructure | 4334 | 132 | 32.8333 | 30%
QA/Testing | 1595 | 58 | 27.5 | 20%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 8 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 2 weeks
Deliverables:
• Sample Data Analysis Report
• Data Integration Design Document
• Document Processing Environment Setup
• Secure Data Handling Procedures
Phase 2: Development & Configuration
Duration: | 3 weeks
Deliverables:
• Technical Requirements for BRD
• Cost Estimation Template with Sample Data
• Automated Document Generation Scripts
• Version Control Setup
• Continuous Integration Pipeline for Documents
Dependencies: | Phase(s) Planning & Setup
Phase 3: Testing & Validation
Duration: | 2 weeks
Deliverables:
• Stakeholder Validation Report for BRD & Cost Template
• Security Audit Report
• BRD Structure Validation
• Sample Data Accuracy Validation
• Usability Test Report for Cost Estimation Template
• Success Criteria Alignment Check
Dependencies: | Phase(s) Development & Configuration
Phase 4: Final Review & Handoff
Duration: | 1 weeks
Deliverables:
• Final Business Requirements Document (BRD)
• Final Cost Estimation Template
• Project Documentation
• Handoff & Training Materials
Dependencies: | Phase(s) Testing & Validation
KEY MILESTONES
Milestone | Week
Kickoff | 0
Design Complete | 2
MVP | 5
UAT Complete | 7
Go-Live | 8

## Data Engineering
DATA ENGINEERING - COST BREAKDOWN
Total Cost: | 4070
Total Hours: | 120
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Analyze sample data structure and volume | N/A | 16 | 0 | 0
Design data integration process for BRD and Cost Estimation Template | N/A | 24 | 0 | 0
Define technical requirements for BRD | N/A | 20 | 0 | 0
Develop Cost Estimation Template in Excel | N/A | 32 | 0 | 0
Incorporate sample data into Cost Estimation Template | N/A | 16 | 0 | 0
Validate BRD and Cost Estimation Template with stakeholders | N/A | 12 | 0 | 0

## DevOps-Infrastructure
DEVOPS-INFRASTRUCTURE - COST BREAKDOWN
Total Cost: | 4334
Total Hours: | 132
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Set up document processing environment for BRD and Cost Template creation | N/A | 8 | 0 | 0
Implement secure data handling procedures for sample data | N/A | 16 | 0 | 0
Automate BRD and Cost Estimation document generation | N/A | 24 | 0 | 0
Implement version control for document templates and sample data | N/A | 12 | 0 | 0
Establish continuous integration pipeline for document updates | N/A | 32 | 0 | 0
Conduct security audit on document processing and data handling | N/A | 40 | 0 | 0

## QA-Testing
QA-TESTING - COST BREAKDOWN
Total Cost: | 1595
Total Hours: | 58
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Review and validate the structure of the Business Requirements Document (BRD) | N/A | 8 | 0 | 0
Validate the accuracy of sample data representation in BRD and Cost Estimation Template | N/A | 16 | 0 | 0
Test the usability of the Cost Estimation Template with non-technical stakeholders | N/A | 12 | 0 | 0
Ensure alignment of success criteria in BRD with project objectives | N/A | 6 | 0 | 0
Conduct document processing technology test for BRD and Cost Estimation Template creation | N/A | 16 | 0 | 0