## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | POC
Scenario: | baseline
Generated: | 2025-11-26 04:36:03
COST SUMMARY
Total Project Cost: | 9988
Total Hours: | 288
Number of Teams: | 2
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Data Engineering | 6292 | 184 | 34.1957 | 50%
Document Processing | 3696 | 104 | 35.5385 | 50%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 8 weeks
EXECUTION PHASES
Phase 1: Initial Analysis & Design
Duration: | 2 weeks
Deliverables:
• Initial Sample Data Analysis Report
• Preliminary BRD Outline
Phase 2: Development & Documentation
Duration: | 3 weeks
Deliverables:
• Data Preprocessing Pipeline
• Draft BRD
• Excel-based Cost Estimation Template
Dependencies: | Phase(s) Initial Analysis & Design
Phase 3: Testing, QA & Finalization
Duration: | 2 weeks
Deliverables:
• Data Quality Report
• Final BRD
• Final Cost Estimation Template
Dependencies: | Phase(s) Development & Documentation
Phase 4: Review & Handoff
Duration: | 1 weeks
Deliverables:
• Finalized Business Requirements Document
• Formatted Cost Estimation Template
• Project Documentation
Dependencies: | Phase(s) Testing, QA & Finalization
KEY MILESTONES
Milestone | Week
Kickoff | 0
Development Complete | 3
UAT | 5
Go-Live | 8

## Data Engineering
DATA ENGINEERING - COST BREAKDOWN
Total Cost: | 6292
Total Hours: | 184
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Analyze sample data for insights relevant to BRD and cost estimation | N/A | 32 | 0 | 0
Develop data preprocessing pipeline for continuous analysis | N/A | 40 | 0 | 0
Ensure data quality and integrity for sample data | N/A | 24 | 0 | 0
Create Excel-based Cost Estimation Template incorporating data insights | N/A | 40 | 0 | 0
Draft Business Requirements Document (BRD) integrating technical and cost analysis | N/A | 48 | 0 | 0

## Document Processing
DOCUMENT PROCESSING - COST BREAKDOWN
Total Cost: | 3696
Total Hours: | 104
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Analyze provided sample data for BRD insights | N/A | 16 | 0 | 0
Draft the Business Requirements Document (BRD) | N/A | 40 | 0 | 0
Create a detailed Cost Estimation Template in Excel | N/A | 24 | 0 | 0
Ensure BRD and Cost Template alignment with project scope | N/A | 16 | 0 | 0
Format documents for both technical and non-technical stakeholders | N/A | 8 | 0 | 0