## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | POC
Scenario: | baseline
Generated: | 2025-11-26 04:38:15
COST SUMMARY
Total Project Cost: | 5456
Total Hours: | 172
Number of Teams: | 2
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Document Processing | 2684 | 84 | 31.9524 | 50%
Data Engineering | 2772 | 88 | 31.5 | 50%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 8 weeks
EXECUTION PHASES
Phase 1: Initial Planning & Data Analysis
Duration: | 2 weeks
Deliverables:
• Project Scope Analysis
• Sample Data Structure and Quality Report
• Initial Data Processing Scripts
Phase 2: BRD & Cost Estimation Development
Duration: | 2 weeks
Deliverables:
• Business Requirements Document Template
• Cost Estimation Excel Template
• Data Analysis Integration Report
Dependencies: | Phase(s) Initial Planning & Data Analysis
Phase 3: Sample Data Integration & Refinement
Duration: | 2 weeks
Deliverables:
• BRD with Integrated Sample Data Analysis
• Refined Cost Estimation Template
• Scalability Plan for Data Processing
Dependencies: | Phase(s) BRD & Cost Estimation Development
Phase 4: Finalization & Review
Duration: | 2 weeks
Deliverables:
• Final Business Requirements Document
• Reviewed and Finalized Cost Estimation Template
Dependencies: | Phase(s) Sample Data Integration & Refinement
KEY MILESTONES
Milestone | Week
Kickoff | 0
Data Analysis Complete | 2
BRD & Cost Template Draft Complete | 4
Integration & Refinement Complete | 6
Go-Live | 8

## Document Processing
DOCUMENT PROCESSING - COST BREAKDOWN
Total Cost: | 2684
Total Hours: | 84
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Analyze and Document Technical Requirements from Project Scope and Sample Data | N/A | 16 | 0 | 0
Create Business Requirements Document Template | N/A | 8 | 0 | 0
Develop Cost Estimation Excel Template | N/A | 12 | 0 | 0
Incorporate Sample Data Analysis into BRD and Cost Estimation | N/A | 24 | 0 | 0
Finalize Business Requirements Document | N/A | 16 | 0 | 0
Review and Refine Cost Estimation Template with Sample Data Insights | N/A | 8 | 0 | 0

## Data Engineering
DATA ENGINEERING - COST BREAKDOWN
Total Cost: | 2772
Total Hours: | 88
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Analyze sample data for structure and quality assessment | N/A | 16 | 0 | 0
Develop data processing scripts for sample data analysis | N/A | 24 | 0 | 0
Integrate data analysis findings into the BRD | N/A | 8 | 0 | 0
Create a Cost Estimation Template based on sample data analysis | N/A | 16 | 0 | 0
Design scalability plan for data processing | N/A | 24 | 0 | 0