## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | Full Service
Scenario: | baseline
Generated: | 2025-11-26 10:00:52
COST SUMMARY
Total Project Cost: | 0
Total Hours: | 0
Number of Teams: | 0
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 12 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 2 weeks
Deliverables:
• Database schema design
• Initial UI mockups
• User authentication system plan
Phase 2: Development - Core Features
Duration: | 4 weeks
Deliverables:
• API for data ingestion
• Interactive dashboards
• ETL pipeline setup
• External areas quantification feature
Dependencies: | Phase(s) Planning & Setup
Phase 3: Enhancements & Integration
Duration: | 3 weeks
Deliverables:
• Secured API endpoints
• Database optimization
• Support for complex project structures
• Dynamic reporting tool
Dependencies: | Phase(s) Development - Core Features
Phase 4: Testing & QA
Duration: | 2 weeks
Deliverables:
• Backend API testing suite
• UI/UX testing report
• Data processing pipeline validation
• Performance testing results
Dependencies: | Phase(s) Enhancements & Integration
Phase 5: Deployment & Handoff
Duration: | 1 weeks
Deliverables:
• System documentation
• Logging and monitoring setup
• Final performance optimizations
• Feature validation report
Dependencies: | Phase(s) Testing & QA
KEY MILESTONES
Milestone | Week
Kickoff | 0
Design Complete | 2
MVP | 6
UAT | 10
Go-Live | 12