## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | Full Service
Scenario: | baseline
Generated: | 2025-11-26 10:04:07
COST SUMMARY
Total Project Cost: | 0
Total Hours: | 0
Number of Teams: | 0
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 12 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 2 weeks
Deliverables:
• Architecture document
• Database schema for architectural data
• Initial OCR model prototype
Phase 2: Development - Core Features
Duration: | 4 weeks
Deliverables:
• Implemented document processing pipeline
• Algorithms for level counting and GFA measurement
• External area quantification module
• OCR and computer vision integration
Dependencies: | Phase(s) Planning & Setup
Phase 3: User Interface & Experience Development
Duration: | 3 weeks
Deliverables:
• Dashboard for project tracking
• Responsive design implementation
Dependencies: | Phase(s) Development - Core Features
Phase 4: Testing & QA
Duration: | 2 weeks
Deliverables:
• Comprehensive system testing report
• User acceptance testing (UAT) feedback
Dependencies: | Phase(s) User Interface & Experience Development
Phase 5: Deployment & Handoff
Duration: | 1 weeks
Deliverables:
• System deployment to production
• Final documentation
• Training materials for end-users
Dependencies: | Phase(s) Testing & QA
KEY MILESTONES
Milestone | Week
Kickoff | 0
Design Complete | 2
Core Feature Development Complete | 6
UI/UX Development Complete | 9
UAT Complete | 11
Go-Live | 12