## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | Full Service
Scenario: | baseline
Generated: | 2025-11-26 11:43:34
COST SUMMARY
Total Project Cost:
Total Hours:
Number of Teams: | 5
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Backend Engineering | 10948 | 332 | 32.9759 | 70%
Frontend/UI Engineering | 7341.6 | 268 | 27.394 | 60%
Data Engineering | 10810 | 332 | 32.5602 | 50%
QA/Testing | 4945 | 172 | 28.75 | 40%
DevOps/Infrastructure | 8832 | 260 | 33.9692 | 50%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 12 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 2 weeks
Deliverables:
• Database schema design
• Development environment setup
• UI design plan
Phase 2: Development - Core Features
Duration: | 4 weeks
Deliverables:
• APIs for data import/export
• Document processing service
• Real-time collaboration system
• Multi-role access control
Dependencies: | Phase(s) Planning & Setup
Phase 3: Testing & UAT
Duration: | 3 weeks
Deliverables:
• API integration testing report
• Load testing report
• User acceptance testing feedback
Dependencies: | Phase(s) Development - Core Features
Phase 4: Deployment & Handoff
Duration: | 3 weeks
Deliverables:
• Deployment to production environment
• System documentation and user guides
• Training sessions for end-users
Dependencies: | Phase(s) Testing & UAT
KEY MILESTONES
Milestone | Week
Kickoff | 0
Design Complete | 2
MVP | 6
UAT | 9
Go-Live | 12

## Backend Engineering
BACKEND ENGINEERING - COST BREAKDOWN
Total Cost: | 10948
Total Hours: | 332
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design relational database schema for architectural and user data | N/A | 32 | 0 | 0
Implement RESTful API for architectural data import/export | N/A | 40 | 0 | 0
Develop real-time collaboration system | N/A | 48 | 0 | 0
Create document processing service for plan data extraction | N/A | 60 | 0 | 0
Integrate multi-role access control system | N/A | 36 | 0 | 0
Setup the development environment for real-time and database systems | N/A | 16 | 0 | 0
Conduct API integration testing with architectural software | N/A | 24 | 0 | 0
Perform load testing on real-time collaboration features | N/A | 32 | 0 | 0
Document API endpoints and real-time collaboration usage | N/A | 20 | 0 | 0
Database and API deployment to production environment | N/A | 24 | 0 | 0

## Frontend-UI Engineering
FRONTEND-UI ENGINEERING - COST BREAKDOWN
Total Cost: | 7341.6
Total Hours: | 268
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design interactive UI for architectural plan uploads and data extraction | N/A | 32 | 0 | 0
Implement real-time collaborative features for architectural plan review | N/A | 40 | 0 | 0
Develop multi-role access control system for project data | N/A | 36 | 0 | 0
Integrate UI with architectural software for data import/export | N/A | 48 | 0 | 0
Optimize UI for efficient handling of medium complexity architectural data | N/A | 40 | 0 | 0
Conduct usability testing for the architectural data extraction UI | N/A | 24 | 0 | 0
Prepare documentation for frontend features and user guide | N/A | 16 | 0 | 0
Implement feedback loop for continuous UI improvement | N/A | 32 | 0 | 0

## Data Engineering
DATA ENGINEERING - COST BREAKDOWN
Total Cost: | 10810
Total Hours: | 332
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design relational database schema for architectural data and user permissions | N/A | 32 | 0 | 0
Implement data extraction pipeline for architectural plans | N/A | 40 | 0 | 0
Create API for integration with architectural software | N/A | 36 | 0 | 0
Develop real-time collaboration system | N/A | 48 | 0 | 0
Set up role-based access control (RBAC) system | N/A | 24 | 0 | 0
Perform integration testing with architectural software | N/A | 40 | 0 | 0
Optimize data processing pipeline for scale | N/A | 32 | 0 | 0
Develop user documentation and system usage guides | N/A | 24 | 0 | 0
Deploy the system to a cloud environment | N/A | 16 | 0 | 0
Conduct user acceptance testing (UAT) with project teams | N/A | 40 | 0 | 0

## QA-Testing
QA-TESTING - COST BREAKDOWN
Total Cost: | 4945
Total Hours: | 172
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Automated API testing for data extraction endpoints | N/A | 32 | 0 | 0
UI/UX compliance testing for real-time collaboration features | N/A | 40 | 0 | 0
Data validation testing for gross floor area calculations | N/A | 36 | 0 | 0
Integration testing with architectural software | N/A | 24 | 0 | 0
Load testing for multi-user real-time collaboration | N/A | 40 | 0 | 0

## DevOps-Infrastructure
DEVOPS-INFRASTRUCTURE - COST BREAKDOWN
Total Cost: | 8832
Total Hours: | 260
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Configure scalable cloud infrastructure for real-time processing | N/A | 32 | 0 | 0
Implement relational database using PostgreSQL for architectural data | N/A | 40 | 0 | 0
Set up CI/CD pipeline for automated deployment and integration | N/A | 24 | 0 | 0
Implement WebSocket service for real-time collaboration features | N/A | 48 | 0 | 0
Configure secure access and multi-role access control | N/A | 36 | 0 | 0
Design and implement data import/export integration with architectural software | N/A | 40 | 0 | 0
Set up monitoring and logging for system health and performance tracking | N/A | 16 | 0 | 0
Plan and execute load testing to validate scalability and real-time processing | N/A | 24 | 0 | 0