## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | Full Service
Scenario: | baseline
Generated: | 2025-11-26 11:46:34
COST SUMMARY
Total Project Cost:
Total Hours:
Number of Teams: | 4
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Backend Engineering | 8004 | 244 | 32.8033 | 70%
Frontend/UI Engineering | 9549.6 | 372 | 25.671 | 60%
AI/ML Engineering | 10971 | 330 | 33.2455 | 50%
QA/Testing | 6785 | 236 | 28.75 | 40%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 12 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 2 weeks
Deliverables:
• Database schema design
• Infrastructure setup
• UI design mockups
• PostgreSQL schema for tracking
Phase 2: Development - Core Features
Duration: | 4 weeks
Deliverables:
• API for real-time updates
• Data processing module
• GFA measurement tool
• ML model for architectural elements
Dependencies: | Phase(s) Planning & Setup
Phase 3: Integration & Advanced Development
Duration: | 3 weeks
Deliverables:
• Secure data access
• UI integration with backend
• Real-time collaboration features
• Document processing pipeline
Dependencies: | Phase(s) Development - Core Features
Phase 4: Testing & QA
Duration: | 2 weeks
Deliverables:
• Backend system QA
• UI testing suite
• ML model and system reliability QA
• Usability testing
Dependencies: | Phase(s) Integration & Advanced Development
Phase 5: Deployment & Handoff
Duration: | 1 weeks
Deliverables:
• System documentation
• Training materials
• Final system deployment
Dependencies: | Phase(s) Testing & QA
KEY MILESTONES
Milestone | Week
Kickoff | 0
Design Complete | 2
Core Development Complete | 6
Integration Complete | 9
UAT Complete | 11
Go-Live | 12

## Backend Engineering
BACKEND ENGINEERING - COST BREAKDOWN
Total Cost: | 8004
Total Hours: | 244
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design relational database schema for architectural elements and construction stages | N/A | 32 | 0 | 0
Implement API for real-time construction plan updates | N/A | 40 | 0 | 0
Develop a data processing module for architectural drawing extraction | N/A | 48 | 0 | 0
Secure data access control for project stakeholders | N/A | 24 | 0 | 0
Set up a scalable cloud-based relational database | N/A | 16 | 0 | 0
Implement automated backup and recovery strategy for the database | N/A | 20 | 0 | 0
Quality assurance and testing of the API and data processing modules | N/A | 40 | 0 | 0
Documentation of the backend system and APIs | N/A | 24 | 0 | 0

## Frontend-UI Engineering
FRONTEND-UI ENGINEERING - COST BREAKDOWN
Total Cost: | 9549.6
Total Hours: | 372
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design interactive UI for inputting architectural plans | N/A | 40 | 0 | 0
Implement measurement tools for Gross Floor Area (GFA) in UI | N/A | 60 | 0 | 0
Develop UI components for external area quantification | N/A | 48 | 0 | 0
Integrate UI with document processing backend | N/A | 32 | 0 | 0
Implement support for staged/portion/part plans in UI | N/A | 56 | 0 | 0
Develop real-time collaboration features for plan updates | N/A | 64 | 0 | 0
Create comprehensive UI testing suite | N/A | 40 | 0 | 0
Optimize UI for various devices and screen sizes | N/A | 32 | 0 | 0

## AI-ML Engineering
AI-ML ENGINEERING - COST BREAKDOWN
Total Cost: | 10971
Total Hours: | 330
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Develop ML model for identifying and counting architectural elements | N/A | 60 | 0 | 0
Automate measurement of Gross Floor Area (GFA) from plans | N/A | 40 | 0 | 0
Implement algorithm for quantifying external areas | N/A | 40 | 0 | 0
Develop a system for handling staged/portion/part plans | N/A | 50 | 0 | 0
Integrate real-time update capability for construction plans | N/A | 32 | 0 | 0
Design PostgreSQL schema for construction project tracking | N/A | 24 | 0 | 0
Implement document processing pipeline for architectural drawings | N/A | 36 | 0 | 0
Conduct testing and QA for ML model accuracy and system reliability | N/A | 48 | 0 | 0

## QA-Testing
QA-TESTING - COST BREAKDOWN
Total Cost: | 6785
Total Hours: | 236
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Define test cases for architectural drawing identification and counting | N/A | 32 | 0 | 0
Validate measurement accuracy of Gross Floor Area (GFA) | N/A | 40 | 0 | 0
Test quantification accuracy for external areas | N/A | 36 | 0 | 0
Ensure real-time update mechanism integrity | N/A | 48 | 0 | 0
Perform usability testing on frontend interfaces | N/A | 40 | 0 | 0
Verify handling of staged/portion/part plans and multi-level plans | N/A | 40 | 0 | 0