## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | Full Service
Scenario: | baseline
Generated: | 2025-11-26 11:51:50
COST SUMMARY
Total Project Cost:
Total Hours:
Number of Teams: | 4
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Backend Engineering | 10603 | 328 | 32.3262 | 70%
Frontend/UI Engineering | 8648 | 268 | 32.2687 | 60%
AI/ML Engineering | 17280 | 576 | 30 | 50%
QA/Testing | 9085 | 316 | 28.75 | 40%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 12 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 2 weeks
Deliverables:
• Database schema design
• UI/UX design mockups
• AI/ML project plan
• Infrastructure setup plan
Phase 2: Development - Core Features
Duration: | 4 weeks
Deliverables:
• REST API endpoints
• Document processing integration
• Real-time collaboration features
• Dynamic data visualization
Dependencies: | Phase(s) Planning & Setup
Phase 3: Enhancements & Integration
Duration: | 3 weeks
Deliverables:
• System scalability enhancements
• Front-end and back-end integration
• WebSocket service for real-time updates
Dependencies: | Phase(s) Development - Core Features
Phase 4: Testing & UAT
Duration: | 2 weeks
Deliverables:
• Backend system testing report
• Frontend responsive design test report
• AI model accuracy report
• User Acceptance Testing (UAT) feedback
Dependencies: | Phase(s) Enhancements & Integration
Phase 5: Deployment & Handoff
Duration: | 1 weeks
Deliverables:
• Deployment plan execution
• Backend and frontend documentation
• User training and handoff documentation
Dependencies: | Phase(s) Testing & UAT
KEY MILESTONES
Milestone | Week
Kickoff | 0
Design Complete | 2
Core Development Complete | 6
UAT Complete | 10
Go-Live | 12

## Backend Engineering
BACKEND ENGINEERING - COST BREAKDOWN
Total Cost: | 10603
Total Hours: | 328
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design relational database schema for construction data management | N/A | 32 | 0 | 0
Implement REST API for project and construction plan management | N/A | 40 | 0 | 0
Integrate document processing for architectural plan analysis | N/A | 48 | 0 | 0
Develop real-time system for collaboration among construction teams | N/A | 36 | 0 | 0
Design data model for staged/portion/part plans management | N/A | 28 | 0 | 0
Ensure system scalability for handling multiple users and data sources | N/A | 40 | 0 | 0
Integrate front-end interfaces for real-time collaboration | N/A | 24 | 0 | 0
Conduct comprehensive testing for backend systems | N/A | 40 | 0 | 0
Prepare deployment plan and environment setup | N/A | 16 | 0 | 0
Document backend architecture and API endpoints | N/A | 24 | 0 | 0

## Frontend-UI Engineering
FRONTEND-UI ENGINEERING - COST BREAKDOWN
Total Cost: | 8648
Total Hours: | 268
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design responsive UI for architectural plan uploads and data entry | N/A | 32 | 0 | 0
Implement real-time collaboration features for construction teams | N/A | 40 | 0 | 0
Integrate frontend with document processing APIs for plan analysis | N/A | 36 | 0 | 0
Develop dynamic data visualization for GFA and External Area calculations | N/A | 40 | 0 | 0
Create feedback mechanism for users to report inaccuracies or bugs | N/A | 24 | 0 | 0
Implement responsive design testing across various devices | N/A | 32 | 0 | 0
User testing sessions for UI/UX feedback on construction project management features | N/A | 40 | 0 | 0
Prepare documentation for frontend features and user guides | N/A | 24 | 0 | 0

## AI-ML Engineering
AI-ML ENGINEERING - COST BREAKDOWN
Total Cost: | 17280
Total Hours: | 576
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Develop OCR and image processing system for architectural plan analysis | N/A | 80 | 0 | 0
Implement algorithm for automated counting of levels excluding/including basement | N/A | 60 | 0 | 0
Design and implement GFA measurement algorithm | N/A | 40 | 0 | 0
Develop system for quantification of External Area | N/A | 40 | 0 | 0
Create real-time collaboration platform for construction teams | N/A | 120 | 0 | 0
Integrate AI models with backend for automated data extraction | N/A | 32 | 0 | 0
Continuous training pipeline for model improvement | N/A | 60 | 0 | 0
Design PostgreSQL schema for construction project tracking | N/A | 24 | 0 | 0
Implement WebSocket service for real-time team updates | N/A | 40 | 0 | 0
Comprehensive testing of AI models and real-time systems | N/A | 80 | 0 | 0

## QA-Testing
QA-TESTING - COST BREAKDOWN
Total Cost: | 9085
Total Hours: | 316
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Validate accuracy of level counting in architectural plans | N/A | 32 | 0 | 0
Verify Gross Floor Area (GFA) calculation accuracy from plans | N/A | 40 | 0 | 0
Test quantification accuracy of external areas | N/A | 36 | 0 | 0
Assess real-time collaboration feature performance and reliability | N/A | 48 | 0 | 0
Conduct performance testing for scalability | N/A | 56 | 0 | 0
Implement security testing protocols | N/A | 64 | 0 | 0
Facilitate User Acceptance Testing (UAT) for construction teams | N/A | 40 | 0 | 0