## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | Full Service
Scenario: | baseline
Generated: | 2025-11-26 11:55:45
COST SUMMARY
Total Project Cost:
Total Hours:
Number of Teams: | 5
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Backend Engineering | 9982 | 296 | 33.723 | 70%
AI/ML Engineering | 14030 | 424 | 33.0896 | 60%
Frontend/UI Engineering | 10064.8 | 376 | 26.7681 | 50%
QA/Testing | 5175 | 180 | 28.75 | 40%
DevOps/Infrastructure | 7268 | 220 | 33.0364 | 30%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 12 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 2 weeks
Deliverables:
• Database schema for architectural elements
• Initial ML model design
• UI design prototype
• Project infrastructure plan
Phase 2: Development - Core Features
Duration: | 4 weeks
Deliverables:
• API endpoints for data handling
• Document processing implementation
• ML models for level identification and GFA measurement
• Interactive architectural plan visualization
Dependencies: | Phase(s) Planning & Setup
Phase 3: Integration & Advanced Feature Development
Duration: | 3 weeks
Deliverables:
• Data integrity and security measures
• Integration of ML models with frontend
• Support for complex architectural plans
Dependencies: | Phase(s) Development - Core Features
Phase 4: Testing & QA
Duration: | 2 weeks
Deliverables:
• ML model and algorithm validation
• Backend and frontend performance reports
• Usability testing feedback
Dependencies: | Phase(s) Integration & Advanced Feature Development
Phase 5: Deployment, Documentation & Training
Duration: | 1 weeks
Deliverables:
• Deployment to production
• API and system documentation
• User training sessions
Dependencies: | Phase(s) Testing & QA
KEY MILESTONES
Milestone | Week
Kickoff | 0
Design Complete | 2
Core Feature Completion | 6
Integration Complete | 9
UAT Complete | 11
Go-Live | 12

## Backend Engineering
BACKEND ENGINEERING - COST BREAKDOWN
Total Cost: | 9982
Total Hours: | 296
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design relational database schema for architectural elements and quantifications | N/A | 40 | 0 | 0
Implement RESTful API for architectural plan data ingestion | N/A | 32 | 0 | 0
Develop API endpoints for data retrieval and manipulation | N/A | 48 | 0 | 0
Implement document processing for architectural plans | N/A | 60 | 0 | 0
Ensure data integrity and security for sensitive documents | N/A | 36 | 0 | 0
Develop a data validation and error handling mechanism | N/A | 24 | 0 | 0
Create a system for handling staged/portion/part plans | N/A | 40 | 0 | 0
Implement backup and recovery strategies for the database | N/A | 16 | 0 | 0

## AI-ML Engineering
AI-ML ENGINEERING - COST BREAKDOWN
Total Cost: | 14030
Total Hours: | 424
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Develop ML model for identifying and counting above and below ground levels | N/A | 80 | 0 | 0
Implement algorithm for measuring Gross Floor Area (GFA) | N/A | 60 | 0 | 0
Design relational database schema for architectural elements quantification | N/A | 32 | 0 | 0
Develop data extraction pipeline from architectural plans | N/A | 40 | 0 | 0
Implement quantification algorithm for External Area | N/A | 60 | 0 | 0
Create API for integration of ML models and algorithms with front-end application | N/A | 40 | 0 | 0
Testing and validation of ML models and algorithms | N/A | 48 | 0 | 0
Prepare deployment plan for ML models and data pipeline | N/A | 24 | 0 | 0
Document API usage and integration guidelines | N/A | 16 | 0 | 0
Conduct training sessions for end-users on the AI/ML system | N/A | 24 | 0 | 0

## Frontend-UI Engineering
FRONTEND-UI ENGINEERING - COST BREAKDOWN
Total Cost: | 10064.8
Total Hours: | 376
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design interactive UI for document upload and review | N/A | 40 | 0 | 0
Implement visualization tool for architectural plans | N/A | 60 | 0 | 0
Develop feature for identification and counting of levels | N/A | 32 | 0 | 0
Create functionality for GFA measurement and documentation | N/A | 48 | 0 | 0
Implement external area quantification tools | N/A | 40 | 0 | 0
Ensure UI supports staged/portion/part plans | N/A | 36 | 0 | 0
Optimize UI for non-technical user interaction | N/A | 24 | 0 | 0
Conduct usability testing with target user groups | N/A | 32 | 0 | 0
Implement feedback and optimize UI performance | N/A | 40 | 0 | 0
Prepare comprehensive user documentation | N/A | 24 | 0 | 0

## QA-Testing
QA-TESTING - COST BREAKDOWN
Total Cost: | 5175
Total Hours: | 180
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Develop test cases for document processing accuracy | N/A | 40 | 0 | 0
Test backend API performance for large architectural document uploads | N/A | 32 | 0 | 0
Validate database integrity and relationships | N/A | 24 | 0 | 0
Usability testing of frontend application with real user scenarios | N/A | 36 | 0 | 0
Automate regression testing for staged/portion/part plans handling | N/A | 48 | 0 | 0

## DevOps-Infrastructure
DEVOPS-INFRASTRUCTURE - COST BREAKDOWN
Total Cost: | 7268
Total Hours: | 220
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design and implement scalable cloud infrastructure for architectural project documentation | N/A | 32 | 0 | 0
Implement CI/CD pipelines for document processing application | N/A | 40 | 0 | 0
Configure relational database service for project data management | N/A | 16 | 0 | 0
Set up data backup and disaster recovery strategy | N/A | 24 | 0 | 0
Implement monitoring and alerting for system health and performance | N/A | 20 | 0 | 0
Ensure compliance with data protection and privacy regulations | N/A | 28 | 0 | 0
Design database schema for construction project management with progress tracking | N/A | 24 | 0 | 0
Automate scalability of document processing workload | N/A | 36 | 0 | 0