## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | Full Service
Scenario: | baseline
Generated: | 2025-11-26 17:19:52
COST SUMMARY
Total Project Cost:
Total Hours:
Number of Teams: | 3
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Backend Engineering | 10315.5 | 299 | 34.5 | 70%
Frontend/UI Engineering | 12489 | 362 | 34.5 | 20%
Scraping/Data Collection | 828 | 24 | 34.5 | 10%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 36 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 4 weeks
Deliverables:
• Architecture document
• Database schema
Phase 2: Development - Core Features (Part 1)
Duration: | 8 weeks
Deliverables:
• Database schema for architectural plans and site sections
Dependencies: | Phase(s) Phase 1
Phase 3: Development - Core Features (Part 2)
Duration: | 8 weeks
Deliverables:
• Database schema for multi-project management and collaboration features
Dependencies: | Phase(s) Phase 2
Phase 4: Testing & QA
Duration: | 6 weeks
Deliverables:
• Real-time progress updates using WebSockets and Node.js for team dashboards
Dependencies: | Phase(s) Phase 3
Phase 5: Deployment & Handoff
Duration: | 4 weeks
Deliverables:
• Cloud-based storage configuration for project documents and data management
Dependencies: | Phase(s) Phase 4
KEY MILESTONES
Milestone | Week
Kickoff | 0
Go-Live | 12

## Backend Engineering
BACKEND ENGINEERING - COST BREAKDOWN
Total Cost: | 10315.5
Total Hours: | 299
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design PostgreSQL schema for construction project management with progress tracking | N/A | 24 | 0 | 0
Implement REST API endpoints for project progress tracking and management | N/A | 30 | 0 | 0
Design database schema for architectural plans and site sections | N/A | 20 | 0 | 0
Implement real-time progress tracking and document processing capabilities | N/A | 35 | 0 | 0
Design database schema for multi-level site sections and architectural plans | N/A | 25 | 0 | 0
Implement document processing capabilities for various types of construction documents | N/A | 30 | 0 | 0
Design database schema for multi-project management and collaboration features | N/A | 32 | 0 | 0
Implement REST API for project creation, update, and deletion | N/A | 35 | 0 | 0
Implement WebSocket service for real-time progress updates across team dashboards and notifications | N/A | 40 | 0 | 0
Implement multi-level site sections with detailed level information on the site | N/A | 28 | 0 | 0

## Frontend-UI Engineering
FRONTEND-UI ENGINEERING - COST BREAKDOWN
Total Cost: | 12489
Total Hours: | 362
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design database schema for construction project management with progress tracking | N/A | 24 | 0 | 0
Implement real-time progress updates using WebSockets and Node.js for team dashboards | N/A | 40 | 0 | 0
Create responsive design for mobile access using React Native | N/A | 48 | 0 | 0
Integrate Site Sections with Level Information using Geospatial Technologies | N/A | 30 | 0 | 0
Implement Document Processing Capabilities including PDFs, Excel files, and images using OCR technology | N/A | 60 | 0 | 0
Develop user interfaces for project management using Angular and Material Design | N/A | 40 | 0 | 0
Configure cloud-based storage for project documents and data management | N/A | 40 | 0 | 0
Implement real-time notifications and alerts for progress updates using Firebase Cloud Messaging (FCM) | N/A | 40 | 0 | 0
Develop a user manual for the construction management system | N/A | 40 | 0 | 0

## Scraping-Data Collection
SCRAPING-DATA COLLECTION - COST BREAKDOWN
Total Cost: | 828
Total Hours: | 24
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design database schema for construction project management with progress tracking | N/A | 24 | 0 | 0

## Sample Guidance
GUIDANCE FROM UPLOADED SAMPLE DOCUMENTS
This estimation was guided by the patterns extracted from your uploaded sample cost estimate documents:
### 1. How Tasks are Categorized and Numbered
The cost estimate documents provided follow a structured categorization of tasks, typically divided into high-level categories such as "Development," "Testing," "Deployment," and "Support." Each category is further broken down into detailed subtasks that represent specific work units or activities within the project scope. For example:
- Development: Subtasks include coding, unit testing, integration testing, system testing, and user acceptance testing.
- Testing: Subtasks encompass functional testing, performance testing, security testing, and regression testing.
- Deployment: Tasks involve installation, configuration, monitoring, and post-deployment support.
- Support: This category includes maintenance activities like bug fixes, updates, and customer assistance.
### 2. Typical Effort Estimation Patterns
The effort estimation patterns in these documents are generally based on historical data or expert judgment to determine the time required for each task. Commonly used metrics include:
- **Hours**: The most straightforward approach where tasks are estimated in hours.
- **Days**: Tasks are also often broken down into days, which can be a more granular way of estimating effort.
For example, if a project has 10 subtasks under the "Development" category, each task might be estimated as follows:
- Coding: 3 days
- Unit Testing: 2 days
- Integration Testing: 4 days
### 3. Team Composition Patterns
The team composition patterns in these documents are typically based on the project's current workforce and future projections of skill levels. Commonly used metrics include:
- **Current Workforce**: The number of developers, testers, deployment specialists, etc., currently employed.
- **Skill Levels**: Tasks might be assigned to specific team members based on their expertise level.
For instance, if a project needs 10 days for coding and the current workforce includes three developers with varying levels of experience in this area, the effort could be distributed as follows:
- Developer A: 3 days
- Developer B: 2 days
- Developer C: 4 days
### 4. Infrastructure and Overhead Patterns
Infrastructure and overhead patterns are estimated based on historical data or project-specific information about resource allocation. Commonly used metrics include:
- **Resource Allocation**: Tasks might be assigned to specific resources, such as servers, databases, or software tools.
- **Overheads**: These can include costs for utilities, maintenance, training, and other non-project-related expenses.
For example, if a project requires 10 days of server time