## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | Full Service
Scenario: | baseline
Generated: | 2025-11-26 17:41:12
COST SUMMARY
Total Project Cost:
Total Hours:
Number of Teams: | 3
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Backend Engineering | 7038 | 204 | 34.5 | 70%
ML Engineering | 6540 | 218 | 30 | 30%
Data Engineering | 6831 | 198 | 34.5 | 10%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 28 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 4 weeks
Deliverables:
• Architecture document
• Database schema
• Infrastructure setup
Phase 2: Development - Core Features
Duration: | 8 weeks
Deliverables:
• Real-time progress tracking system
• WebSocket service
• Deployment infrastructure setup
Dependencies: | Phase(s) Planning & Setup
Phase 3: Testing & QA
Duration: | 4 weeks
Deliverables:
• Predictive models for risk assessment
• AI algorithms trained for defect detection
• Deployment infrastructure setup, Documentation
Dependencies: | Phase(s) Development - Core Features
Phase 4: Deployment & Handoff
Duration: | 8 weeks
Deliverables:
• Production deployment
• User manuals, API documentation, other necessary documents
Dependencies: | Phase(s) Testing & QA
Phase 5: Final Deliverables
Duration: | 4 weeks
Deliverables:
• Final project documentation, training materials
Dependencies: | Phase(s) Deployment & Handoff
KEY MILESTONES
Milestone | Week
Kickoff | 0
Planning & Setup | 4
Development - Core Features | 12
Testing & QA | 16
Deployment & Handoff | 20
Final Deliverables | 24

## Backend Engineering
BACKEND ENGINEERING - COST BREAKDOWN
Total Cost: | 7038
Total Hours: | 204
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Implement REST API for project management | N/A | 20 | 0 | 0
Design database schema for construction project management with progress tracking | N/A | 24 | 0 | 0
Implement real-time progress tracking system | N/A | 20 | 0 | 0
Design database schema for construction data management (Architectural Drawings) | N/A | 20 | 0 | 0
Design database schema for gross floor area measurement (Architectural General Arrangement Plans) | N/A | 20 | 0 | 0
Design database schema for external area measurement (Architectural Site Plan) | N/A | 20 | 0 | 0
Design database schema for construction project tracking with entities: Project, Task, Resource, Progress | N/A | 20 | 0 | 0
Design database schema for construction project management with entities: Project, Task, Resource, Progress, and Team Members | N/A | 20 | 0 | 0
Design database schema for construction project management with entities: Project, Task, Resource, Progress, and Team Members (advanced) | N/A | 40 | 0 | 0

## ML Engineering
ML ENGINEERING - COST BREAKDOWN
Total Cost: | 6540
Total Hours: | 218
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Create project scope document | N/A | 24 | 0 | 0
Analyze key features to implement (context #2) | N/A | 16 | 0 | 0
Check tech stack requirements (context #3) | N/A | 8 | 0 | 0
Calibrate with complexity (context #4) | N/A | 8 | 0 | 0
Design database schema for construction project management with progress tracking | N/A | 24 | 0 | 0
Implement WebSocket service for real-time progress updates across team dashboards | N/A | 20 | 0 | 0
Configure hardware and software for project management tools (context #5) | N/A | 16 | 0 | 0
Implement web scraping (if needed) to gather initial data (context #5) | N/A | 16 | 0 | 0
Develop predictive models for risk assessment (context #5) | N/A | 20 | 0 | 0
Train AI algorithms for defect detection in drawings (context #5) | N/A | 30 | 0 | 0
Implement deployment infrastructure (context #5) | N/A | 20 | 0 | 0
Documentation: Write user manuals, API documentation, and other necessary documents (context #5) | N/A | 16 | 0 | 0

## Data Engineering
DATA ENGINEERING - COST BREAKDOWN
Total Cost: | 6831
Total Hours: | 198
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design PostgreSQL schema for construction project management with progress tracking | N/A | 24 | 0 | 0
Create data cleaning pipeline using Python and Pandas | N/A | 16 | 0 | 0
Implement real-time progress updates using WebSocket in a web application | N/A | 40 | 0 | 0
Set up AWS S3 bucket for storing project documents and images | N/A | 12 | 0 | 0
Implement a simple data visualization tool using Tableau or similar software | N/A | 20 | 0 | 0
Implement a script for extracting data from various sources using Python libraries | N/A | 18 | 0 | 0
Configure monitoring tools for project performance tracking | N/A | 12 | 0 | 0
Perform initial testing of the data pipeline using JUnit for unit tests and integration testing with end-to-end scenarios | N/A | 24 | 0 | 0
Document project governance and approval processes using a simple text editor or wiki tool | N/A | 8 | 0 | 0
Implement a script for extracting data from various sources using Python libraries (continued) | N/A | 24 | 0 | 0

## Sample Guidance
GUIDANCE FROM UPLOADED SAMPLE DOCUMENTS
This estimation was guided by the patterns extracted from your uploaded sample cost estimate documents:
### 1. How tasks are categorized and numbered
The cost estimate document provided is structured in a hierarchical manner, starting with the overall project scope followed by specific tasks broken down into sub-tasks. The tasks are sequentially numbered to ensure clarity and maintainability.
- **Category:** The document begins with an overview of the project’s objectives and high-level goals.
- **Numbering System:** Tasks are sequentially numbered within each category, ensuring a logical flow from broad to detailed work items.
### 2. Typical effort estimation patterns (hours/days)
The typical effort estimation pattern in this cost estimate is based on historical data and expert judgment. The document uses both hours and days as units of measurement for task estimates:
- **Hours:** Tasks are estimated in terms of the number of hours required to complete each item.
- **Days:** Some tasks are also broken down into days, indicating a more granular effort estimate.
### 3. Team composition patterns
The team composition pattern is detailed and includes information on the roles and responsibilities of key personnel involved in the project:
- **Roles and Responsibilities:** Each task is assigned to specific individuals or teams based on their expertise and availability.
- **Responsibility Assignment Matrix (RAM):** A matrix is used to map tasks to responsible parties, ensuring accountability.
### 4. Infrastructure and overhead patterns
The infrastructure and overhead pattern includes details about the necessary resources and costs associated with running the project:
- **Infrastructure Costs:** The document specifies hardware and software requirements, including licenses and maintenance fees.
- **Overheads:** Overhead costs such as utilities, insurance, and other administrative expenses are estimated.
### 5. Task granularity (high-level vs detailed)
The task granularity in this cost estimate is high level, focusing on broad categories of work without delving into specific details:
- **High-Level Tasks:** The document outlines the major tasks that need to be completed.
- **Detailed Tasks:** Specific sub-tasks are not provided, which means each item is estimated based on a general understanding rather than detailed breakdowns.
### Summary
This cost estimate document provides a clear and structured overview of the project scope. It categorizes tasks into high-level categories with sequential numbering for clarity. Effort estimates are given in hours or days, indicating a balance between broad planning and detailed task estimation. The team composition is well-documented, ensuring accountability through responsibility assignment matrices. Infrastructure costs and overheads are specified but not detailed, focusing on the essentials rather than specific resources. Finally, the task granularity is high