## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | Full Service
Scenario: | baseline
Generated: | 2025-11-26 17:46:47
COST SUMMARY
Total Project Cost:
Total Hours:
Number of Teams: | 3
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Backend Engineering | 7728 | 224 | 34.5 | 70%
Data Engineering | 8280 | 240 | 34.5 | 20%
QA/Testing | 828 | 24 | 34.5 | 10%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 36 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 4 weeks
Deliverables:
• Architecture document
• Database schema
Phase 2: Development - Core Features
Duration: | 8 weeks
Deliverables:
• Real-time progress tracking system
• Multi-level access control system
• Staged/portion/part plans handling system
• Gross floor area calculation
• Building area measurement
Dependencies: | Phase(s) Phase 1
Phase 3: Development - Integration
Duration: | 8 weeks
Deliverables:
• Integration with real-time progress tracking system for multi-level projects
• Real-time collaboration tool integration
• System handling staged/portion/part plans with multiple pages per level on architectural drawings
• Live collaboration tool implementation
Dependencies: | Phase(s) Phase 2
Phase 4: Testing & QA
Duration: | 8 weeks
Deliverables:
• Database schema for construction project management with progress logging and multi-project management capabilities
• Real-time progress tracking system integration
• Live collaboration tool implementation
Dependencies: | Phase(s) Phase 3
Phase 5: Deployment & Training
Duration: | 4 weeks
Deliverables:
• System ready for production deployment
• User training materials
Dependencies: | Phase(s) Phase 4
KEY MILESTONES
Milestone | Week
Kickoff | 0
Go-Live | 12

## Backend Engineering
BACKEND ENGINEERING - COST BREAKDOWN
Total Cost: | 7728
Total Hours: | 224
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design PostgreSQL schema for construction project management with progress tracking | N/A | 24 | 0 | 0
Implement WebSocket service for real-time progress updates across team dashboards | N/A | 32 | 0 | 0
Design REST API for project management endpoints | N/A | 24 | 0 | 0
Implement multi-level access control system for construction teams with real-time permissions | N/A | 40 | 0 | 0
Design and implement staged/portion/part plans handling system for construction drawings | N/A | 48 | 0 | 0
Develop gross floor area calculation functionality including basement levels and external areas | N/A | 32 | 0 | 0
Implement building area measurement excluding the building footprint | N/A | 24 | 0 | 0

## Data Engineering
DATA ENGINEERING - COST BREAKDOWN
Total Cost: | 8280
Total Hours: | 240
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design PostgreSQL schema for construction project tracking with progress logging and multi-project management capabilities | N/A | 24 | 0 | 0
Develop RESTful API for real-time progress tracking across team dashboards | N/A | 16 | 0 | 0
Implement WebSocket service for real-time progress updates across team dashboards | N/A | 16 | 0 | 0
Develop real-time progress tracking system for multi-level projects | N/A | 40 | 0 | 0
Calculate gross floor area including basement levels and external areas for multi-story projects | N/A | 24 | 0 | 0
Measure building area excluding the building footprint for multi-story projects | N/A | 16 | 0 | 0
Create integration with real-time progress tracking system for multiple levels on a multi-story building project | N/A | 16 | 0 | 0
Develop system for handling staged/portion/part plans with multiple pages per level on architectural drawings | N/A | 32 | 0 | 0
Implement live collaboration tool for multi-level construction projects | N/A | 16 | 0 | 0
Develop system for handling multi-level construction project progress tracking with real-time updates and live collaboration | N/A | 40 | 0 | 0

## QA-Testing
QA-TESTING - COST BREAKDOWN
Total Cost: | 828
Total Hours: | 24
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design database schema for construction project management with progress tracking | N/A | 24 | 0 | 0

## Sample Guidance
GUIDANCE FROM UPLOADED SAMPLE DOCUMENTS
This estimation was guided by the patterns extracted from your uploaded sample cost estimate documents:
### 1. How Tasks are Categorized and Numbered
The cost estimate document provided includes tasks categorized into several distinct sections, each with its own numbering scheme:
- **Project Overview**: This section typically covers the project's scope, objectives, timeline, budget, and key stakeholders. It is numbered sequentially from 1 to 4.
- **Resource Allocation**: Here, resources such as personnel, equipment, and materials are allocated based on their availability and required for each task. The tasks in this section are numbered from 5 onwards.
- **Task Breakdown Structure (TBS)**: This part details the specific tasks that need to be completed within each phase of the project. It is organized hierarchically with parent-child relationships, where higher-level tasks lead to lower-level sub-tasks. For instance:
- Task 101: Project Kickoff
- Sub-task 102: Stakeholder Engagement
- Sub-task 103: Scope Definition
- **Infrastructure and Overhead**: This section includes the costs associated with setting up project infrastructure, such as servers, software licenses, and other operational expenses. The tasks in this section are numbered from 15 onwards.
### 2. Typical Effort Estimation Patterns (Hours/Days)
The typical effort estimation patterns for each task can be summarized as follows:
- **Project Overview**: Tasks here require minimal effort, often estimated in hours or days depending on the project's complexity and scope.
- **Resource Allocation**: This section involves significant effort allocation based on resource availability. Effort is typically measured in hours or days.
- **Task Breakdown Structure (TBS)**: The tasks within this section are more detailed and require higher estimation accuracy, often estimated in hours or days. For example:
- Task 102: Stakeholder Engagement
- Sub-task 102.1: Initial Meeting
- Estimated effort: 5 hours
- **Infrastructure and Overhead**: This section involves significant overhead costs that are typically estimated in days.
### 3. Team Composition Patterns
The team composition patterns can be summarized as follows:
- The project is led by a Project Manager (PM), who oversees the entire project.
- A dedicated Resource Management Specialist manages resource allocation, ensuring tasks are completed on time and within budget.
- Various functional teams such as Development, QA, Design, and Business Analysts contribute to specific tasks.
### 4. Infrastructure and Overhead Patterns
Infrastructure costs can be estimated in days