## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | Full Service
Scenario: | baseline
Generated: | 2025-11-26 17:48:54
COST SUMMARY
Total Project Cost:
Total Hours:
Number of Teams: | 3
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Backend Engineering | 8832 | 256 | 34.5 | 70%
Frontend/UI Engineering | 1500 | 50 | 30 | 25%
QA/Testing | 7383 | 214 | 34.5 | 5%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 40 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 4 weeks
Deliverables:
• Architecture document
• Database schema
• Infrastructure setup
Phase 2: Development - Core Features
Duration: | 8 weeks
Dependencies: | Phase(s) Phase 1
Phase 3: Development - Core Features (continued)
Duration: | 8 weeks
Dependencies: | Phase(s) Phase 2
Phase 4: Testing & QA
Duration: | 6 weeks
Dependencies: | Phase(s) Phase 2
Phase 5: Deployment & Handoff
Duration: | 8 weeks
Dependencies: | Phase(s) Phase 4
Phase 6: Documentation & Training
Duration: | 8 weeks
Dependencies: | Phase(s) Phase 5
KEY MILESTONES
Milestone | Week
Kickoff | 0
Go-Live | 40

## Backend Engineering
BACKEND ENGINEERING - COST BREAKDOWN
Total Cost: | 8832
Total Hours: | 256
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design database schema for construction project management with progress tracking | N/A | 24 | 0 | 0
Implement REST API endpoints for project tracking and progress updates | N/A | 32 | 0 | 0
Configure WebSocket service for live progress tracking across teams | N/A | 20 | 0 | 0
Implement authentication and authorization for user management system | N/A | 28 | 0 | 0
Configure database connection parameters for PostgreSQL and Node.js environment setup | N/A | 20 | 0 | 0
Create a dashboard interface for project management and progress tracking | N/A | 32 | 0 | 0
Implement unit tests for API endpoints using Jest framework | N/A | 24 | 0 | 0
Perform security testing on the backend system | N/A | 20 | 0 | 0
Deploy the backend system on AWS EC2 instance with SSL certificate and load balancer setup | N/A | 32 | 0 | 0
Create detailed documentation for project management and API endpoints | N/A | 24 | 0 | 0

## Frontend-UI Engineering
FRONTEND-UI ENGINEERING - COST BREAKDOWN
Total Cost: | 1500
Total Hours: | 50
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design architectural site plans | N/A | 20 | 0 | 0
Develop interactive user interface for project management | N/A | 30 | 0 | 0

## QA-Testing
QA-TESTING - COST BREAKDOWN
Total Cost: | 7383
Total Hours: | 214
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design database schema for construction project management with progress tracking | N/A | 24 | 0 | 0
Implement real-time progress updates via WebSocket service | N/A | 28 | 0 | 0
Configure web scraping for extracting site plans data from public databases | N/A | 32 | 0 | 0
Create mockup and user interface design for mobile app interface | N/A | 20 | 0 | 0
Perform system testing for real-time progress updates | N/A | 24 | 0 | 0
Configure email notifications for progress updates and project alerts | N/A | 18 | 0 | 0
Implement user feedback mechanism for feature improvements | N/A | 24 | 0 | 0
Document project management process for future reference | N/A | 20 | 0 | 0
Prepare project documentation for submission to client | N/A | 24 | 0 | 0

## Sample Guidance
GUIDANCE FROM UPLOADED SAMPLE DOCUMENTS
This estimation was guided by the patterns extracted from your uploaded sample cost estimate documents:
### 1. How Tasks are Categorized and Numbered
The cost estimate document provided is structured in a way that categorizes tasks into specific categories, which helps in organizing the project scope clearly. The tasks are numbered sequentially to ensure consistency and ease of reference.
### 2. Typical Effort Estimation Patterns (Hours/Days)
The typical effort estimation patterns for each task vary significantly based on the complexity and requirements of the project. For example, high-level tasks such as "System Design" often require an initial estimate in days or hours, whereas detailed tasks like "Database Implementation" might be estimated in terms of hours.
### 3. Team Composition Patterns
The team composition patterns are not explicitly provided in this document but can be inferred from the project's scope and requirements. The document mentions that the project involves multiple teams working together, including developers, designers, and QA testers. This indicates a distributed or multi-team approach to project management.
### 4. Infrastructure and Overhead Patterns
The infrastructure and overhead patterns are not detailed in this particular document but can be inferred from the overall cost breakdown. The document suggests that significant portions of the budget go towards hardware costs (e.g., servers, storage), software licensing fees, and administrative expenses related to project management tools.
### 5. Task Granularity (High-Level vs Detailed)
The task granularity is high-level in nature, focusing on broad categories such as "System Design," "Database Implementation," and "User Interface Development." This approach allows for a quick overview of the project's scope without delving into detailed technical specifications or specific implementation details.
### Summary
To generate tasks effectively from this cost estimate document, one should first categorize tasks based on their nature (e.g., high-level vs detailed) to ensure that the most relevant information is extracted. The typical effort estimation patterns can be estimated in hours or days depending on the complexity of each task. Team composition patterns indicate a multi-team approach, which may require additional resources and management overhead.
Infrastructure and overhead costs should be factored into the overall budget analysis but are not detailed here. High-level tasks provide a quick overview without delving into specific implementation details, making them suitable for initial project planning stages.