## Master Summary
PROJECT COST ESTIMATION - MASTER SUMMARY
Project Type: | POC
Scenario: | baseline
Generated: | 2025-11-26 17:57:08
COST SUMMARY
Total Project Cost:
Total Hours:
Number of Teams: | 2
COST BREAKDOWN BY TEAM
Team Name | Total Cost | Total Hours | Average Rate | Allocation %
Backend Engineering | 6600 | 200 | 33 | 70%
Data Engineering | 3432 | 104 | 33 | 30%

## Project Workflow
PROJECT WORKFLOW & TIMELINE
Total Duration: | 28 weeks
EXECUTION PHASES
Phase 1: Planning & Setup
Duration: | 4 weeks
Deliverables:
• Architecture document
• Database schema
• Infrastructure setup
Phase 2: Development - Core Features
Duration: | 8 weeks
Dependencies: | Phase(s) Phase 1
Phase 3: Development - Additional Features
Duration: | 8 weeks
Dependencies: | Phase(s) Phase 1
Phase 4: Testing & QA
Duration: | 6 weeks
Dependencies: | Phase(s) Phase 2, Phase 3
Phase 5: Deployment & Handoff
Duration: | 4 weeks
Dependencies: | Phase(s) Phase 4
KEY MILESTONES
Milestone | Week
Kickoff | 0
Go-Live | 28

## Backend Engineering
BACKEND ENGINEERING - COST BREAKDOWN
Total Cost: | 6600
Total Hours: | 200
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design PostgreSQL schema for construction project tracking with entities: Project, Task, Resource, Progress | N/A | 24 | 0 | 0
Implement WebSocket service for project updates across team dashboards | N/A | 40 | 0 | 0
Configure authentication and authorization systems for project management platform | N/A | 20 | 0 | 0
Design microservices architecture for construction project tracking | N/A | 16 | 0 | 0
Implement key-value store for project data management | N/A | 16 | 0 | 0
Implement frontend integration with backend for user interface | N/A | 20 | 0 | 0
Configure database connection settings for testing environment | N/A | 8 | 0 | 0
Implement basic error handling for project management system | N/A | 16 | 0 | 0
Perform initial data migration for project management system | N/A | 16 | 0 | 0
Set up monitoring and logging infrastructure for the project management system | N/A | 24 | 0 | 0

## Data Engineering
DATA ENGINEERING - COST BREAKDOWN
Total Cost: | 3432
Total Hours: | 104
TASK BREAKDOWN
Task | Phase | Effort (hrs) | Rate | Cost
Design PostgreSQL schema for construction project tracking with entities: Project, Task, Resource, Progress | N/A | 24 | 0 | 0
Implement WebSocket service for real-time progress updates across team dashboards | N/A | 16 | 0 | 0
Create JSON structure for key-value pairs and nested JSON objects | N/A | 16 | 0 | 0
Perform initial filtering and aggregation of sample data | N/A | 16 | 0 | 0
Create a Business Requirement Document (Word) and Cost Estimation Template (Excel) | N/A | 20 | 0 | 0
Prepare cost estimates for sample data files using Excel templates | N/A | 12 | 0 | 0

## Sample Guidance
GUIDANCE FROM UPLOADED SAMPLE DOCUMENTS
This estimation was guided by the patterns extracted from your uploaded sample cost estimate documents:
### Analysis of Cost Estimate Examples
#### 1. How Tasks Are Categorized and Numbered:
The cost estimate examples provided are organized in a structured manner, typically starting with high-level tasks such as "Project Overview" and "Scope Definition." These initial sections lay the groundwork for more detailed breakdowns.
For instance, one document begins with:
- **Project Overview**
- Scope of Work
- Milestones
- Budget Breakdown
Following this, it delves into more specific tasks like:
- **Scope Definition**
- Requirements Gathering
- Stakeholder Analysis
- Risk Assessment
Each task is numbered sequentially to ensure a clear and organized breakdown. This methodical approach helps in tracking progress and ensuring that all aspects of the project are accounted for.
#### 2. Typical Effort Estimation Patterns:
The effort estimation patterns observed vary but generally follow common practices:
- **High-Level Tasks:**
- "Project Overview" might be estimated at 50 hours.
- "Scope Definition" could range from 10 to 30 hours depending on complexity.
- **Detailed Tasks:**
- "Requirements Gathering" might take 20 hours.
- "Stakeholder Analysis" could require 15 hours.
Effort estimates are often based on historical data, project size, and team expertise. This method ensures that tasks are estimated accurately without overestimating or underestimating the actual time required.
#### 3. Team Composition Patterns:
The team composition patterns in these examples include:
- **Project Manager:**
- Typically responsible for overseeing the entire project.
- Estimated to be involved in multiple high-level tasks like "Project Overview" and "Scope Definition."
- **Technical Lead:**
- Handles detailed technical aspects of scope definition, risk assessment, etc.
- Estimates around 15 hours per task.
- **Development Team:**
- Breaks down into smaller teams for specific tasks such as requirements gathering, design, implementation, testing, and documentation.
- Each team member estimates their contribution based on their expertise and experience.
The team composition is often divided into roles that align with the project's needs, ensuring that each task is assigned to the most appropriate person. This approach enhances efficiency and ensures that tasks are completed within budget constraints.
#### 4. Infrastructure and Overhead Patterns:
Infrastructure patterns include:
- **Technology Stack:**
- "Requirements Gathering" might require setting up a basic development environment.
- "Stakeholder Analysis"